## Code Codes
|  | M007 - GR1904063 - Coney Island Sites |  |  |  | Contract Value |  | 187311891.5 |  |  | Total Mhs |  | 364756.4314
[6 empty] | Projected Cost |  | 170627009.32 |  |  | Mhs to Date |  | 139734.5615
Category Total
[27 empty] | 7486040.46 | 2082218.64 | 231109.06 | 40820 | 10750 | -2.2283e-11
SOV ID# | Assigned | Code | Name | Qty | UOM | Mhs | Qty/MH | Projected Forecast |  | Spent to Date | Committed to Date | Qty to Date | Mhs to Date |  |  | SOV % | SOV Total Bill | Billed to Date | Spent>Forecast | $%>qty% | $*75%>qty% | Spent 66% | Committed>Forecast | MH=QTY | QTD>Qty Total | Reforecast Notes | Labor | Subcontract | Consumable | Permanent Material | Equipment | Other
0 | Brian | 00-0001 | SECOND FLOOR APARTMENT REMOVALS | 7 | EA | 0 | 1 | 19333.9 | #DIV/0! | 14032 | 19333.9 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 19333.9 | 0 | 0 | 0 | 0
0 | Brian | 00-0002 | SITE 8 SLAB SHORING | 60 | HR | 60 | 1 | 15736.31 | 262.2718 | 15736.31 | 15736.31 | 60 | 60 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 6521.61 | 0 | 9214.7 | 0 | 0 | 0
0 | Brian | 00-0003 | OG8 Obstruction Removal | 144 | HR | 155.5 | 0.92605 | 17042.53 | 109.5983 | 17042.53 | 17042.53 | 144 | 155.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 17042.53 | 0 | 0 | 0 | 0 | 0
0 | 0 | 00-0004 | Floor Drain PCO | 180.5 | NA | 34 | 5.3088 | 0 |  | 17791.39 | 18807.42 | 180.5 | 164.5 |  |  | 0% | 0 | 0 | TRUE | #DIV/0! | #DIV/0! | #DIV/0! | TRUE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 00-0005 | Equipment Pad PCO | 1 | NA | 1 | 1 | 0 |  | 95.84 | 95.84 | 1 | 1 |  |  | 0% | 0 | 0 | TRUE | #DIV/0! | #DIV/0! | #DIV/0! | TRUE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 00-0006 | Additional Windows PCO | 0 | NA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 00-0007 | IRMA PAGAN APARTMENT MOVE | 0 | NA | 0 | 1 | 2500 |  | 2500 | 2500 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | TRUE | FALSE |  | FALSE |  | 0 | 0 | 2500 | 0 | 0 | 0
0 | 0 | 00-0008 | National Grid Gas Line Relocation | 90.5 | NA | 90.5 | 1 | 11667.88 | 128.9269 | 11667.88 | 11667.88 | 90.5 | 90.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 9920.13 | 0 | 1747.75 | 0 | 0 | 0
0 | 0 | 00-0009 | Bracing for POE Penetration Through SG4 Wall | 44.5 | NA | 44.5 | 1 | 0 |  | 4946.26 | 5942.51 | 44.5 | 44.5 |  |  | 0% | 0 | 0 | TRUE | #DIV/0! | #DIV/0! | #DIV/0! | TRUE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 00-0010 | SG1 RELOCATE BELONGINGS | 161 | NA | 193 | 0.8342 | 57486.84 | 112.8158 | 21773.44 | 22076.26 | 161 | 193 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 53772.02 | 0 | 3714.82 | 0 | 0 | -4.5475e-13
0 | 0 | 00-0011 | PERAMBULATOR ROOM DEMO | 138.5 | NA | 77 | 1.7987 | 20378.14 | 101.856 | 14107.06 | 14107.06 | 138.5 | 138.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 20378.14 | 0 | 0 | 0 | 0 | 0
0 | 0 | 00-0012 | OG8 Tank Removal | 0 | NA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 00-0013 | Exist Bldgs Bracing due to Penetrations | 0 | NA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 00-0014 | SG4 DEMO FOR STEEL BEAMS INSTALL | 13 | NA | 13 | 1 | 0 |  | 1285.34 | 1285.34 | 13 | 13 |  |  | 0% | 0 | 0 | TRUE | #DIV/0! | #DIV/0! | #DIV/0! | TRUE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 00-0015 | SG5 DEMO FOR STEEL BEAMS INSTALL | 17 | NA | 17 | 1 | 0 |  | 1678.93 | 1678.93 | 17 | 17 |  |  | 0% | 0 | 0 | TRUE | #DIV/0! | #DIV/0! | #DIV/0! | TRUE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 00-0016 | OG4 BRACING FOR POE PENETRATION | 36 | NA | 36 | 1 | 0 |  | 6187.46 | 6187.46 | 36 | 36 |  |  | 0% | 0 | 0 | TRUE | #DIV/0! | #DIV/0! | #DIV/0! | TRUE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 00-0017 | National Grid Additional Allowance | 58.5 | NA | 58.5 | 1 | 205770.46 | 100.6403 | 5887.46 | 5887.46 | 58.5 | 58.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 5887.46 | 199883 | 0 | 0 | 0 | 0
0 | Kurston | 00-0018 | SG6 Additional Strobe | 0 | NA | 0 | 1 | 2361.7 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 2361.7 | 0 | 0 | 0 | 0
0 | 0 | 00-0019 | ODWYER FENCE INSTALL | 267.5 | NA | 1356.85 | 0.19715 | 143970.4 | 105.2209 | 29724.91 | 29724.91 | 267.5 | 282.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 143970.4 | 0 | 0 | 0 | 0 | 0
0 | Brian | 00-0021 | MOVE PLAYGROUNDS | 19 | HR | 19 | 1 | 1941.36 | 102.1768 | 1941.36 | 1941.36 | 19 | 19 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 1941.36 | 0 | 0 | 0 | 0 | 0
0 | Brian | 00-0022 | SITE 8 CLEANING | 57 | HR | 57 | 1 | 5968.61 | 104.7125 | 5968.61 | 5968.61 | 57 | 57 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 5968.61 | 0 | 0 | 0 | 0 | 0
0 | #N/A | 00-0023 | S8 FIRE STAND PIPE ACCESS | 61 | HR | 23.5 | 2.5957 | 64306.79 | 117.3264 | 7156.91 | 7156.91 | 61 | 61 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 64306.79 | 0 | 0 | 0 | 0 | 0
0 | #N/A | 00-0024 | Boiler Stack Support | 6.5 | NA | 6.5 | 1 | 796.41 | 122.5246 | 796.41 | 796.41 | 6.5 | 6.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 796.41 | 0 | 0 | 0 | 0 | 0
0 | 0 | 00-1000 | Revenue | 0 | NA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 01-6000 | BUILDING CONDITIONS SUB | 1 | LS | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 01-6100 | CPM SUB | 37 | MO | 0 | 1 | 73150 |  | 48265 | 69685 | 15 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 73150 | 0 | 0 | 0 | 0
0 | Brian | 01-6200 | PHOTO SUB | 37 | MO | 0 | 1 | 87990 |  | 25130 | 87990 | 15 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 87990 | 0 | 0 | 0 | 0
0 | Brian | 01-6300 | OVERHEAD PROTECTION LABOR | 864 | SF | 756.61 | 1.1419 | 79968 | #DIV/0! | 0 | 5820 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 74148 | 0 | 0 | 5820 | 0 | 0
0 | Brian | 01-6310 | OVERHEAD PROTECTION MATERIALS | 239 | LF | 0 | 1 | 35000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 35000 | 0 | 0
0 | 0 | 01-6320 | OVERHEAD PROTECTION EQUIPMENT | 864 | SF | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 01-6400 | RODENT CONTROL SUB | 1 | LS | 0 | 1 | 28596.9 |  | 10573.9 | 38642.09 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | TRUE |  | FALSE |  | 0 | 28596.9 | 0 | 0 | 0 | 0
0 | 0 | 01-6410 | RODENT CONTROL SUB SUPPORT | 1 | LS | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1000 | EROSION CONTROL FABRIC | 34000 | SF | 320 | 106.25 | 32963.2 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 32963.2 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1000 | SGN | 7166 | SF | 67.4447 | 0 | 6947.4792 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1000 | SGS | 7165 | SF | 67.4353 | 0 | 6946.5096 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1000 | OGE | 18440 | SF | 173.5529 | 0 | 17877.6885 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1000 | OGW | 1235 | SF | 11.6235 | 0 | 1197.3398 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1100 | INLET PROTECTION | 96 | EA | 160 | 0.6 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1100 | SGN | 20 | EA | 33.3333 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1100 | SGS | 15 | EA | 25 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1100 | OGE | 25 | EA | 41.6667 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1100 | OGW | 22 | EA | 36.6667 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1100 | S8 | 14 | EA | 23.3333 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1200 | SILT FENCE | 7500 | LF | 160 | 46.875 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1200 | SGN | 1530 | LF | 32.64 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1200 | SGS | 1940 | LF | 41.3867 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1200 | OGE | 1286 | LF | 27.4347 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1200 | OGW | 1739 | LF | 37.0987 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1200 | S8 | 968 | LF | 20.6507 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1300 | STABILIZED CONSTRUCTION ENTRANCE | 8000 | SF | 200 | 40 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1300 | SGN | 1610 | SF | 40.25 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1300 | SGS | 1613 | SF | 40.325 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1300 | OGE | 1580 | SF | 39.5 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1300 | OGW | 1605 | SF | 40.125 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1300 | S8 | 1522 | SF | 38.05 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1400 | MANTAIN EROSION CONTROL | 52 | WK | 312 | 0.16667 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1400 | SGN | 11 | WK | 66 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1400 | SGS | 11 | WK | 66 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1400 | OGE | 11 | WK | 66 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1400 | OGW | 11 | WK | 66 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1400 | S8 | 11 | WK | 66 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1500 | REMOVE EROSION CONTROL | 5 | LO | 160 | 0.03125 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1500 | SGN | 1 | LO | 32 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1500 | SGS | 1 | LO | 32 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1500 | OGE | 1 | LO | 32 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1500 | OGW | 1 | LO | 32 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1500 | S8 | 1 | LO | 32 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1600 | STOCKPILE | 6 | EA | 96 | 0.0625 | 9600 | 112.787 | 3552.79 | 3552.79 | 2.01 | 31.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 9600 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1700 | REMOVE FENCE | 9050 | LF | 634.39 | 14.2657 | 62785.26 | 107.9614 | 20026.84 | 20026.84 | 3430 | 185.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 62785.26 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1700 | SGN | 2350 | LF | 164.7311 | 0 | 16303.3548 |  | 15135.8306 | 0 | 2000 | 140.1967 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1700 | SGS | 2440 | LF | 171.04 | 0 | 16927.7386 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1700 | OGE | 2393 | LF | 167.7453 | 0 | 16601.6715 |  | 10595.0814 | 0 | 1400 | 98.1377 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1700 | OGW | 680 | LF | 47.6669 | 0 | 4717.5665 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1700 | S8 | 1051 | LF | 73.6734 | 0 | 7291.4153 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1800 | REMOVE/REINSTALL BOLLARDS ODG EAST | 32 | EA | 511.99 | 0.062501 | 51378.15 | 104.6533 | 627.92 | 627.92 | 12 | 6 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 51378.15 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1900 | REMOVE FULL DEPTH ASPHALT PVMT | 79200 | SF | 703.16 | 112.6344 | 75977.83 | 111.2035 | 46260.67 | 46260.67 | 46573.38 | 416 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 75977.83 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1900 | SGN | 3750 | SF | 33.2936 | 0 | 3597.4351 |  | 3702.3616 | 0 | 3750 | 33.2936 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1900 | SGS | 13765 | SF | 122.2096 | 0 | 13204.9852 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1900 | OGE | 28350 | SF | 251.6993 | 0 | 27196.6096 |  | 27989.8536 | 0 | 28350 | 251.6993 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1900 | OGW | 31539 | SF | 280.0122 | 0 | 30255.8684 |  | 11821.2752 | 0 | 11973.38 | 106.3031 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-1900 | S8 | 1750 | SF | 15.537 | 0 | 1678.8031 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2000 | REMOVE SITE FURNISHING | 117 | EA | 751.43 | 0.1557 | 77397.6 | 106.8576 | 22440.1 | 22440.1 | 31 | 210 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 77397.6 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2000 | SGN | 36.4874 | EA | 234.3395 | 0 | 24137.0667 |  | 19216.1417 | 0 | 28 | 179.8294 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2000 | SGS | 13 | EA | 83.4922 | 0 | 8599.7333 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2000 | OGE | 19.8824 | EA | 127.694 | 0 | 13152.5333 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2000 | OGW | 23.3782 | EA | 150.1457 | 0 | 15465.0667 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2000 | S8 | 24.2521 | EA | 155.7586 | 0 | 16043.2 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2100 | REMOVE CONCRETE CURB & STEPS | 13000 | LF | 640 | 20.3125 | 64530.23 | 106.7794 | 35824.5 | 35824.5 | 6999.4 | 335.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 64530.23 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2100 | SGN | 164 | LF | 8.0738 | 0 | 814.0737 |  | 525.6834 | 0 | 100 | 4.9231 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2100 | SGS | 2410 | LF | 118.6462 | 0 | 11962.9119 |  | 12616.4008 | 0 | 2400 | 118.1538 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2100 | OGE | 2791 | LF | 137.4031 | 0 | 13854.144 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2100 | OGW | 3941 | LF | 194.0185 | 0 | 19562.5874 |  | 15641.1829 | 0 | 2975.4 | 146.4812 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2100 | S8 | 624 | LF | 30.72 | 0 | 3097.451 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2200 | REMOVE PVMTS | 156053 | SF | 1091.82 | 142.9292 | 107421.11 | 110.2605 | 12018.39 | 12018.39 | 12627.4 | 109 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 107421.11 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2200 | SGN | 30370 | SF | 212.4828 | 0 | 20905.5841 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2200 | SGS | 20125 | SF | 140.8039 | 0 | 13853.3052 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2200 | OGE | 40520 | SF | 283.4969 | 0 | 27892.4684 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2200 | OGW | 41915 | SF | 293.257 | 0 | 28852.7348 |  | 9340.0588 | 0 | 12107.4 | 84.7091 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2200 | S8 | 23123 | SF | 161.7794 | 0 | 15917.0175 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-2300 | BASEMENT MAINTENANCE | 1496 | HR | 2040.37 | 0.7332 | 215616.75 | 109.7754 | 176463.89 | 176463.89 | 1496 | 1607.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 201345.16 | 0 | 14271.59 | 0 | 0 | -3.638e-12
0 | Ricky | 02-3000 | CORE DRILLING | 100 | EA | 766.21 | 0.13051 | 196000 | 400.5735 | 275194.02 | 485806.59 | 81.19 | 687 |  |  | 0% | 0 | 0 | TRUE | TRUE | TRUE | TRUE | TRUE |  | FALSE | waiting for number from ricky | 77038.75 | 116000 | 2961.25 | 0 | 0 | 0
0 | Brian | 02-6000 | OG-7 DEMO LABOR | 1 | EA | 146.05 | 0.006847 | 19934.86 | 199.3486 | 19934.86 | 19934.86 | 0.8 | 100 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 11132.31 | 0 | 8802.55 | 0 | 0 | 1.819e-12
0 | Brian | 02-6001 | OG-7 DEMO EQUIPMENT | 1 | EA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-6002 | OG-7 DEMO MATERIAL | 70 | CY | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6005 | PAINT AND PLASTER REMOVAL IN BASEMENTS | 33320 | SF | 3744.27 | 8.8989 | 368801.61 | 98.5644 | 317476.05 | 317476.05 | 27799.75 | 3221 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE | Get Numbers from SOV; leave as is | 367263.88 | 0 | 1537.73 | 0 | 0 | -1.8645e-11
462 | Kurston | 02-6005 | OG1 | 2040 | SF | 229.241 | 0 | 22579.6904 |  | 22595.012 | 0 | 2040 | 229.241 |  |  | 100% | 60000 | 60000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
642 | Kurston | 02-6005 | OG2 | 1210 | SF | 135.9714 | 0 | 13392.8556 |  | 13401.9434 | 0 | 1210 | 135.9714 |  |  | 100% | 60000 | 60000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
823 | Kurston | 02-6005 | OG3 | 1830 | SF | 205.6427 | 0 | 20255.3105 |  | 20269.0549 | 0 | 1830 | 205.6427 |  |  | 100% | 60000 | 60000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1005 | Kurston | 02-6005 | OG4 | 1750 | SF | 196.6528 | 0 | 19369.8325 |  | 19382.976 | 0 | 1750 | 196.6528 |  |  | 100% | 60000 | 60000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1189 | Kurston | 02-6005 | OG5 | 1630 | SF | 183.1681 | 0 | 18041.6154 |  | 18053.8576 | 0 | 1630 | 183.1681 |  |  | 100% | 60000 | 60000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1372 | Kurston | 02-6005 | OG6 | 3310 | SF | 371.9548 | 0 | 36636.6545 |  | 36661.5146 | 0 | 3310 | 371.9548 |  |  | 80% | 60000 | 48000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
57 | Kurston | 02-6005 | SG1 | 2790 | SF | 313.5208 | 0 | 30881.0472 |  | 13133.3507 | 0 | 1185.75 | 133.2463 |  |  | 100% | 60000 | 60000 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1176 | Kurston | 02-6005 | SG2 | 2370 | SF | 266.3241 | 0 | 26232.2874 |  | 26250.0875 | 0 | 2370 | 266.3241 |  |  | 0% | 60000 | 0 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2577 | Kurston | 02-6005 | SG3 | 3470 | SF | 389.9345 | 0 | 38407.6106 |  | 38433.6724 | 0 | 3470 | 389.9345 |  |  | 0% | 60000 | 0 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2744 | Kurston | 02-6005 | SG4 | 3340 | SF | 375.326 | 0 | 36968.7088 |  | 36993.7942 | 0 | 3340 | 375.326 |  |  | 100% | 60000 | 60000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2917 | Kurston | 02-6005 | SG5 | 3470 | SF | 389.9345 | 0 | 38407.6106 |  | 38433.6724 | 0 | 3470 | 389.9345 |  |  | 100% | 60000 | 60000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2250 | Kurston | 02-6005 | S81 | 6110 | SF | 686.5993 | 0 | 67628.3865 |  | 0 | 0 | 0 | 0 |  |  | 0% | 60000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6006 | LEAD CONSULTANT | 1 | LS | 0 | 1 | 17915 |  | 17352.5 | 30694.23 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | TRUE |  | FALSE |  | 0 | 0 | 17915 | 0 | 0 | 0
0 | Kurston | 02-6007 | LEAD DISPOSAL | 13.19 | CY | 0 | 1 | 12862 |  | 5400.21 | 20005.08 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | TRUE |  | FALSE |  | 0 | 0 | 12862 | 0 | 0 | 0
0 | Kurston | 02-6008 | LEAD TRAINING | 14 | EA | 143.51 | 0.097554 | 17219.94 | 172.3851 | 7757.33 | 10442.93 | 6 | 45 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 13740 | 0 | 3479.94 | 0 | 0 | -1.3642e-12
0 | Ricky | 02-6009 | Paint Removal Elevator Pits | 12 | EA | 671.98 | 0.017858 | 67200 | 100.2324 | 1052.44 | 1052.44 | 0.2 | 10.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 67200 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6010 | REMOVE SUMP PUMPS | 36 | EA | 416 | 0.086538 | 39532.48 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 39532.48 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6010 | OG1 | 2 | EA | 23.1111 | 0 | 2196.2489 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
643 | Kurston | 02-6010 | OG2 | 3 | EA | 34.6667 | 0 | 3294.3733 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
825 | Kurston | 02-6010 | OG3 | 3 | EA | 34.6667 | 0 | 3294.3733 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1006 | Kurston | 02-6010 | OG4 | 2 | EA | 23.1111 | 0 | 2196.2489 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1190 | Kurston | 02-6010 | OG5 | 2 | EA | 23.1111 | 0 | 2196.2489 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1373 | Kurston | 02-6010 | OG6 | 2 | EA | 23.1111 | 0 | 2196.2489 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
58 | Kurston | 02-6010 | SG1 | 3 | EA | 34.6667 | 0 | 3294.3733 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1187 | Kurston | 02-6010 | SG2 | 2 | EA | 23.1111 | 0 | 2196.2489 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2578 | Kurston | 02-6010 | SG3 | 6 | EA | 69.3333 | 0 | 6588.7467 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2745 | Kurston | 02-6010 | SG4 | 4 | EA | 46.2222 | 0 | 4392.4978 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2918 | Kurston | 02-6010 | SG5 | 3 | EA | 34.6667 | 0 | 3294.3733 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2251 | Kurston | 02-6010 | S81 | 4 | EA | 46.2222 | 0 | 4392.4978 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6015 | DEMO EXISTING VENT, WINDOW, AND FRAME | 185 | EA | 576 | 0.32118 | 54737.28 |  | 43638.78 | 43638.78 | 108 | 423.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 54737.28 | 0 | 0 | 0 | 0 | 0
463 | Kurston | 02-6015 | OG1 | 13 | EA | 40.4757 | 0 | 3846.4035 |  | 4170.7417 | 0 | 13 | 40.4757 | 13 |  | 100% | 20000 | 20000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
644 | Kurston | 02-6015 | OG2 | 13 | EA | 40.4757 | 0 | 3846.4035 |  | 4170.7417 | 0 | 13 | 40.4757 | 13 |  | 100% | 20000 | 20000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
826 | Kurston | 02-6015 | OG3 | 14 | EA | 43.5892 | 0 | 4142.2806 |  | 4491.568 | 0 | 14 | 43.5892 | 14 |  | 100% | 20000 | 20000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1007 | Kurston | 02-6015 | OG4 | 12 | EA | 37.3622 | 0 | 3550.5263 |  | 3849.9154 | 0 | 12 | 37.3622 | 12 |  | 100% | 20000 | 20000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1191 | Kurston | 02-6015 | OG5 | 12 | EA | 37.3622 | 0 | 3550.5263 |  | 3529.0891 | 0 | 11 | 34.2486 | 12 |  | 100% | 20000 | 20000 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1375 | Kurston | 02-6015 | OG6 | 27 | EA | 84.0649 | 0 | 7988.6841 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
59 | Kurston | 02-6015 | SG1 | 13 | EA | 40.4757 | 0 | 3846.4035 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1198 | Kurston | 02-6015 | SG2 | 12 | EA | 37.3622 | 0 | 3550.5263 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2579 | Kurston | 02-6015 | SG3 | 16 | EA | 49.8162 | 0 | 4734.035 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2746 | Kurston | 02-6015 | SG4 | 10 | EA | 31.1351 | 0 | 2958.7719 |  | 3208.2628 | 0 | 10 | 31.1351 | 10 |  | 100% | 20000 | 20000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2919 | Kurston | 02-6015 | SG5 | 14 | EA | 43.5892 | 0 | 4142.2806 |  | 4491.568 | 0 | 14 | 43.5892 | 14 |  | 100% | 20000 | 20000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2252 | Kurston | 02-6015 | S81 | 29 | EA | 90.2919 | 0 | 8580.4385 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6020 | DEMO EXISTING DOOR, FRAME AND HARDWARE | 24 | EA | 208 | 0.11538 | 19766.24 | 98.9518 | 1088.47 | 1088.47 | 1 | 11 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 19766.24 | 0 | 0 | 0 | 0 | 0
464 | Kurston | 02-6020 | OG1 | 1 | EA | 8.6667 | 0 | 823.5933 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
645 | Kurston | 02-6020 | OG2 | 3 | EA | 26 | 0 | 2470.78 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
827 | Kurston | 02-6020 | OG3 | 1 | EA | 8.6667 | 0 | 823.5933 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1008 | Kurston | 02-6020 | OG4 | 1 | EA | 8.6667 | 0 | 823.5933 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1192 | Kurston | 02-6020 | OG5 | 1 | EA | 8.6667 | 0 | 823.5933 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1376 | Kurston | 02-6020 | OG6 | 5 | EA | 43.3333 | 0 | 4117.9667 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
60 | Kurston | 02-6020 | SG1 | 3 | EA | 26 | 0 | 2470.78 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1209 | Kurston | 02-6020 | SG2 | 1 | EA | 8.6667 | 0 | 823.5933 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2580 | Kurston | 02-6020 | SG3 | 3 | EA | 26 | 0 | 2470.78 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2747 | Kurston | 02-6020 | SG4 | 1 | EA | 8.6667 | 0 | 823.5933 |  | 857.5824 | 0 | 1 | 8.6667 |  |  | 50% | 20000 | 10000 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2920 | Kurston | 02-6020 | SG5 | 1 | EA | 8.6667 | 0 | 823.5933 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2253 | Kurston | 02-6020 | S81 | 3 | EA | 26 | 0 | 2470.78 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20000 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | REMOVE AREAWAYS LABOR | 52.17 | CY | 1239.98 | 0.042073 | 124977.12 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 124977.12 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | OG1 | 4 | CY | 95.0723 | 0 | 9582.2979 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | OG2 | 4 | CY | 95.0723 | 0 | 9582.2979 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | OG3 | 4 | CY | 95.0723 | 0 | 9582.2979 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | OG4 | 4 | CY | 95.0723 | 0 | 9582.2979 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | OG5 | 4 | CY | 95.0723 | 0 | 9582.2979 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | OG6 | 4 | CY | 95.0723 | 0 | 9582.2979 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | SG1 | 5 | CY | 118.8403 | 0 | 11977.8723 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | SG2 | 5 | CY | 118.8403 | 0 | 11977.8723 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | SG3 | 5 | CY | 118.8403 | 0 | 11977.8723 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | SG4 | 5 | CY | 118.8403 | 0 | 11977.8723 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | SG5 | 5 | CY | 118.8403 | 0 | 11977.8723 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6025 | S81 | 5 | CY | 118.8403 | 0 | 11977.8723 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6026 | REMOVE AREAWAYS EQUIPMENT | 52.17 | CY | 0 | 1 | 7750 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 7750 | 0
0 | Kurston | 02-6030 | PREPARE EXISTING WALL SURFACE FOR PAINT | 9460 | SF | 2363.1 | 4.0032 | 227761.46 | 96.3825 | 385.53 | 385.53 | 880 | 4 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 227761.46 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6030 | OG1 | 1520 | SF | 379.6947 | 0 | 36595.9217 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6030 | OG2 | 1590 | SF | 397.1807 | 0 | 38281.2602 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6030 | OG3 | 2280 | SF | 569.5421 | 0 | 54893.8825 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6030 | OG4 | 1990 | SF | 497.1003 | 0 | 47911.7659 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6030 | OG5 | 2080 | SF | 519.5822 | 0 | 50078.6297 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6035 | REMOVE EXISTING PORTION WALL SITE-8 | 0.22 | CY | 16 | 0.01375 | 1520.48 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 1520.48 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6035 | S81 | 1 | CY | 72.7273 | 0 | 6911.2727 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | SAWCUT OPENINGS THROUGH SLAB FOR CELLAR VENIT | 0.77 | CY | 192 | 0.0040104 | 18245.76 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 18245.76 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | OG1 | 2 | CY | 498.7013 | 0 | 47391.5844 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | OG2 | 2 | CY | 498.7013 | 0 | 47391.5844 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | OG3 | 2 | CY | 498.7013 | 0 | 47391.5844 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | OG4 | 2 | CY | 498.7013 | 0 | 47391.5844 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | OG5 | 2 | CY | 498.7013 | 0 | 47391.5844 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | OG6 | 1 | CY | 249.3506 | 0 | 23695.7922 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | SG1 | 2 | CY | 498.7013 | 0 | 47391.5844 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | SG2 | 2 | CY | 498.7013 | 0 | 47391.5844 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | SG3 | 2 | CY | 498.7013 | 0 | 47391.5844 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | SG4 | 2 | CY | 498.7013 | 0 | 47391.5844 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | SG5 | 2 | CY | 498.7013 | 0 | 47391.5844 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6040 | S81 | 2 | CY | 498.7013 | 0 | 47391.5844 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6045 | REMOVE EXISTING AC UNITS AND SLEEVES | 114 | EA | 320 | 0.35625 | 30409.6 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 30409.6 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6045 | OG1 | 18 | EA | 50.5263 | 0 | 4801.5158 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6045 | OG2 | 17 | EA | 47.7193 | 0 | 4534.7649 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6045 | OG3 | 17 | EA | 47.7193 | 0 | 4534.7649 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6045 | OG4 | 17 | EA | 47.7193 | 0 | 4534.7649 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6045 | OG5 | 17 | EA | 47.7193 | 0 | 4534.7649 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6045 | OG6 | 23 | EA | 64.5614 | 0 | 6135.2702 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6045 | SG3 | 5 | EA | 14.0351 | 0 | 1333.7544 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6050 | DEMO STAIRS AND RAMPS LABOR | 15.07 | CY | 168.01 | 0.089697 | 17116.64 | 99.1881 | 3669.96 | 3669.96 | 4 | 37 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 17116.64 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6050 | SG1 | 3 | CY | 33.4459 | 0 | 3407.4267 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6050 | SG2 | 1 | CY | 11.1486 | 0 | 1135.8089 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6050 | SG4 | 1 | CY | 11.1486 | 0 | 1135.8089 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6050 | SG5 | 1 | CY | 11.1486 | 0 | 1135.8089 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6051 | DEMO STAIRS AND RAMPS EQUIPMENT | 5 | DY | 0 | 1 | 3000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 3000 | 0
0 | Kurston | 02-6055 | SAWCUT SLAB OPENING FOR MECHANICAL | 2.06 | CY | 360 | 0.0057222 | 34210.8 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 34210.8 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6055 | OG1 | 6 | CY | 1048.5437 | 0 | 99643.1068 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6055 | OG2 | 2 | CY | 349.5146 | 0 | 33214.3689 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6055 | OG3 | 3 | CY | 524.2718 | 0 | 49821.5534 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6055 | OG4 | 4 | CY | 699.0291 | 0 | 66428.7379 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6055 | OG5 | 6 | CY | 1048.5437 | 0 | 99643.1068 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6055 | OG6 | 2 | CY | 349.5146 | 0 | 33214.3689 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6055 | SG3 | 5 | CY | 873.7864 | 0 | 83035.9223 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6055 | SG4 | 2 | CY | 349.5146 | 0 | 33214.3689 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6055 | SG5 | 4 | CY | 699.0291 | 0 | 66428.7379 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6060 | DEMO SECOND FLOOR APARTMENTS | 9 | EA | 1728.35 | 0.0052073 | 164244.84 | 102.6005 | 79053.72 | 79053.72 | 4.61 | 770.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 164244.84 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6060 | OG3 | 1 | EA | 192.0389 | 0 | 18249.4267 |  | 29751.975 | 0 | 1.51 | 289.9787 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | FALSE |  | TRUE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6060 | OG4 | 1 | EA | 192.0389 | 0 | 18249.4267 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6060 | OG5 | 1 | EA | 192.0389 | 0 | 18249.4267 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6060 | OG6 | 1 | EA | 192.0389 | 0 | 18249.4267 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6060 | SG1 | 1 | EA | 192.0389 | 0 | 18249.4267 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6060 | SG2 | 1 | EA | 192.0389 | 0 | 18249.4267 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6060 | SG3 | 1 | EA | 192.0389 | 0 | 18249.4267 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6060 | SG4 | 1 | EA | 192.0389 | 0 | 18249.4267 |  | 19703.2947 | 0 | 1 | 192.0389 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6060 | SG5 | 1 | EA | 192.0389 | 0 | 18249.4267 |  | 19703.2947 | 0 | 1 | 192.0389 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-6065 | DEMO FOR MECHANICAL | 2250 | HR | 1999.73 | 1.1252 | 200000 | 104.5381 | 7160.86 | 7160.86 | 110 | 68.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 200000 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6066 | FLOOR DRAIN DEMO | 48 | EA | 725.5 | 0.066161 | 70083.35 | 96.6001 | 70083.35 | 70083.35 | 48 | 725.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 70083.35 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-6070 | DEMO FOR ELECTRICAL | 2213.91 | HR | 2214.2 | 0.99987 | 225000 | 101.2043 | 6983.1 | 6983.1 | 69 | 69 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 225000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-6075 | DEMO FOR PLUMBING | 2187.94 | HR | 2187.93 | 1 | 211879.62 | 105.1614 | 13881.31 | 13881.31 | 132 | 132 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 211879.62 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6100 | ASBESTOS SUB | 1 | LS | 0 | 1 | 1554903.14 |  | 736861.97 | 1569944.22 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | TRUE |  | FALSE |  | 0 | 1554903.14 | 0 | 0 | 0 | 0
0 | Kurston | 02-6110 | ASBESTOS SUB SUPPORT | 0 | HR | 0 | 1 | 79433.41 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 79433.41 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 02-6120 | ASEBESTOS CONSULTANT | 9 | EA | 0 | 1 | 39847 |  | 23691.55 | 84866.98 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | TRUE |  | FALSE |  | 0 | 0 | 39847 | 0 | 0 | 0
0 | Kurston | 02-6130 | ASBESTOS SUB ACCESS | 166 | HR | 167.35 | 0.99193 | 25443.75 | 128.4726 | 21069.51 | 24792.47 | 166 | 164 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 20000 | 0 | 5443.75 | 0 | 0 | 0
0 | Brian | 02-7000 | EROSION CONTROL FABRIC CONST MATERIAL | 1 | LS | 0 | 1 | 0 |  | 1900.42 | 1900.42 | 0 | 0 |  |  | 0% | 0 | 0 | TRUE | #DIV/0! | #DIV/0! | #DIV/0! | TRUE |  | FALSE | ask to transfer cost | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 02-7100 | STONE FOR EROSION CONTROL | 405 | CY | 0 | 1 | 26810.98 |  | 18543.32 | 28639.1 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | TRUE |  | FALSE |  | 0 | 0 | 26810.98 | 0 | 0 | 0
0 | Brian | 02-7200 | SOIL TESTING | 35 | EA | 0 | 1 | 80000 |  | 83535 | 93315 | 0 | 0 |  |  | 0% | 0 | 0 | TRUE | TRUE | TRUE | TRUE | TRUE |  | FALSE |  | 0 | 0 | 80000 | 0 | 0 | 0
0 | Brian | 03-1000 | FORMWORK NEW BUILDING | 62292 | SF | 18185.24 | 3.4254 | 2057455.94 | 113.2545 | 1649494.79 | 1649494.79 | 47834.09 | 14564.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 2057455.94 | 0 | 0 | 0 | 0 | 0
3081 | Brian | 03-1000 | SG6 | 12658 | SF | 3695.3183 | 0 | 418083.8196 |  | 410131.1863 | 0 | 12404.54 | 3621.3244 |  |  | 100% | 469701 | 469701 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
127 | Brian | 03-1000 | SG7 | 9518 | SF | 2778.6411 | 0 | 314372.0805 |  | 141608.7877 | 0 | 4283 | 1250.3593 |  |  | 100% | 353185 | 353185 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1549 | Brian | 03-1000 | OG8 | 20263 | SF | 5915.487 | 0 | 669271.0093 |  | 402105.8067 | 0 | 12161.81 | 3550.4629 |  |  | 100% | 751900 | 751900 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1736 | Brian | 03-1000 | OG9 | 5800 | SF | 1693.2253 | 0 | 191569.4544 |  | 163008.1469 | 0 | 4930.23 | 1439.3087 |  |  | 100% | 215221 | 215221 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1900 | Brian | 03-1000 | OG10 | 5463 | SF | 1594.8431 | 0 | 180438.6085 |  | 144485.5985 | 0 | 4370.01 | 1275.7606 |  |  | 100% | 202716 | 202716 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2515 | Ksenofon | 03-1000 | S82 | 8549 | SF | 2495.7557 | 0 | 282366.7699 |  | 0 | 0 | 0 | 0 |  |  | 0% | 317228 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 03-1100 | FORMWORK EXIST BLDGS | 23967 | SF | 6001 | 3.9938 | 649653.32 | 113.9743 | 215753.34 | 215753.34 | 6509.6 | 1893 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 649653.32 | 0 | 0 | 0 | 0 | 0
69 | Brian | 03-1100 | SG1 | 1674 | SF | 419.1461 | 0 | 45375.7107 |  | 18435.2649 | 0 | 646 | 161.7493 |  |  | 0% | 50095 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1297 | Ksenofon | 03-1100 | SG2 | 1109 | SF | 277.678 | 0 | 30060.7307 |  | 0 | 0 | 0 | 0 |  |  | 0% | 33187 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2600 | Brian | 03-1100 | SG3 | 1768 | SF | 442.6824 | 0 | 47923.6896 |  | 12232.3405 | 0 | 428.64 | 107.3254 |  |  | 0% | 52908 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2767 | Brian | 03-1100 | SG4 | 3543 | SF | 887.1174 | 0 | 96037.1224 |  | 46521.9332 | 0 | 1630.2 | 408.1792 |  |  | 75% | 106025 | 79518.75 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2941 | Brian | 03-1100 | SG5 | 2891 | SF | 723.8658 | 0 | 78363.9065 |  | 41251.0455 | 0 | 1445.5 | 361.9329 |  |  | 75% | 86514 | 64885.5 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
486 | Brian | 03-1100 | OG1 | 1006 | SF | 251.8883 | 0 | 27268.7963 |  | 11483.5149 | 0 | 402.4 | 100.7553 |  |  | 50% | 30105 | 15052.5 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
667 | Brian | 03-1100 | OG2 | 1026 | SF | 256.896 | 0 | 27810.9194 |  | 11711.8153 | 0 | 410.4 | 102.7584 |  |  | 70% | 30704 | 21492.8 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
847 | Ksenofon | 03-1100 | OG3 | 1026 | SF | 256.896 | 0 | 27810.9194 |  | 0 | 0 | 0 | 0 |  |  | 0% | 30704 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1030 | Ksenofon | 03-1100 | OG4 | 1026 | SF | 256.896 | 0 | 27810.9194 |  | 0 | 0 | 0 | 0 |  |  | 0% | 30704 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1214 | Ksenofon | 03-1100 | OG5 | 1026 | SF | 256.896 | 0 | 27810.9194 |  | 0 | 0 | 0 | 0 |  |  | 0% | 30704 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1397 | Ksenofon | 03-1100 | OG6 | 6557 | SF | 1641.7807 | 0 | 177735.0865 |  | 0 | 0 | 0 | 0 |  |  | 0% | 196219 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2362 | Ksenofon | 03-1100 | S81 | 5224 | SF | 1308.0162 | 0 | 141602.5762 |  | 0 | 0 | 0 | 0 |  |  | 0% | 143660 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 03-1200 | OPERATOR FOR CONCRETE WORK | 3100 | CY | 384 | 8.0729 | 49920 | 151.8205 | 29756.82 | 29756.82 | 993 | 196 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 49920 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-1300 | SET ANCHOR BOLTS FOR STEEL COLUMNS | 308 | EA | 506.89 | 0.60763 | 58444.2 | 115.1596 | 46812.36 | 46812.36 | 252 | 406.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 58444.2 | 0 | 0 | 0 | 0 | 0
3082 | Ricky | 03-1300 | SG6 | 44 | EA | 72.4129 | 0 | 8349.1714 |  | 8339.0326 | 0 | 44 | 72.4129 |  |  | 100% | 5411 | 5411 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
128 | Ricky | 03-1300 | SG7 | 60 | EA | 98.7448 | 0 | 11385.2338 |  | 9097.1264 | 0 | 48 | 78.9958 |  |  | 100% | 5411 | 5411 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1551 | Ricky | 03-1300 | OG8 | 64 | EA | 105.3278 | 0 | 12144.2494 |  | 12129.5019 | 0 | 64 | 105.3278 |  |  | 100% | 5411 | 5411 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1738 | Ricky | 03-1300 | OG9 | 40 | EA | 65.8299 | 0 | 7590.1558 |  | 7580.9387 | 0 | 40 | 65.8299 |  |  | 100% | 5411 | 5411 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1901 | Ricky | 03-1300 | OG10 | 48 | EA | 78.9958 | 0 | 9108.187 |  | 9097.1264 | 0 | 48 | 78.9958 |  |  | 100% | 5411 | 5411 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2516 | Ricky | 03-1300 | S82 | 52 | EA | 85.5788 | 0 | 9867.2026 |  | 0 | 0 | 0 | 0 |  |  | 0% | 5411 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-1400 | DRILL & GROUT DOWELS | 4450 | EA | 1110.67 | 4.0066 | 106416.19 | 102.3106 | 77704.91 | 77704.91 | 3384.75 | 759.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE | Got number from ricky | 106416.19 | 0 | 0 | 0 | 0 | 0
70 | Ricky | 03-1400 | SG1 | 228 | EA | 56.9062 | 0 | 5452.3351 |  | 0 | 0 | 0 | 0 |  |  | 0% | 6278 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1308 | Ricky | 03-1400 | SG2 | 122 | EA | 30.4498 | 0 | 2917.4776 |  | 0 | 0 | 0 | 0 |  |  | 0% | 3359 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2601 | Ricky | 03-1400 | SG3 | 286 | EA | 71.3824 | 0 | 6839.3327 |  | 0 | 0 | 0 | 0 |  |  | 0% | 7874 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2768 | Ricky | 03-1400 | SG4 | 943 | EA | 235.3622 | 0 | 22550.6668 |  | 24080.0512 | 0 | 943 | 235.3622 |  |  | 100% | 25962 | 25962 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2942 | Ricky | 03-1400 | SG5 | 582 | EA | 145.2607 | 0 | 13917.8028 |  | 14861.7071 | 0 | 582 | 145.2607 |  |  | 100% | 26772 | 26772 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
487 | Ricky | 03-1400 | OG1 | 136 | EA | 33.9441 | 0 | 3252.2701 |  | 0 | 0 | 0 | 0 |  |  | 50% | 3745 | 1872.5 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
668 | Ricky | 03-1400 | OG2 | 136 | EA | 33.9441 | 0 | 3252.2701 |  | 0 | 0 | 0 | 0 |  |  | 50% | 3745 | 1872.5 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
848 | Ricky | 03-1400 | OG3 | 136 | EA | 33.9441 | 0 | 3252.2701 |  | 0 | 0 | 0 | 0 |  |  | 50% | 3745 | 1872.5 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1031 | Ricky | 03-1400 | OG4 | 136 | EA | 33.9441 | 0 | 3252.2701 |  | 0 | 0 | 0 | 0 |  |  | 100% | 3745 | 3745 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1215 | Ricky | 03-1400 | OG5 | 136 | EA | 33.9441 | 0 | 3252.2701 |  | 0 | 0 | 0 | 0 |  |  | 50% | 3745 | 1872.5 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1398 | Ricky | 03-1400 | OG6 | 1549 | EA | 386.613 | 0 | 37042.3996 |  | 13144.4394 | 0 | 514.75 | 128.4758 |  |  | 10% | 42646 | 4264.6 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2363 | Ricky | 03-1400 | S81 | 907 | EA | 226.377 | 0 | 21689.7718 |  | 0 | 0 | 0 | 0 |  |  | 0% | 20861 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-1500 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE | 164 | CY | 1416.38 | 0.11579 | 162759.19 | 111.6145 | 16909.6 | 16909.6 | 12.4 | 151.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 162759.19 | 0 | 0 | 0 | 0 | 0
71 | Ricky | 03-1500 | SG1 | 12 | CY | 103.6376 | 0 | 11909.209 |  | 0 | 0 | 0 | 0 |  |  | 0% | 30151 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1319 | Ricky | 03-1500 | SG2 | 10 | CY | 86.3646 | 0 | 9924.3409 |  | 0 | 0 | 0 | 0 |  |  | 0% | 25126 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2602 | Ricky | 03-1500 | SG3 | 17 | CY | 146.8199 | 0 | 16871.3795 |  | 0 | 0 | 0 | 0 |  |  | 0% | 42713 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2769 | Ricky | 03-1500 | SG4 | 10 | CY | 86.3646 | 0 | 9924.3409 |  | 9639.5473 | 0 | 10 | 86.3646 | 10 |  | 100% | 25126 | 25126 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2943 | Ricky | 03-1500 | SG5 | 10 | CY | 86.3646 | 0 | 9924.3409 |  | 0 | 0 | 0 | 0 | 10 |  | 100% | 41980 | 41980 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
488 | Ricky | 03-1500 | OG1 | 11 | CY | 95.0011 | 0 | 10916.7749 |  | 0 | 0 | 0 | 0 | 11 |  | 100% | 27638 | 27638 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
669 | Ricky | 03-1500 | OG2 | 11 | CY | 95.0011 | 0 | 10916.7749 |  | 0 | 0 | 0 | 0 | 11 |  | 100% | 27638 | 27638 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
849 | Ricky | 03-1500 | OG3 | 11 | CY | 95.0011 | 0 | 10916.7749 |  | 0 | 0 | 0 | 0 | 5.5 |  | 50% | 27638 | 13819 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1032 | Ricky | 03-1500 | OG4 | 10 | CY | 86.3646 | 0 | 9924.3409 |  | 0 | 0 | 0 | 0 | 5 |  | 50% | 25126 | 12563 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1216 | Ricky | 03-1500 | OG5 | 10 | CY | 86.3646 | 0 | 9924.3409 |  | 0 | 0 | 0 | 0 | 5 |  | 50% | 25126 | 12563 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1399 | Ricky | 03-1500 | OG6 | 23 | CY | 198.6387 | 0 | 22825.984 | 212.3254 | 0 | 0 | 0 | 0 | 5.75 |  | 25% | 57788 | 14447 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2365 | Ricky | 03-1500 | S81 | 29 | CY | 250.4574 | 0 | 28780.5885 | 509.6167 | 0 | 0 | 0 | 0 | 0 |  | 0% | 60871 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-1600 | FORMWORK SITE CONCRETE LABOR | 7400 | SF | 1701.87 | 4.3482 | 209994.21 | 118.2038 | 5023.66 | 5023.66 | 198 | 42.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 209994.21 | 0 | 0 | 0 | 0 | 0
311 | Ricky | 03-1600 | SGN | 1500 | SF | 344.9736 | 0 | 42566.3939 |  | 5382.5883 | 0 | 198 | 45.5365 |  |  | 33% | 55661 | 18368.13 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
394 | Ricky | 03-1600 | SGS | 1500 | SF | 344.9736 | 0 | 42566.3939 |  | 0 | 0 | 0 | 0 |  |  | 0% | 55661 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2076 | Ricky | 03-1600 | OGE | 1500 | SF | 344.9736 | 0 | 42566.3939 |  | 0 | 0 | 0 | 0 |  |  | 25% | 55661 | 13915.25 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2154 | Ricky | 03-1600 | OGW | 1500 | SF | 344.9736 | 0 | 42566.3939 |  | 0 | 0 | 0 | 0 |  |  | 33% | 55661 | 18368.13 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2261 | Ricky | 03-1600 | S8 | 1500 | SF | 344.9736 | 0 | 42566.3939 |  | 0 | 0 | 0 | 0 |  |  | 0% | 55661 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 03-1610 | FORMWORK SITE CONCRETE MATERIAL | 0 | NA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 03-1700 | CONCRETE REINFORCEMENT NEW BUILDING UNLOAD | 393500 | LB | 403.61 | 974.9511 | 46808.66 | 116.5567 | 56763.12 | 56763.12 | 393500 | 487 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | TRUE |  | FALSE |  | 46808.66 | 0 | 0 | 0 | 0 | 0
0 | Brian | 03-1800 | CONCRETE REINFORCEMENT BARRIER FOUNDATIONS UNLOAD | 254277 | LB | 293 | 867.8396 | 33109 | 107.1255 | 4499.27 | 4499.27 | 41000 | 42 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 33109 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-1900 | POUR CONCRETE NEW BUILDINGS | 3100 | CY | 4015.71 | 0.77197 | 432096.31 | 112.932 | 345120.19 | 345120.19 | 2651.2 | 3056 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 432096.31 | 0 | 0 | 0 | 0 | 0
3083 | Ricky | 03-1900 | SG6 | 469 | CY | 607.5381 | 0 | 65371.9901 |  | 68610.4879 | 0 | 469 | 607.5381 |  |  | 100% | 179646 | 179646 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
129 | Ricky | 03-1900 | SG7 | 575 | CY | 744.8494 | 0 | 80146.8962 |  | 58516.4076 | 0 | 400 | 518.1561 |  |  | 95% | 220248 | 209235.6 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1552 | Ricky | 03-1900 | OG8 | 1050 | CY | 1360.1598 | 0 | 146355.2018 |  | 98014.9828 | 0 | 670 | 867.9115 |  |  | 95% | 402192 | 382082.4 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1739 | Ricky | 03-1900 | OG9 | 267 | CY | 345.8692 | 0 | 37216.037 |  | 39059.7021 | 0 | 267 | 345.8692 |  |  | 100% | 102272 | 102272 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1903 | Ricky | 03-1900 | OG10 | 322 | CY | 417.1157 | 0 | 44882.2619 |  | 47105.7081 | 0 | 322 | 417.1157 |  |  | 100% | 123339 | 123339 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2517 | Ricky | 03-1900 | S82 | 384 | CY | 497.4299 | 0 | 53524.1881 |  | 0 | 0 | 0 | 0 |  |  | 0% | 147088 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 03-2000 | FINISH SLABS - NEW BLDGS | 0 | SF | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 03-2000 | SG6 | 5373 | SF | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 03-2000 | SG7 | 8948 | SF | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 03-2000 | OG8 | 17400 | SF | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 03-2000 | OG9 | 4383 | SF | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 03-2000 | OG10 | 6510 | SF | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 03-2000 | S82 | 6658 | SF | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2100 | POUR CONC EXIST BLDGS | 1039.5 | CY | 1825.83 | 0.56933 | 180380.55 | 102.8078 | 63895.03 | 63895.03 | 272.5 | 621.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 180380.55 | 0 | 0 | 0 | 0 | 0
72 | Ricky | 03-2100 | SG1 | 103 | CY | 180.9144 | 0 | 17873.2051 |  | 0 | 0 | 0 | 0 |  |  | 0% | 33906 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1330 | Ricky | 03-2100 | SG2 | 76 | CY | 133.4902 | 0 | 13187.996 |  | 0 | 0 | 0 | 0 |  |  | 0% | 25018 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2603 | Ricky | 03-2100 | SG3 | 92 | CY | 161.5934 | 0 | 15964.4162 |  | 0 | 0 | 0 | 0 |  |  | 0% | 30285 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2770 | Ricky | 03-2100 | SG4 | 149 | CY | 261.7111 | 0 | 25855.4131 |  | 26905.9331 | 0 | 149 | 261.7111 |  |  | 75% | 49048 | 36786 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2944 | Ricky | 03-2100 | SG5 | 139 | CY | 244.1466 | 0 | 24120.1505 |  | 632.0186 | 0 | 3.5 | 6.1476 |  |  | 50% | 45756 | 22878 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
489 | Ricky | 03-2100 | OG1 | 56 | CY | 98.3612 | 0 | 9717.4707 |  | 0 | 0 | 0 | 0 |  |  | 0% | 18434 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
671 | Ricky | 03-2100 | OG2 | 57 | CY | 100.1177 | 0 | 9890.997 |  | 0 | 0 | 0 | 0 |  |  | 75% | 18763 | 14072.25 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
850 | Ricky | 03-2100 | OG3 | 57 | CY | 100.1177 | 0 | 9890.997 |  | 0 | 0 | 0 | 0 |  |  | 0% | 18763 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1034 | Ricky | 03-2100 | OG4 | 57 | CY | 100.1177 | 0 | 9890.997 |  | 0 | 0 | 0 | 0 |  |  | 0% | 18763 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1217 | Ricky | 03-2100 | OG5 | 57 | CY | 100.1177 | 0 | 9890.997 |  | 0 | 0 | 0 | 0 |  |  | 0% | 18763 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1400 | Ricky | 03-2100 | OG6 | 173 | CY | 303.8659 | 0 | 30020.0434 |  | 0 | 0 | 0 | 0 |  |  | 0% | 56948 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2366 | Ricky | 03-2100 | S81 | 389 | CY | 683.2591 | 0 | 67501.7162 |  | 0 | 0 | 0 | 0 |  |  | 0% | 117673 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 03-2200 | CONCRETE FOOTING FOR SITE FURNISHING | 150 | CY | 144 | 1.0417 | 13759.32 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 13759.32 | 0 | 0 | 0 | 0 | 0
312 | Ksenofon | 03-2200 | SGN | 18 | CY | 17.28 | 0 | 1651.1184 |  | 0 | 0 | 0 | 0 |  |  | 0% | 5947 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
396 | Ksenofon | 03-2200 | SGS | 18 | CY | 17.28 | 0 | 1651.1184 |  | 0 | 0 | 0 | 0 |  |  | 0% | 5947 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2077 | Ksenofon | 03-2200 | OGE | 10 | CY | 9.6 | 0 | 917.288 |  | 0 | 0 | 0 | 0 |  |  | 0% | 3304 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2156 | Ksenofon | 03-2200 | OGW | 16 | CY | 15.36 | 0 | 1467.6608 |  | 0 | 0 | 0 | 0 |  |  | 0% | 5286 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2262 | Ksenofon | 03-2200 | S81 | 18 | CY | 17.28 | 0 | 1651.1184 |  | 0 | 0 | 0 | 0 |  |  | 0% | 5947 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 03-2300 | CONCRETE DUCTBANKS | 1220 | CY | 1234.36 | 0.98837 | 128078.47 | 112.0773 | 143122.69 | 143122.69 | 951 | 1277 |  |  | 0% | 0 | 0 | TRUE | TRUE | TRUE | TRUE | TRUE |  | FALSE | need QTD from sully | 128078.47 | 0 | 0 | 0 | 0 | 0
313 | Sully | 03-2300 | SGN | 158 | CY | 159.8597 | 0 | 16587.2117 |  | 17916.645 | 0 | 158 | 159.8597 | 158 |  | 100% | 40284 | 40284 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
397 | Sully | 03-2300 | SGS | 235 | CY | 237.7661 | 0 | 24670.8528 |  | 24153.4518 | 0 | 213 | 215.5071 | 0 |  | 0% | 59916 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2079 | Sully | 03-2300 | OGE | 221 | CY | 223.6013 | 0 | 23201.0999 |  | 25060.6237 | 0 | 221 | 223.6013 | 176.8 |  | 80% | 56347 | 45077.6 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2157 | Sully | 03-2300 | OGW | 243 | CY | 245.8602 | 0 | 25510.7116 |  | 27555.3464 | 0 | 243 | 245.8602 | 218.7 |  | 90% | 61956 | 55760.4 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2263 | Sully | 03-2300 | S8 | 150 | CY | 151.7656 | 0 | 15747.3529 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 38245 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2400 | CONCRETE SITE RETAINING WALL AND FOOTINGS | 171 | CY | 360 | 0.475 | 36435.9 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 36435.9 | 0 | 0 | 0 | 0 | 0
314 | Ricky | 03-2400 | SGN | 48 | CY | 101.0526 | 0 | 10227.6211 |  | 0 | 0 | 0 | 0 |  |  | 0% | 25224 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2080 | Ricky | 03-2400 | OGE | 63 | CY | 132.6316 | 0 | 13423.7526 |  | 0 | 0 | 0 | 0 |  |  | 0% | 33106 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2158 | Ricky | 03-2400 | OGW | 60 | CY | 126.3158 | 0 | 12784.5263 |  | 0 | 0 | 0 | 0 |  |  | 0% | 31529 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2500 | CONCRETE SHELF AND BOND BEAM EXTG BL (INCL FORMS) | 270 | CY | 1218.35 | 0.22161 | 143548.86 | 115.8023 | 15864.91 | 15864.91 | 106 | 137 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 143548.86 | 0 | 0 | 0 | 0 | 0
73 | Ricky | 03-2500 | SG1 | 22 | CY | 99.273 | 0 | 11696.5738 |  | 0 | 0 | 0 | 0 |  |  | 0% | 18856 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1341 | Ricky | 03-2500 | SG2 | 29 | CY | 130.8598 | 0 | 15418.2109 |  | 0 | 0 | 0 | 0 |  |  | 0% | 24855 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2604 | Ricky | 03-2500 | SG3 | 36 | CY | 162.4467 | 0 | 19139.848 |  | 0 | 0 | 0 | 0 |  |  | 0% | 30854 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2771 | Ricky | 03-2500 | SG4 | 28 | CY | 126.3474 | 0 | 14886.5484 |  | 0 | 0 | 0 | 0 |  |  | 100% | 23998 | 23998 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2945 | Ricky | 03-2500 | SG5 | 28 | CY | 126.3474 | 0 | 14886.5484 |  | 0 | 0 | 0 | 0 |  |  | 100% | 23998 | 23998 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
490 | Ricky | 03-2500 | OG1 | 18 | CY | 81.2233 | 0 | 9569.924 |  | 0 | 0 | 0 | 0 |  |  | 0% | 15427 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
672 | Ricky | 03-2500 | OG2 | 18 | CY | 81.2233 | 0 | 9569.924 |  | 0 | 0 | 0 | 0 |  |  | 0% | 15427 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
851 | Ricky | 03-2500 | OG3 | 18 | CY | 81.2233 | 0 | 9569.924 |  | 0 | 0 | 0 | 0 |  |  | 0% | 15427 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1035 | Ricky | 03-2500 | OG4 | 18 | CY | 81.2233 | 0 | 9569.924 |  | 0 | 0 | 0 | 0 |  |  | 0% | 15427 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1218 | Ricky | 03-2500 | OG5 | 18 | CY | 81.2233 | 0 | 9569.924 |  | 0 | 0 | 0 | 0 |  |  | 0% | 15427 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1401 | Ricky | 03-2500 | OG6 | 13 | CY | 58.6613 | 0 | 6911.6118 |  | 0 | 0 | 0 | 0 |  |  | 0% | 11142 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2367 | Ricky | 03-2500 | S81 | 13 | CY | 58.6613 | 0 | 6911.6118 |  | 0 | 0 | 0 | 0 |  |  | 0% | 10239 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2600 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL | 6650 | SF | 144 | 46.1806 | 13834.32 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 13834.32 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2600 | SG3 | 904 | SF | 19.5753 | 0 | 1880.6354 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2600 | SG4 | 864 | SF | 18.7092 | 0 | 1797.4214 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2600 | SG5 | 750 | SF | 16.2406 | 0 | 1560.2617 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2600 | OG1 | 650 | SF | 14.0752 | 0 | 1352.2268 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2600 | OG2 | 650 | SF | 14.0752 | 0 | 1352.2268 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2600 | OG3 | 650 | SF | 14.0752 | 0 | 1352.2268 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2600 | OG4 | 675 | SF | 14.6165 | 0 | 1404.2355 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2600 | OG5 | 650 | SF | 14.0752 | 0 | 1352.2268 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-2600 | OG6 | 820 | SF | 17.7564 | 0 | 1705.8861 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 03-2700 | EXISTING BLDGS EQUIPMENT PAD WORK | 0 | CY | 0 | 1 | 95.84 | 95.84 | 95.84 | 95.84 | 0 | 1 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | TRUE | FALSE |  | FALSE |  | 95.84 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-5000 | FURNISH CONCRETE | 6341 | CY | 0 | 1 | 1341498.46 | 0.59858 | 802992.57 | 1883438.32 | 2425 | 0 | 0.38243 | 1370.5883 | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | TRUE |  | FALSE |  | 0 | 0 | 0 | 1341498.46 | 0 | 0
0 | Ricky | 03-5100 | FURNISH INSULATION | 19200 | SF | 0 | 1 | 50669.81 | 0.77787 | 39414.64 | 50669.81 | 1012 | 0 | 0.052708 | 13923.1475 | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 50669.81 | 0 | 0
0 | Ricky | 03-5200 | FURNISH REBAR | 1714793 | LB | 0 | 1 | 8896.21 | 0.91848 | 8171.02 | 8896.21 | 0 | 0 | 0 | 1575008.6721 | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 1777.19 | 7119.02 | 0 | 0
0 | Ricky | 03-5250 | FURNISH WIREMESH | 51750 | SF | 0 | 1 | 18277.69 | 0.95575 | 17468.88 | 18277.69 | 0 | 0 | 0 | 49459.9996 | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 18277.69 | 0 | 0
0 | Ricky | 03-5400 | FURNISH SAKCRETE | 12100 | BG | 0 | 1 | 181500 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 181500 | 0 | 0
0 | Ricky | 03-5500 | FURNISH CONC PATCH MATERIAL | 6650 | SF | 0 | 1 | 13300 | 0.68981 | 9174.5 | 9627.4 | 0 | 0 | 0 | 4587.25 | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 13300 | 0 | 0
0 | Ricky | 03-6000 | FRP WORK | 8972 | SF | 2966.33 | 3.0246 | 407507.13 | 89.1062 | 122824 | 182919.15 | 2510 | 748 | 0.27976 | 796950.8552 | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE | Got number from ricky | 298739.42 | 0 | 0 | 108767.71 | 0 | 1.4552e-11
2606 | Ricky | 03-6000 | SG3 | 684 | SF | 226.1446 | 0 | 31067.1954 |  | 0 | 0 | 0 | 0 |  |  | 0% | 50274 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2773 | Ricky | 03-6000 | SG4 | 1264.4 | SF | 418.037 | 0 | 57428.8916 |  | 27687.3898 | 0 | 510 | 168.6166 |  |  | 100% | 50274 | 50274 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2947 | Ricky | 03-6000 | SG5 | 1027.67 | SF | 339.7691 | 0 | 46676.6443 |  | 32573.3997 | 0 | 600 | 198.3725 |  |  | 25% | 168000 | 42000 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
492 | Ricky | 03-6000 | OG1 | 1021.33 | SF | 337.673 | 0 | 46388.6822 |  | 0 | 0 | 0 | 0 |  |  | 0% | 50274 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
674 | Ricky | 03-6000 | OG2 | 1105.33 | SF | 365.4451 | 0 | 50203.9519 |  | 0 | 0 | 0 | 0 |  |  | 0% | 50274 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
853 | Ricky | 03-6000 | OG3 | 902.67 | SF | 298.4415 | 0 | 40999.1597 |  | 0 | 0 | 0 | 0 |  |  | 100% | 50274 | 50274 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1037 | Ricky | 03-6000 | OG4 | 1133.73 | SF | 374.8347 | 0 | 51493.8763 |  | 0 | 0 | 0 | 0 |  |  | 0% | 50274 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1221 | Ricky | 03-6000 | OG5 | 782.67 | SF | 258.767 | 0 | 35548.7746 |  | 0 | 0 | 0 | 0 |  |  | 0% | 50274 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1403 | Ricky | 03-6000 | OG6 | 1050.67 | SF | 347.3734 | 0 | 47721.3014 |  | 0 | 0 | 0 | 0 |  |  | 0% | 50274 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 03-6010 | FRP Self Perform | 0 | HR | 3 | 0 | 33860.62 | 11286.8733 | 33860.62 | 33860.62 | 0 | 3 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | TRUE | FALSE |  | FALSE |  | 383.93 | 0 | 33476.69 | 0 | 0 | 0
0 | Ricky | 03-6100 | REBAR SUB | 1 | LS | 0 | 1 | 1527067.44 |  | 606867.52 | 1420047.7 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 1527067.44 | 0 | 0 | 0 | 0
0 | Ricky | 03-6110 | REBAR SUB SUPPORT | 0 | NA | 0 | 1 | 26262.3 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 26262.3 | 0 | 0 | 0 | 0
0 | Brian | 03-6120 | REBAR DELIVERY SUPPORT | 36660 | LB | 35 | 1047.4286 | 4041.34 | 115.4669 | 4041.34 | 4041.34 | 36660 | 35 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 4041.34 | 0 | 0 | 0 | 0 | 0
0 | Brian | 03-7000 | FORMWORK MATERIAL | 92612 | SF | 76.82 | 1205.5715 | 302507.86 | 297505.25 | 297505.25 | 347595.73 | 37044.59 | 1 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | TRUE |  | FALSE |  | 9305.66 | 0 | 293202.2 | 0 | 0 | 0
0 | Ricky | 03-7100 | MATERIAL FOR FLOWABLE FILL BACKFILL | 0 | NA | 0 | 1 | 250757.5 |  | 121280 | 163140 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE | take money out | 0 | 0 | 250757.5 | 0 | 0 | 0
0 | Ricky | 04-1000 | CLEAN CONC SURF FOUND WALL/PATCH VOIDS W/MORTAR | 995 | SF | 72 | 13.8194 | 6917.16 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 6917.16 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 04-1000 | SG1 | 100 | SF | 7.2362 | 0 | 695.192 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 04-1000 | SG2 | 90 | SF | 6.5126 | 0 | 625.6728 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 04-1000 | SG3 | 105 | SF | 7.598 | 0 | 729.9516 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 04-1000 | SG4 | 75 | SF | 5.4271 | 0 | 521.394 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 04-1000 | SG5 | 75 | SF | 5.4271 | 0 | 521.394 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 04-1000 | OG1 | 110 | SF | 7.9598 | 0 | 764.7112 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 04-1000 | OG2 | 110 | SF | 7.9598 | 0 | 764.7112 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 04-1000 | OG3 | 110 | SF | 7.9598 | 0 | 764.7112 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 04-1000 | OG4 | 110 | SF | 7.9598 | 0 | 764.7112 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 04-1000 | OG5 | 110 | SF | 7.9598 | 0 | 764.7112 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 04-6000 | GROUT INJECTION SUB | 1 | LS | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 04-6100 | MASONRY SUB | 1 | LS | 0 | 1 | 9090000 | 0.048328 | 439300 | 9090000 | 0 | 0 | 0 | 0.048328 | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 8578380 | 0 | 511620 | 0 | 0
0 | Ricky | 04-6110 | MASONRY SUB SUPPORT | 0 | NA | 0 | 1 | 200000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 200000 | 0 | 0 | 0 | 0
0 | #N/A | 04-6120 | MASON EUIP SUPPORT | 21 | NA | 21 | 1 | 2638.6 | 125.6476 | 2638.6 | 2638.6 | 21 | 21 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 2638.6 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 04-6200 | STONE SUB | 1 | LS | 0 | 1 | 135000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 135000 | 0 | 0 | 0 | 0
0 | Ricky | 04-7000 | MASONRY CLEANER | 995 | SF | 0 | 1 | 2166.71 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 2166.71 | 0 | 0 | 0
0 | Ricky | 05-6000 | STRUCTURAL STEEL SUB | 1 | LS | 0 | 1 | 5889965 |  | 4123548.51 | 5889965 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 5838000 | 51965 | 0 | 0 | 0
0 | Ricky | 05-6010 | STRUCTURAL STEEL SUB SUPPORT | 32 | HR | 37.5 | 0.85333 | 33300.7 | 97.6613 | 3662.3 | 3662.3 | 32 | 37.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 3662.3 | 29638.4 | 0 | 0 | 0 | 3.638e-12
0 | Ricky | 05-6020 | GROUT STEEL COLUMNS | 99 | EA | 363.71 | 0.27219 | 36371 | 106.6294 | 19086.66 | 19086.66 | 67 | 179 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 36371 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 05-6030 | STEEL & CRANE DELIVERIES | 3 | HR | 148.54 | 0.020197 | 18000 | 175.8195 | 7296.51 | 7296.51 | 0.72 | 41.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 18000 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 05-6040 | Ground Prep For Crane | 63 | HR | 63 | 1 | 7328.3 | 116.3222 | 7328.3 | 7328.3 | 63 | 63 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 7328.3 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 05-6050 | PREP COLUMNS FOR STEEL INSTALL | 45 | HR | 45.24 | 0.99469 | 5000 | 110.5227 | 1215.75 | 1215.75 | 0 | 11 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 5000 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 05-6100 | MISC METALS SUB | 1 | LS | 0 | 1 | 2010175 |  | 0 | 2010175 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 2010175 | 0 | 0 | 0 | 0
0 | Ksenofon | 05-6110 | MISC METALS SUB SUPPORT | 0 | NA | 0 | 1 | 100000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 100000 | 0 | 0 | 0 | 0
0 | Ksenofon | 05-6200 | SIGNAGE SUB | 1 | LS | 0 | 1 | 138024 |  | 0 | 138024 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 138024 | 0 | 0 | 0 | 0
0 | Ksenofon | 05-6210 | SIGNAGE SUB SUPPORT | 0 | NA | 0 | 1 | 10000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 10000 | 0 | 0 | 0 | 0
0 | Kurston | 06-6000 | CARPENTRY SUB | 1 | LS | 0 | 1 | 1840000 |  | 239141 | 1840000 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 1840000 | 0 | 0 | 0 | 0
0 | Kurston | 06-6010 | CARPENTRY SUB SUPPORT | 0 | NA | 0 | 1 | 50000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 50000 | 0 | 0 | 0 | 0
0 | Ricky | 07-1000 | HIGH DENSITY STYROFOAM INFILL NEW BLDGS | 30 | CF | 14 | 2.1429 | 1589.15 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 1589.15 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 07-1000 | SG6 | 5 | CF | 2.3333 | 0 | 264.8583 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 07-1000 | SG7 | 5 | CF | 2.3333 | 0 | 264.8583 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 07-1000 | OG8 | 5 | CF | 2.3333 | 0 | 264.8583 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 07-1000 | OG9 | 5 | CF | 2.3333 | 0 | 264.8583 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 07-1000 | OG10 | 5 | CF | 2.3333 | 0 | 264.8583 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 07-1000 | S82 | 5 | CF | 2.3333 | 0 | 264.8583 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 07-1100 | 3 RIGID INSULATION UNDER GRADE NEW BLDGS | 19200 | SF | 367.14 | 52.2961 | 38139.48 | 103.3249 | 25262.94 | 25330.09 | 11932 | 244.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 38139.48 | 0 | 0 | 0 | 0 | 0
3120 | Ricky | 07-1100 | SG6 | 402 | SF | 7.687 | 0 | 798.5454 |  | 794.2579 | 0 | 402 | 7.687 |  |  | 100% | 1444 | 1444 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
169 | Ricky | 07-1100 | SG7 | 2015 | SF | 38.5306 | 0 | 4002.659 |  | 3981.1684 | 0 | 2015 | 38.5306 |  |  | 100% | 7236 | 7236 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1591 | Ricky | 07-1100 | OG8 | 6850 | SF | 130.9848 | 0 | 13607.0541 |  | 6253.2993 | 0 | 3165 | 60.5207 |  |  | 100% | 24599 | 24599 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1777 | Ricky | 07-1100 | OG9 | 2800 | SF | 53.5412 | 0 | 5562.0075 |  | 5532.1447 | 0 | 2800 | 53.5412 |  |  | 100% | 10055 | 10055 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1940 | Ricky | 07-1100 | OG10 | 3550 | SF | 67.8827 | 0 | 7051.8309 |  | 7013.9692 | 0 | 3550 | 67.8827 |  |  | 100% | 12749 | 12749 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2533 | Ricky | 07-1100 | S82 | 3500 | SF | 66.9266 | 0 | 6952.5094 |  | 0 | 0 | 0 | 0 |  |  | 0% | 12569 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | PENETRATION FIRESTOPPING EXTG BLDGS | 12 | BL | 576 | 0.020833 | 55337.28 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 55337.28 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | SG1 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | SG2 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | SG3 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | SG4 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | SG5 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | OG1 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | OG2 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | OG3 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | OG4 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | OG5 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | OG6 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1200 | S81 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1300 | PENETRATION FIRESTOPPING NEW BLDGS | 6 | BL | 288 | 0.020833 | 27668.64 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 27668.64 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1300 | SG6 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1300 | SG7 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1300 | OG8 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1300 | OG9 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1300 | OG10 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1300 | S82 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | JOINT SEALANTS EXTG BLDGS | 12 | BL | 576 | 0.020833 | 55337.28 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 55337.28 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | SG1 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | SG2 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | SG3 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | SG4 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | SG5 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | OG1 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | OG2 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | OG3 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | OG4 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | OG5 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | OG6 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1400 | S81 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1500 | JOINT SEALANTS NEW BLDGS | 6 | BL | 288 | 0.020833 | 27668.64 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 27668.64 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1500 | SG6 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1500 | SG7 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1500 | OG8 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1500 | OG9 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1500 | OG10 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-1500 | S82 | 1 | BL | 48 | 0 | 4611.44 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 07-2000 | INSTALL WATERSTOP | 313 | HR | 34 | 9.2059 | 3491.54 | 102.6924 | 3491.54 | 3491.54 | 313 | 34 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 3491.54 | 0 | 0 | 0 | 0 | 0
0 | ? | 07-5000 | FURNISH FIRESTOPPING | 18 | BL | 0 | 1 | 90000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 90000 | 0 | 0
0 | ? | 07-5100 | FURNISH JOINT SEALANT | 18 | BL | 0 | 1 | 90000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 90000 | 0 | 0
0 | Ricky | 07-6000 | WATERPROOFING SUB | 140655 | SF | 0 | 1 | 1007406.25 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 1007406.25 | 0 | 0 | 0 | 0
0 | Ricky | 07-6010 | WATERPROOFING SUB SUPPORT | 14065.5 | SF | 11.5 | 1223.087 | 135030.36 | 101.9939 | 1172.93 | 1172.93 | 0 | 11.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 1172.93 | 133857.43 | 0 | 0 | 0 | 0
0 | Ricky | 07-6020 | PREP SURFACE FOR WATERPROOFING | 214.5 | HR | 190.1 | 1.1284 | 20000 | 100.0833 | 23169.28 | 23169.28 | 214.5 | 231.5 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | TRUE |  | FALSE |  | 20000 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 07-6100 | METAL PANELS SUB | 38765 | SF | 0 | 1 | 3350000 |  | 0 | 3350000 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 3350000 | 0 | 0 | 0 | 0
0 | Ksenofon | 07-6110 | METAL PANELS SUB SUPPORT | 0 | NA | 0 | 1 | 100000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 100000 | 0 | 0 | 0 | 0
0 | Ricky | 07-6200 | ROOFING SUB | 21000 | SF | 0 | 1 | 1135000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 1135000 | 0 | 0 | 0 | 0
0 | Ricky | 07-6210 | ROOFING SUB SUPPORT | 0 | NA | 0 | 1 | 100000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 100000 | 0 | 0 | 0 | 0
0 | Ricky | 07-6300 | SPRAY ON FIREPROOFING SUB | 67690 | SF | 0 | 1 | 239000 |  | 71755.38 | 254755.38 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | TRUE |  | FALSE |  | 0 | 239000 | 0 | 0 | 0 | 0
0 | Ricky | 07-6310 | SPRAY ON FIREPROOFING SUB SUPPORT | 0 | NA | 0 | 1 | 15000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 15000 | 0 | 0 | 0 | 0
0 | Ricky | 07-6320 | Maintain heat for Fireproofers | 75.64 | HR | 300 | 0.25213 | 30000 | 100.5133 | 9196.97 | 9196.97 | 75.64 | 91.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 30000 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 07-6330 | FIREPROOFING CLEANUP | 45 | HR | 45.1 | 0.99778 | 5000 | 110.8736 | 2771.84 | 2771.84 | 25 | 25 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 5000 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 08-1600 | ACCESS HATCH | 36 | EA | 1008 | 0.035714 | 114418.44 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 114418.44 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 08-1700 | (1''4WX8H) S.S. FLOOD VENTS NEW BL (153) | 33 | EA | 168 | 0.19643 | 19069.74 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 19069.74 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 08-1700 | SG6 | 6 | EA | 30.5455 | 0 | 3467.2255 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 08-1700 | SG7 | 5 | EA | 25.4545 | 0 | 2889.3545 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 08-1700 | OG8 | 7 | EA | 35.6364 | 0 | 4045.0964 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 08-1700 | OG9 | 6 | EA | 30.5455 | 0 | 3467.2255 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 08-1700 | OG10 | 4 | EA | 20.3636 | 0 | 2311.4836 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 08-1700 | S82 | 7 | EA | 35.6364 | 0 | 4045.0964 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 08-1800 | 2'9"x8" SS FLOOD VENT W/SS SCRN NEW BLDG(8.06) | 17 | EA | 56 | 0.30357 | 6356.58 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 6356.58 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 08-1800 | SG1 | 4 | EA | 13.1765 | 0 | 1495.6659 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 08-1800 | SG2 | 4 | EA | 13.1765 | 0 | 1495.6659 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 08-1800 | SG4 | 4 | EA | 13.1765 | 0 | 1495.6659 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 08-1800 | SG5 | 4 | EA | 13.1765 | 0 | 1495.6659 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 08-5000 | FURNISH HM DOORS | 96 | EA | 0 | 1 | 191266.4 | 0.045489 | 8700.5 | 130000 | 0 | 0 | 0 | 4.3669 | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 191266.4 | 0 | 0
0 | Ksenofon | 08-5010 | HM DOOR SUPPORT | 0 | LS | 0 | 1 | 50000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 50000 | 0 | 0
0 | Brian | 08-5100 | FURNISH ACCESS HATCHES | 36 | EA | 0 | 1 | 90000 | 1.0198 | 91781 | 99876.64 | 0 | 0 | 0 | 36.7124 | 0% | 0 | 0 | TRUE | TRUE | TRUE | TRUE | TRUE |  | FALSE | ask Ricky to look into? Stefon? | 0 | 0 | 0 | 90000 | 0 | 0
0 | Ricky | 08-6000 | OVERHEAD DOORS SUB | 2 | EA | 0 | 1 | 22632 |  | 5658 | 22632 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 22632 | 0 | 0 | 0 | 0
0 | Ricky | 08-6010 | OVERHEAD DOORS SUB SUPPORT | 0 | NA | 0 | 1 | 5000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 5000 | 0 | 0 | 0 | 0
0 | ? | 08-6100 | GLAZING SUB | 2 | EA | 0 | 1 | 28000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 28000 | 0 | 0 | 0 | 0
0 | 0 | 08-6200 | LOUVERS SUB | 1 | LS | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 09-6000 | STUCCO SUB | 5060 | SF | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 09-6100 | TILE SUB | 246 | SF | 0 | 1 | 17530 |  | 0 | 11910 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 17530 | 0 | 0 | 0 | 0
0 | Ksenofon | 09-6110 | TILING SUB SUPPORT | 0 | NA | 0 | 1 | 5000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 5000 | 0 | 0 | 0 | 0
0 | 0 | 09-6200 | VCT FLOORING SUB | 173 | SF | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 09-6300 | PAINT SUB | 1 | LS | 0 | 1 | 533755 |  | 0 | 330000 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 533755 | 0 | 0 | 0 | 0
0 | Ksenofon | 09-6310 | PAINTING SUB SUPPORT | 0 | NA | 0 | 1 | 40000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 40000 | 0 | 0 | 0 | 0
0 | Ksenofon | 10-1000 | FIRE EXTINGUISHERS NEW BLDGS | 7 | EA | 16 | 0.4375 | 1836.95 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 1836.95 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 10-1000 | SG6 | 4 | EA | 9.1429 | 0 | 1049.6857 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 10-1000 | SG7 | 1 | EA | 2.2857 | 0 | 262.4214 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 10-1000 | S82 | 2 | EA | 4.5714 | 0 | 524.8429 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 10-1100 | TOILET ACCESSORIES NEW BLDGS | 15 | EA | 96 | 0.15625 | 11021.7 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 11021.7 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 10-1100 | SG6 | 3 | EA | 19.2 | 0 | 2204.34 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 10-1100 | SG7 | 3 | EA | 19.2 | 0 | 2204.34 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 10-1100 | OG8 | 3 | EA | 19.2 | 0 | 2204.34 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 10-1100 | OG9 | 3 | EA | 19.2 | 0 | 2204.34 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 10-1100 | OG10 | 3 | EA | 19.2 | 0 | 2204.34 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) | 930 | LF | 2480 | 0.375 | 289147.86 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 289147.86 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | SG1 | 68 | LF | 181.3333 | 0 | 21141.9941 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | SG2 | 42 | LF | 112 | 0 | 13058.2905 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | SG3 | 44 | LF | 117.3333 | 0 | 13680.1138 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | SG4 | 50 | LF | 133.3333 | 0 | 15545.5839 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | SG5 | 48 | LF | 128 | 0 | 14923.7605 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | OG1 | 56 | LF | 149.3333 | 0 | 17411.0539 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | OG2 | 56 | LF | 149.3333 | 0 | 17411.0539 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | OG3 | 56 | LF | 149.3333 | 0 | 17411.0539 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | OG4 | 56 | LF | 149.3333 | 0 | 17411.0539 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | OG5 | 56 | LF | 149.3333 | 0 | 17411.0539 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | OG6 | 108 | LF | 288 | 0 | 33578.4612 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1200 | S81 | 298 | LF | 794.6667 | 0 | 92651.6799 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1300 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) | 14 | EA | 196 | 0.071429 | 22248.03 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 22248.03 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1300 | SG1 | 1 | EA | 14 | 0 | 1589.145 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1300 | SG2 | 1 | EA | 14 | 0 | 1589.145 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1300 | OG1 | 2 | EA | 28 | 0 | 3178.29 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1300 | OG2 | 2 | EA | 28 | 0 | 3178.29 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1300 | OG3 | 2 | EA | 28 | 0 | 3178.29 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1300 | OG4 | 2 | EA | 28 | 0 | 3178.29 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1300 | OG5 | 2 | EA | 28 | 0 | 3178.29 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1300 | OG6 | 2 | EA | 28 | 0 | 3178.29 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1400 | WINDOW FLOODGATES (8.06 AND 8.14) | 387 | LF | 440.49 | 0.87857 | 50000.29 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 50000.29 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1400 | SG1 | 112 | LF | 127.4803 | 0 | 14470.3682 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1400 | SG2 | 131 | LF | 149.1064 | 0 | 16925.1628 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1400 | SG4 | 19 | LF | 21.6261 | 0 | 2454.7946 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1400 | SG5 | 44 | LF | 50.0816 | 0 | 5684.7875 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1400 | S81 | 81 | LF | 92.1956 | 0 | 10465.177 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1500 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE | 105 | LF | 168 | 0.625 | 19069.74 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 19069.74 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1500 | SG4 | 40 | LF | 64 | 0 | 7264.6629 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 10-1500 | SG5 | 40 | LF | 64 | 0 | 7264.6629 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 10-5000 | FURNISH TOILET ACCESSORIES | 15 | EA | 0 | 1 | 811.05 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 811.05 | 0 | 0
0 | Ksenofon | 10-5100 | FURNISH FIRE EXTINGUISHERS | 7 | EA | 0 | 1 | 2450 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 2450 | 0 | 0
0 | Ricky | 10-5200 | FURNISH AQUA FLOOD BARRIERS | 930 | LF | 0 | 1 | 1682724.63 | 0.36923 | 621312.2 | 1532090 | 0 | 0 | 0 | 343.3838 | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 1682724.63 | 0 | 0
0 | 0 | 10-5300 | FURNISH 8.08 FLOOD DOORS | 30 | EA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 10-5400 | FURNISH FLOOD ITEMS (153, 8.06 / 8.14, 8.11, 8.15) | 1 | LS | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 11-1000 | EXCAVATE & POUR CONCRETE FOOTINGS | 7 | EA | 336 | 0.020833 | 35505.12 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 35505.12 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 11-1000 | SGN | 2 | EA | 96 | 0 | 10144.32 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 11-1000 | OGW | 2 | EA | 96 | 0 | 10144.32 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 11-1000 | S8 | 3 | EA | 144 | 0 | 15216.48 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 11-6000 | PLAY AREA ITEMS SUB | 7 | EA | 0 | 1 | 446718.49 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 446718.49 | 0 | 0 | 0 | 0
0 | Ricky | 14-6000 | ELEVATOR SUB | 1 | LS | 0 | 1 | 1027903.5 |  | 31860 | 34687.58 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 1027903.5 | 0 | 0 | 0 | 0
0 | Ricky | 14-6010 | ELEVATOR JUNCTION BOXES | 36 | EA | 0 | 1 | 250000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 250000 | 0 | 0 | 0 | 0
0 | Kurston | 22-5000 | Purchase Yard Pumps | 16 | EA | 0 | 1 | 90656 |  | 0 | 90656 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 90656 | 0 | 0 | 0
0 | Kurston | 22-6000 | PLUMBING SUB | 1 | LS | 0 | 1 | 13100000 |  | 3489359.8 | 13099982.4 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 13100000 | 0 | 0 | 0 | 0
0 | Kurston | 22-6010 | PLUMBING BOND | 1 | LS | 0 | 1 | 125426 |  | 125426 | 125426 | 1 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 125426 | 0 | 0 | 0
0 | Ricky | 22-6020 | PIPE INSULATION | 0 | NA | 0 | 1 | 500000 |  | 2980 | 400000 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 500000 | 0 | 0 | 0 | 0
0 | Ricky | 22-6025 | PLUMBING INSULATION REMOVAL | 2000 | LF | 250 | 8 | 25000 | 100.0677 | 8405.69 | 8405.69 | 670 | 84 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 25000 | 0 | 0 | 0 | 0 | 0
0 | 0 | 22-6030 | YARD PUMP SUPPLY | 0 | NA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 22-6040 | YARD PUMP INSTALL | 16 | EA | 2093.44 | 0.0076429 | 209344 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 209344 | 0 | 0 | 0 | 0 | 0
0 | Brian | 22-6050 | SPRAY SHOWER AND DRINKING FOUNTAIN | 21 | EA | 0 | 1 | 45000 | 0.91284 | 41078 | 44723.67 | 0 | 0 | 0 | 19.1697 | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 45000 | 0 | 0
0 | 0 | 22-6060 | PLUMBING SUB SUPPORT | 0 | NA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 23-6000 | HVAC SUB | 1 | LS | 0 | 1 | 24100000 |  | 9404527.3 | 22500000 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 24100000 | 0 | 0 | 0 | 0
0 | Sully | 23-6010 | HVAC SUB SUPPORT | 0 | NA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Kurston | 26-6000 | ELECTRICAL SUB | 1 | LS | 0 | 1 | 50185000 |  | 8506605 | 50075000 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 50185000 | 0 | 0 | 0 | 0
0 | Kurston | 26-6010 | TEMP ELECTRIC | 18 | EA | 0 | 1 | 130000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 130000 | 0 | 0 | 0 | 0
0 | Kurston | 26-6020 | ELECTRICAL SUB SUPPORT | 0 | NA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | #N/A | 26-6030 | EQUIPMENT INSTALLATION SUPPORT | 64 | HR | 141.12 | 0.45351 | 20000 | 121.5048 | 8019.32 | 8019.32 | 64 | 66 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 20000 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 31-1000 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND CONCRETE | 6738 | CY | 1411.1 | 4.775 | 153344.35 | 109.9651 | 63064.96 | 63064.96 | 2067 | 573.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 153344.35 | 0 | 0 | 0 | 0 | 0
1022 | Ricky | 31-1000 | SG1 | 295 | CY | 61.7801 | 0 | 6713.6514 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 20834 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2566 | Ricky | 31-1000 | SG2 | 180 | CY | 37.6963 | 0 | 4096.4653 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 12713 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2732 | Ricky | 31-1000 | SG3 | 220 | CY | 46.0733 | 0 | 5006.7909 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 15538 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2904 | Ricky | 31-1000 | SG4 | 250 | CY | 52.356 | 0 | 5689.5351 |  | 5757.3349 | 0 | 250 | 52.356 | 225 |  | 90% | 17656 | 15890.4 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
3078 | Ricky | 31-1000 | SG5 | 250 | CY | 52.356 | 0 | 5689.5351 |  | 5757.3349 | 0 | 250 | 52.356 | 250 |  | 100% | 17656 | 17656 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
631 | Ricky | 31-1000 | OG1 | 160 | CY | 33.5079 | 0 | 3641.3025 |  | 3684.6944 | 0 | 160 | 33.5079 | 152 |  | 95% | 11300 | 10735 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
812 | Ricky | 31-1000 | OG2 | 160 | CY | 33.5079 | 0 | 3641.3025 |  | 3684.6944 | 0 | 160 | 33.5079 | 128 |  | 80% | 11300 | 9040 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
992 | Ricky | 31-1000 | OG3 | 160 | CY | 33.5079 | 0 | 3641.3025 |  | 0 | 0 | 0 | 0 | 40 |  | 25% | 11300 | 2825 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1175 | Ricky | 31-1000 | OG4 | 160 | CY | 33.5079 | 0 | 3641.3025 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 11300 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1359 | Ricky | 31-1000 | OG5 | 160 | CY | 33.5079 | 0 | 3641.3025 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 11300 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1543 | Ricky | 31-1000 | OG6 | 280 | CY | 58.6388 | 0 | 6372.2793 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 19775 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2316 | Ricky | 31-1000 | S81 | 1060 | CY | 221.9896 | 0 | 24123.6288 |  | 0 | 0 | 0 | 0 | 0 |  | 0% | 4025 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 31-1100 | BACKFILL FOR FLOOD BARRIER FFTGS & CONCRETE SHELF | 2125 | CY | 566.66 | 3.75 | 54203.86 | 113.7917 | 17182.54 | 17182.54 | 560 | 151 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 54203.86 | 0 | 0 | 0 | 0 | 0
1033 | Ricky | 31-1100 | SG1 | 180 | CY | 47.9994 | 0 | 4591.3858 |  | 0 | 0 | 0 | 0 |  |  | 0% | 7542 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2567 | Ricky | 31-1100 | SG2 | 120 | CY | 31.9996 | 0 | 3060.9239 |  | 0 | 0 | 0 | 0 |  |  | 0% | 5028 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2733 | Ricky | 31-1100 | SG3 | 150 | CY | 39.9995 | 0 | 3826.1548 |  | 0 | 0 | 0 | 0 |  |  | 0% | 6285 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2905 | Ricky | 31-1100 | SG4 | 180 | CY | 47.9994 | 0 | 4591.3858 |  | 606.8817 | 0 | 20 | 5.3333 |  |  | 25% | 7542 | 1885.5 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
3079 | Ricky | 31-1100 | SG5 | 180 | CY | 47.9994 | 0 | 4591.3858 |  | 0 | 0 | 0 | 0 |  |  | 25% | 7542 | 1885.5 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
632 | Ricky | 31-1100 | OG1 | 95 | CY | 25.333 | 0 | 2423.2314 |  | 0 | 0 | 0 | 0 |  |  | 0% | 3981 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
814 | Ricky | 31-1100 | OG2 | 95 | CY | 25.333 | 0 | 2423.2314 |  | 0 | 0 | 0 | 0 |  |  | 0% | 3981 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
993 | Ricky | 31-1100 | OG3 | 95 | CY | 25.333 | 0 | 2423.2314 |  | 0 | 0 | 0 | 0 |  |  | 0% | 3981 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1177 | Ricky | 31-1100 | OG4 | 95 | CY | 25.333 | 0 | 2423.2314 |  | 0 | 0 | 0 | 0 |  |  | 0% | 3981 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1360 | Ricky | 31-1100 | OG5 | 95 | CY | 25.333 | 0 | 2423.2314 |  | 0 | 0 | 0 | 0 |  |  | 0% | 3981 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1544 | Ricky | 31-1100 | OG6 | 150 | CY | 39.9995 | 0 | 3826.1548 |  | 0 | 0 | 0 | 0 |  |  | 0% | 6285 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2513 | Ricky | 31-1100 | S81 | 690 | CY | 183.9978 | 0 | 17600.3122 |  | 0 | 0 | 0 | 0 |  |  | 0% | 28908 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 31-1200 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - ALL EXIST BLDGS | 161 | CY | 42.94 | 3.7494 | 4107.44 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 4107.44 | 0 | 0 | 0 | 0 | 0
1044 | Ricky | 31-1200 | SG1 | 19 | CY | 5.0675 | 0 | 484.7289 |  | 0 | 0 | 0 | 0 |  |  | 0% | 1320 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2568 | Ricky | 31-1200 | SG2 | 7 | CY | 1.867 | 0 | 178.5843 |  | 0 | 0 | 0 | 0 |  |  | 0% | 486 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2734 | Ricky | 31-1200 | SG3 | 9 | CY | 2.4004 | 0 | 229.6084 |  | 0 | 0 | 0 | 0 |  |  | 0% | 625 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2906 | Ricky | 31-1200 | SG4 | 9 | CY | 2.4004 | 0 | 229.6084 |  | 0 | 0 | 0 | 0 |  |  | 0% | 625 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
3080 | Ricky | 31-1200 | SG5 | 9 | CY | 2.4004 | 0 | 229.6084 |  | 0 | 0 | 0 | 0 |  |  | 0% | 625 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
633 | Ricky | 31-1200 | OG1 | 17 | CY | 4.534 | 0 | 433.7048 |  | 0 | 0 | 0 | 0 |  |  | 0% | 1181 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
815 | Ricky | 31-1200 | OG2 | 17 | CY | 4.534 | 0 | 433.7048 |  | 0 | 0 | 0 | 0 |  |  | 0% | 1181 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
994 | Ricky | 31-1200 | OG3 | 17 | CY | 4.534 | 0 | 433.7048 |  | 0 | 0 | 0 | 0 |  |  | 0% | 1181 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1178 | Ricky | 31-1200 | OG4 | 17 | CY | 4.534 | 0 | 433.7048 |  | 0 | 0 | 0 | 0 |  |  | 0% | 1181 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1361 | Ricky | 31-1200 | OG5 | 17 | CY | 4.534 | 0 | 433.7048 |  | 0 | 0 | 0 | 0 |  |  | 0% | 1181 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1545 | Ricky | 31-1200 | OG6 | 17 | CY | 4.534 | 0 | 433.7048 |  | 0 | 0 | 0 | 0 |  |  | 0% | 1181 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2514 | Ricky | 31-1200 | S81 | 6 | CY | 1.6002 | 0 | 153.0723 |  | 0 | 0 | 0 | 0 |  |  | 0% | 417 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1300 | EXCAVATION NEW BLDGS | 7237.55 | CY | 1784.69 | 4.0554 | 198142.88 | 111.5174 | 198891.36 | 198891.36 | 7237.55 | 1783.5 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | TRUE |  | FALSE |  | 198142.88 | 0 | 0 | 0 | 0 | 0
122 | Brian | 31-1300 | SG6 | 624 | CY | 153.8707 | 0 | 17083.2888 |  | 17159.262 | 0 | 624 | 153.8707 |  |  | 100% | 38439 | 38439 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
293 | Brian | 31-1300 | SG7 | 695 | CY | 171.3784 | 0 | 19027.0605 |  | 19111.6781 | 0 | 695 | 171.3784 |  |  | 100% | 42812 | 42812 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1730 | Brian | 31-1300 | OG8 | 1400 | CY | 345.2226 | 0 | 38327.8916 |  | 38498.3443 | 0 | 1400 | 345.2226 |  |  | 100% | 86240 | 86240 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1895 | Brian | 31-1300 | OG9 | 1150 | CY | 283.5757 | 0 | 31483.6253 |  | 31623.64 | 0 | 1150 | 283.5757 |  |  | 100% | 70840 | 70840 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2058 | Brian | 31-1300 | OG10 | 1310 | CY | 323.0297 | 0 | 35863.9557 |  | 36023.4508 | 0 | 1310 | 323.0297 |  |  | 100% | 80696 | 80696 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2550 | Ksenofon | 31-1300 | S82 | 1150 | CY | 283.5757 | 0 | 31483.6253 |  | 0 | 0 | 0 | 0 |  |  | 0% | 70840 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1400 | BACKFILL NEW BLDGS | 3448 | CY | 2191.96 | 1.573 | 223514.5 | 109.1311 | 108530.84 | 108530.84 | 2382.25 | 994.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 223514.5 | 0 | 0 | 0 | 0 | 0
123 | Brian | 31-1400 | SG6 | 432 | CY | 274.6307 | 0 | 28004.1369 |  | 29970.7417 | 0 | 432 | 274.6307 |  |  | 100% | 18099 | 18099 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
294 | Brian | 31-1400 | SG7 | 431 | CY | 273.995 | 0 | 27939.3125 |  | 29901.365 | 0 | 431 | 273.995 |  |  | 88.92% | 18057 | 16057 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1731 | Brian | 31-1400 | OG8 | 880 | CY | 559.4329 | 0 | 57045.464 |  | 61051.5109 | 0 | 880 | 559.4329 |  |  | 95% | 36868 | 35024.6 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
1896 | Brian | 31-1400 | OG9 | 900 | CY | 572.1473 | 0 | 58341.9519 |  | 62439.0453 | 0 | 900 | 572.1473 |  |  | 100% | 37706 | 37706 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2059 | Brian | 31-1400 | OG10 | 950 | CY | 603.9333 | 0 | 61583.1714 |  | 65907.8811 | 0 | 950 | 603.9333 |  |  | 100% | 39801 | 39801 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2552 | Ksenofon | 31-1400 | S82 | 840 | CY | 534.0042 | 0 | 54452.4884 |  | 0 | 0 | 0 | 0 |  |  | 0% | 35192 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1500 | BACKFILL STONE/GRAVEL/CRUSHED STONE - ALL | 301 | CY | 187.5 | 1.6053 | 21000.47 | 111.5326 | 10930.19 | 10930.19 | 171 | 98 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 21000.47 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-1500 | OG8 | 104 | CY | 64.7841 | 0 | 7255.9763 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1500 | OG9 | 104 | CY | 64.7841 | 0 | 7255.9763 |  | 7225.5307 | 0 | 104 | 64.7841 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1500 | OG10 | 104 | CY | 64.7841 | 0 | 7255.9763 |  | 4307.5279 | 0 | 62 | 38.6213 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 31-1600 | PUMP OPERATOR FOR FLOOD BARRIERS | 0 | MO | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1700 | DEWATER NEW BLDGS | 1006 | HR | 1032.05 | 0.97476 | 146472.08 | 147.4372 | 138001.19 | 138001.19 | 39.41 | 936 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 146472.08 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1700 | SG6 | 1.2 | HR | 1.2311 | 0 | 174.7182 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1700 | SG7 | 1.2 | HR | 1.2311 | 0 | 174.7182 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1700 | OG8 | 1.2 | HR | 1.2311 | 0 | 174.7182 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1700 | OG9 | 1.2 | HR | 1.2311 | 0 | 174.7182 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1700 | OG10 | 1.2 | HR | 1.2311 | 0 | 174.7182 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1700 | S82 | 1.2 | HR | 1.2311 | 0 | 174.7182 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1800 | INSTALL H PILES | 280 | LF | 223 | 1.2556 | 26802.94 | 120.1926 | 26802.94 | 26802.94 | 280 | 223 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 26802.94 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1800 | SG6 | 549 | LF | 437.2393 | 0 | 52552.9074 |  | 26802.94 | 0 | 280 | 223 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1800 | SG7 | 549 | LF | 437.2393 | 0 | 52552.9074 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1800 | OG8 | 1097 | LF | 873.6821 | 0 | 105010.0899 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1800 | OG10 | 549 | LF | 437.2393 | 0 | 52552.9074 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1800 | S82 | 1097 | LF | 873.6821 | 0 | 105010.0899 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1810 | SOE MATERIAL | 1 | LS | 0 | 1 | 498198.19 | 0.89169 | 444237.81 | 488598.19 | 0 | 0 | 0 | 0.89169 | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 493598.19 | 4600 | 0 | 0
0 | Brian | 31-1820 | INSTALL SHEETING | 8508.69 | SF | 1738.42 | 4.8945 | 210938.15 | 121.2359 | 203191.33 | 203191.33 | 8508.69 | 1676 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 210938.15 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1830 | INSTALL LAGGING | 6781 | SF | 339.21 | 19.9906 | 40239.14 | 119.1041 | 35909.9 | 35909.9 | 5810.5 | 301.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 38467.94 | 0 | 0 | 0 | 0 | 1771.2
0 | Brian | 31-1840 | MUD SLAB | 1110 | CY | 569.92 | 1.9476 | 63782.24 | 112.2803 | 55578.77 | 55578.77 | 863 | 495 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 63782.24 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1850 | SOE Sub | 836 | HR | 988.5 | 0.84573 | 582338.93 | 589.1137 | 582338.93 | 582338.93 | 836 | 988.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 133053.32 | 449285.61 | 0 | 0 | 0 | -5.8208e-11
0 | Brian | 31-1860 | SOE Sub Support | 12 | SH | 143 | 0.083916 | 15201.85 | 106.3066 | 15201.85 | 15201.85 | 11.91 | 143 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 15201.85 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1900 | TREE PROTECTION | 135 | EA | 347.66 | 0.38831 | 40000 | 109.5343 | 42006.42 | 42006.42 | 131 | 383.5 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | TRUE |  | FALSE |  | 40000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1900 | SGN | 28 | EA | 72.1073 | 0 | 8296.2963 |  | 7898.2212 | 0 | 28 | 72.1073 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1900 | SGS | 17 | EA | 43.7794 | 0 | 5037.037 |  | 4795.3486 | 0 | 17 | 43.7794 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1900 | OGE | 28 | EA | 72.1073 | 0 | 8296.2963 |  | 7898.2212 | 0 | 28 | 72.1073 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1900 | OGW | 48 | EA | 123.6124 | 0 | 14222.2222 |  | 5641.5865 | 0 | 20 | 51.5052 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-1900 | S8 | 14 | EA | 36.0536 | 0 | 4148.1481 |  | 846.238 | 0 | 3 | 7.7258 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2000 | TEST PIT SUPPORT | 1500.62 | CY | 493.38 | 3.0415 | 50000 | 104.44 | 67990.47 | 67990.47 | 1500.62 | 651 |  |  | 0% | 0 | 0 | TRUE | TRUE | TRUE | TRUE | TRUE |  | FALSE |  | 50000 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2000 | SGN | 150 | CY | 49.3176 | 0 | 4997.9342 |  | 5150.734 | 0 | 150 | 49.3176 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2000 | SGS | 160 | CY | 52.6055 | 0 | 5331.1298 |  | 5494.1163 | 0 | 160 | 52.6055 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2000 | OGE | 280 | CY | 92.0595 | 0 | 9329.4771 |  | 9614.7035 | 0 | 280 | 92.0595 |  |  | 0% | 0 | 0 | TRUE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2000 | OGW | 660 | CY | 216.9975 | 0 | 21990.9104 |  | 19572.7893 | 0 | 570 | 187.4069 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2000 | S8 | 400 | CY | 131.5136 | 0 | 13327.8245 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2010 | HAND EXCAVATION SUPPORT | 800 | CY | 256.14 | 3.1233 | 25614.4 | 109.915 | 1978.47 | 1978.47 | 5.87 | 18 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 25614.4 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2100 | EXCAVATION FOR SITE FURNISHING FOOTINGS | 410 | CY | 131.19 | 3.1252 | 13862.87 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 13862.87 | 0 | 0 | 0 | 0 | 0
333 | Ksenofon | 31-2100 | SGN | 82 | CY | 26.238 | 0 | 2772.574 |  | 0 | 0 | 0 | 0 |  |  | 0% | 4025 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
408 | Ksenofon | 31-2100 | SGS | 82 | CY | 26.238 | 0 | 2772.574 |  | 0 | 0 | 0 | 0 |  |  | 0% | 4025 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2091 | Ksenofon | 31-2100 | OGE | 82 | CY | 26.238 | 0 | 2772.574 |  | 0 | 0 | 0 | 0 |  |  | 0% | 4025 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2176 | Ksenofon | 31-2100 | OGW | 82 | CY | 26.238 | 0 | 2772.574 |  | 0 | 0 | 0 | 0 |  |  | 0% | 4025 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2316 | Ksenofon | 31-2100 | S8 | 82 | CY | 26.238 | 0 | 2772.574 |  | 0 | 0 | 0 | 0 |  |  | 0% | 4025 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2200 | BACKFILL UTILITIES | 13200 | CY | 3484.4 | 3.7883 | 383288.4 | 112.9807 | 107275.17 | 107275.17 | 3494.73 | 949.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 383288.4 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2200 | SGN | 2735 | CY | 721.9571 | 0 | 79416.195 |  | 49946.2764 | 0 | 1674.73 | 442.078 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2200 | SGS | 3475 | CY | 917.2947 | 0 | 100903.575 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2200 | OGE | 3955 | CY | 1044.0002 | 0 | 114841.335 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2200 | OGW | 3487 | CY | 920.4623 | 0 | 101252.019 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-2200 | S8 | 2522 | CY | 665.7316 | 0 | 73231.314 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2300 | EXCAVATION FOR PAVEMENTS | 590 | CY | 94.4 | 6.25 | 10328.22 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 10328.22 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2300 | OGE | 300 | CY | 48 | 0 | 5251.6373 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2300 | OGW | 300 | CY | 48 | 0 | 5251.6373 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2300 | S8 | 100 | CY | 16 | 0 | 1750.5458 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2400 | BACKFILL AND COMPACTION FOR PAVEMENTS | 280 | CY | 74.66 | 3.7503 | 7141.61 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 7141.61 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2400 | OGE | 235 | CY | 62.6611 | 0 | 5993.8512 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2400 | OGW | 100 | CY | 26.6643 | 0 | 2550.575 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2400 | S8 | 100 | CY | 26.6643 | 0 | 2550.575 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 31-2500 | DENSE GRADED STONE BASE | 1680 | CY | 627.2 | 2.6786 | 65042.88 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 65042.88 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 31-2500 | SG6 | 280 | CY | 104.5333 | 0 | 10840.48 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 31-2500 | SG7 | 280 | CY | 104.5333 | 0 | 10840.48 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 31-2500 | OG8 | 280 | CY | 104.5333 | 0 | 10840.48 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 31-2500 | OG9 | 280 | CY | 104.5333 | 0 | 10840.48 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 31-2500 | OG10 | 280 | CY | 104.5333 | 0 | 10840.48 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ricky | 31-2500 | S82 | 280 | CY | 104.5333 | 0 | 10840.48 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2600 | SITE FURNISHINGS | 117 | EA | 384 | 0.30469 | 38534.4 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 38534.4 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2600 | SGN | 20 | EA | 65.641 | 0 | 6587.0769 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2600 | SGS | 40 | EA | 131.2821 | 0 | 13174.1538 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2600 | OGE | 25 | EA | 82.0513 | 0 | 8233.8462 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2600 | OGW | 17 | EA | 55.7949 | 0 | 5599.0154 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2600 | S8 | 15 | EA | 49.2308 | 0 | 4940.3077 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2700 | BOLLARDS | 8 | EA | 48 | 0.16667 | 4816.8 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 4816.8 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2700 | SGS | 8 | EA | 48 | 0 | 4816.8 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2800 | DRINKING FOUNTAIN | 6 | EA | 298.95 | 0.02007 | 30000 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 30000 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2800 | SGN | 2 | EA | 99.65 | 0 | 10000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2800 | SGS | 1 | EA | 49.825 | 0 | 5000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2800 | OGE | 1 | EA | 49.825 | 0 | 5000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2800 | OGW | 1 | EA | 49.825 | 0 | 5000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2800 | S8 | 1 | EA | 49.825 | 0 | 5000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2900 | LANDSCAPE BOULDERS | 148 | EA | 96 | 1.5417 | 9888.96 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 9888.96 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2900 | SGN | 11 | EA | 7.1351 | 0 | 734.9903 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-2900 | OGW | 137 | EA | 88.8649 | 0 | 9153.9697 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-3000 | BASKETBALL BACKSTOP | 2 | EA | 32 | 0.0625 | 3296.32 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 3296.32 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-3000 | OGE | 2 | EA | 32 | 0 | 3296.32 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-4000 | VAC TRUCKING SUB | 0 | NA | 0 | 1 | 116000 |  | 90644.5 | 114830 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | TRUE | FALSE |  | FALSE |  | 0 | 116000 | 0 | 0 | 0 | 0
0 | Ksenofon | 31-5000 | FURNISH GRAVEL | 637.2 | CY | 0 | 1 | 12744 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 12744 | 0 | 0
0 | Ksenofon | 31-5100 | FURNISH CLEAN FILL | 8681 | CY | 0 | 1 | 173620 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 173620 | 0 | 0
0 | Brian | 31-6000 | DISPOSAL & TRUCKING SUB | 1 | LS | 0 | 1 | 1825933.66 |  | 1219605.85 | 1622004.33 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 110399 | 1715534.66 | 0 | 0 | 0
0 | Brian | 31-6100 | DEWATERING SUB | 1 | LS | 0 | 1 | 55850 |  | 38820 | 77640 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | TRUE |  | FALSE |  | 0 | 55850 | 0 | 0 | 0 | 0
0 | Brian | 31-6110 | FURNISH SETTLING TANK AND DISCHARGE PIPING BEYOND | 16 | UM | 0 | 1 | 19560 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 19560 | 0 | 0
0 | Brian | 31-6120 | INSTALL SETTLING TANK AND DISCHARGE PIPING BEYOND | 16 | DY | 48 | 0.33333 | 4800 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 4800 | 0 | 0 | 0 | 0 | 0
0 | 0 | 31-6130 | DISCHARGE LOCATIONS NOT INCLUDED WITHIN DEWATERING | 0 | EA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-6140 | DEEP WELL INSTALL SUPPORT & CLEANUP LABOR | 180 | DY | 440 | 0.40909 | 44000 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 44000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-6150 | DEEP WELL INSTALL SUPPORT & CLEANUP EQUIPMENT | 60 | DY | 0 | 1 | 6000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 6000 | 0
0 | Brian | 31-6160 | DEEP WELL INSTALL SUPPORT & CLEANUP CONSUMABLES | 400 | CY | 0 | 1 | 15000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 15000 | 0 | 0 | 0
0 | Brian | 31-6170 | REMOVE AND REINSTALL PUMPS & PIPING | 30 | DY | 0 | 1 | 63528.41 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 63528.41 | 0 | 0 | 0 | 0
0 | Brian | 31-6180 | WATER TREATMENT | 1 | LS | 0 | 1 | 60000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 60000 | 0 | 0 | 0
0 | Brian | 31-6190 | ELECTRIC SERVICE | 1 | LS | 0 | 1 | 66000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 66000 | 0 | 0 | 0
0 | 0 | 31-6200 | DUMPSTERS FOR DEWATERING | 0 | NA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 31-6210 | DEWATERING DISCHARGE | 1 | LS | 0 | 1 | 94177.11 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 94177.11 | 0 | 0 | 0
0 | Brian | 31-7000 | LUMBER - TREE PROTECTION | 9.34 | MB | 4 | 2.335 | 23107.9 | 5731.2525 | 22925.01 | 22925.01 | 9.34 | 4 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 994.29 | 0 | 22113.61 | 0 | 0 | 0
0 | Brian | 31-7100 | DEWATERING PUMPS | 10 | MO | 0 | 1 | 14.07 | #DIV/0! | 14.07 | 14.07 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 14.07 | 0 | 0 | 0 | 0 | 0
0 | 0 | 31-7200 | SOLDIER PILE & LAGGING BLDGS | 1 | LS | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-7300 | TRENCH BOX - UTILITY TRENCHES | 1 | LS | 0 | 1 | 184019.2 |  | 89729.08 | 110609.53 | 0.1 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 184019.2 | 0 | 0 | 0
0 | Sully | 31-7400 | PLATES - UTILITY TRENCHES | 3000 | SF | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 31-7500 | LUMBER - UTILITY TRENCHES | 11.25 | MB | 0 | 1 | 21915.27 |  | 12074.09 | 21915.27 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 21915.27 | 0 | 0 | 0
0 | Ksenofon | 32-5000 | FURNISH BOLLARDS | 8 | EA | 0 | 1 | 7600 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 7600 | 0 | 0
0 | Ksenofon | 32-5100 | FURNISH SUBBASE | 2268 | CY | 0 | 1 | 56700 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 56700 | 0 | 0
0 | Brian | 32-5200 | FURNISH BENCHES & TABLES | 106 | EA | 0 | 1 | 393000 | 0.48446 | 190392.5 | 380865 | 0 | 0 | 0 | 51.3527 | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 393000 | 0 | 0
0 | Ksenofon | 32-5300 | FURNISH PING PONG TABLE | 3 | EA | 0 | 1 | 32700 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 32700 | 0 | 0
0 | Ksenofon | 32-5400 | FURNISH BIKE RACK | 8 | EA | 0 | 1 | 2400 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 2400 | 0 | 0
0 | Ksenofon | 32-5500 | FURNISH DRINKING FOUNTAIN | 6 | EA | 0 | 1 | 9000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 9000 | 0 | 0
0 | Ksenofon | 32-5600 | FURNISH SHOWER EQUIPMENT | 6 | EA | 0 | 1 | 26188.02 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 26188.02 | 0 | 0
0 | Brian | 32-5700 | FURNISH LANDSCAPE BOULDERS | 148 | EA | 0 | 1 | 239316 | 0.79849 | 191092.5 | 221092.5 | 0 | 0 | 0 | 118.1772 | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 239316 | 0 | 0
0 | Ksenofon | 32-5800 | FURNISH BASKETBALL BOARD AND POST | 2 | EA | 0 | 1 | 5340 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 5340 | 0 | 0
0 | Ricky | 32-6000 | SAWCUTTING | 71 | EA | 609.74 | 0.11644 | 73317.26 | 122.8757 | 72496.64 | 72921.26 | 71 | 590 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 61009.11 | 0 | 12308.15 | 0 | 0 | -5.457e-12
0 | Ksenofon | 32-6100 | ASPHALT SUB | 1 | LS | 0 | 1 | 210269.79 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 210269.79 | 0 | 0 | 0 | 0
0 | Ricky | 32-6200 | FLATWORK SUB | 1 | LS | 0 | 1 | 2940000 |  | 0 | 2940000 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 2940000 | 0 | 0 | 0 | 0
0 | Ricky | 32-6210 | FLATWORK SUB SUPPORT | 0 | NA | 0 | 1 | 100000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 100000 | 0 | 0 | 0 | 0
0 | 0 | 32-6300 | ASPHALT- PAVEMENT MARKINGS SUB | 10500 | LF | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Ksenofon | 32-6400 | COURT SURFACES SUB | 8500 | SF | 0 | 1 | 425000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 425000 | 0 | 0 | 0 | 0
0 | Ricky | 32-6500 | FENCING SUB | 1 | LS | 0 | 1 | 1318652.5 |  | 757678.8 | 1036387.5 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 1318652.5 | 0 | 0 | 0 | 0
0 | Brian | 32-6510 | FENCE MESH INSTALL | 12874.82 | LF | 815.68 | 15.7842 | 93745.65 | 106.9209 | 76020.75 | 77071.4 | 12874.82 | 711 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 82644.04 | 0 | 11101.61 | 0 | 0 | 0
0 | Brian | 32-6520 | FENCE INSTALL SELF PERFORM | 6600 | LF | 1895.1 | 3.4827 | 225465.3 | 127.3587 | 184160.72 | 189497.3 | 4358.65 | 1446 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 190465.3 | 0 | 35000 | 0 | 0 | 0
0 | Brian | 32-6600 | LANDSCAPING SUB | 1 | LS | 0 | 1 | 635225.54 |  | 31172.29 | 638633.25 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | TRUE |  | FALSE |  | 0 | 635225.54 | 0 | 0 | 0 | 0
0 | Brian | 32-6610 | CLEAR AND GRUB | 137053 | SF | 793 | 172.8285 | 86871.02 | 113.6631 | 67402.2 | 67402.2 | 96191.99 | 593 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 86871.02 | 0 | 0 | 0 | 0 | 0
0 | Brian | 32-6620 | SELF PERFORM TREE REMOVAL | 52 | EA | 184.1 | 0.28246 | 18000 | 100.1189 | 17771.11 | 17771.11 | 52 | 177.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 18000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 32-6630 | LANDSCAPING SUB SUPPORT | 500 | HR | 516.63 | 0.96781 | 50000 | 98.4848 | 21223.48 | 21223.48 | 151.5 | 215.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 50000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 32-6700 | Arbor Consultant | 0 | HR | 0 | 1 | 1134.2 |  | 960 | 1134.2 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | TRUE | FALSE |  | FALSE |  | 0 | 1134.2 | 0 | 0 | 0 | 0
0 | Sully | 33-1000 | MAINT & PROT EXIST PRIVATELY OWNED UTILITIES | 5 | LO | 428.02 | 0.011682 | 51626.6 | 113.4559 | 22010.45 | 22010.45 | 2.15 | 194 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 51626.6 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-1000 | SGN | 1 | LO | 85.604 | 0 | 10325.32 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-1000 | SGS | 1 | LO | 85.604 | 0 | 10325.32 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-1000 | OGE | 1 | LO | 85.604 | 0 | 10325.32 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-1000 | OGW | 1 | LO | 85.604 | 0 | 10325.32 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-1000 | S8 | 1 | LO | 85.604 | 0 | 10325.32 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-1100 | TERMINATE AND DEMOLISH EXISTING UTILITIES | 3300 | LF | 527.97 | 6.2504 | 56789.26 | 113.4326 | 5501.48 | 5501.48 | 383.13 | 48.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 56789.26 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-1100 | SGN | 950 | LF | 151.9914 | 0 | 16348.4233 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-1100 | SGS | 982 | LF | 157.1111 | 0 | 16899.1071 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-1100 | OGE | 334 | LF | 53.437 | 0 | 5747.7615 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-1100 | OGW | 770 | LF | 123.193 | 0 | 13250.8273 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-1100 | S8 | 263 | LF | 42.0776 | 0 | 4525.9319 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1200 | WATER | 0 | LF | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1300 | WELDING OF WATER PIPE | 383.28 | LF | 1735.36 | 0.22086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1310 | WATER PIPE FIT UP | 0 | EA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1400 | INSTALL JOJNT INSULATORS | 0 | EA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1400 | SGN | 988 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1400 | SGS | 1237 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1400 | OGE | 568 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1400 | OGW | 1109 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1500 | PRESSURE & AIR TEST | 0 | EA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1600 | FIX 10% FAILURE PIPE | 0 | LF | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1700 | PRESSURE & AIR RE-TEST | 2 | EA | 25 | 0.08 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1700 | SGN | 4 | EA | 50 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1700 | SGS | 5 | EA | 62.5 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1700 | OGE | 2 | EA | 25 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1700 | OGW | 5 | EA | 62.5 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1800 | CONDENSATE & STEAM PIPE | 0 | LF | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1900 | WELDING OF STEAM AND CONDENSATE PIPE | 0 | LF | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-1910 | STEAM AND CONDENSATE PIPE FIT UP | 0 | EA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2000 | INSTALL JOJNT INSULATORS | 0 | EA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2000 | SGN | 622 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2000 | SGS | 1042 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2000 | OGE | 862 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2000 | OGW | 1256 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2000 | S8 | 113 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2100 | PRESSURE & AIR TEST | 0 | EA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2200 | FIX 10% FAILURE PIPE | 0 | LF | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-2210 | EXCAVATE UTILITIES | 8515 | CY | 0 | 1 | 15.82 | #DIV/0! | 15.82 | 15.82 | 25 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 15.82 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2300 | PRESSURE & AIR RE-TEST | 2 | EA | 24 | 0.083333 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2300 | SGN | 2 | EA | 24 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2300 | SGS | 3 | EA | 36 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2300 | OGE | 3 | EA | 36 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2300 | OGW | 5 | EA | 60 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-2300 | S8 | 1 | EA | 12 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-2400 | DEWATER UTILITIES | 3.08 | MO | 835.86 | 0.0036848 | 90000 | 157.9289 | 29769.59 | 29769.59 | 0.83 | 188.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 90000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-2400 | SGN | 1.6 | MO | 434.213 | 0 | 46753.2468 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-2400 | SGS | 1.6 | MO | 434.213 | 0 | 46753.2468 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-2400 | OGE | 1.6 | MO | 434.213 | 0 | 46753.2468 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-2400 | OGW | 1.6 | MO | 434.213 | 0 | 46753.2468 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-2400 | S8 | 1.6 | MO | 434.213 | 0 | 46753.2468 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-2500 | DUCTILE IRON PIPE SEWERS | 3799 | LF | 2431.36 | 1.5625 | 276988.13 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 276988.13 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-2500 | SGN | 699 | LF | 447.36 | 0 | 50964.6493 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-2500 | SGS | 615 | LF | 393.6 | 0 | 44840.1421 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-2500 | OGE | 1028 | LF | 657.92 | 0 | 74952.3026 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-2500 | OGW | 869 | LF | 556.16 | 0 | 63359.4854 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-2500 | S8 | 588 | LF | 376.32 | 0 | 42871.5505 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-2600 | CATCH BASIN CONNECTIONS | 86 | EA | 2914.74 | 0.029505 | 313516.44 | 107.7227 | 3177.82 | 3177.82 | 0.5 | 29.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 313516.44 | 0 | 0 | 0 | 0 | 0
377 | Sully | 33-2600 | SGN | 19 | EA | 643.9542 | 0 | 69265.26 |  | 0 | 0 | 0 | 0 |  |  | 50% | 165979 | 82989.5 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
446 | Sully | 33-2600 | SGS | 9 | EA | 305.0309 | 0 | 32809.86 |  | 0 | 0 | 0 | 0 |  |  | 50% | 78622 | 39311 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2136 | Sully | 33-2600 | OGE | 18 | EA | 610.0619 | 0 | 65619.72 |  | 0 | 0 | 0 | 0 |  |  | 10% | 157243 | 15724.3 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2225 | Sully | 33-2600 | OGW | 15 | EA | 508.3849 | 0 | 54683.1 |  | 0 | 0 | 0 | 0 |  |  | 0% | 131036 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2357 | Sully | 33-2600 | S8 | 8 | EA | 271.1386 | 0 | 29164.32 |  | 0 | 0 | 0 | 0 |  |  | 50% | 69886 | 34943 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-2700 | STORM DETENTION TANK (I DON'T THINK THIS EXISTS) | 1 | EA | 64 | 0.015625 | 7291.08 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 7291.08 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-2800 | DRAINAGE MANHOLES | 3 | EA | 192 | 0.015625 | 21873.24 | 110.506 | 552.53 | 552.53 | 0.3 | 5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 21873.24 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-2800 | OGE | 2 | EA | 128 | 0 | 14582.16 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-2900 | REMOVE AREA DRAINS | 18 | EA | 253.01 | 0.071143 | 32809.86 | 129.68 | 1167.12 | 1167.12 | 0.5 | 9 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 32809.86 | 0 | 0 | 0 | 0 | 0
378 | Sully | 33-2900 | SGN | 2 | EA | 28.1122 | 0 | 3645.54 |  | 0 | 0 | 0 | 0 |  |  | 45% | 23320 | 10494 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
447 | Sully | 33-2900 | SGS | 2 | EA | 28.1122 | 0 | 3645.54 |  | 0 | 0 | 0 | 0 |  |  | 0% | 23320 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2138 | Sully | 33-2900 | OGE | 5 | EA | 70.2806 | 0 | 9113.85 |  | 0 | 0 | 0 | 0 |  |  | 0% | 58300 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2226 | Sully | 33-2900 | OGW | 4 | EA | 56.2244 | 0 | 7291.08 |  | 0 | 0 | 0 | 0 |  |  | 0% | 46640 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
2358 | Sully | 33-2900 | S8 | 5 | EA | 70.2806 | 0 | 9113.85 |  | 0 | 0 | 0 | 0 |  |  | 0% | 58300 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-3000 | ELECTRICAL MANHOLES | 0 | EA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-3000 | SGN | 1 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-3000 | SGS | 5 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-3000 | OGE | 2 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-3000 | S8 | 1 | EA | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-3100 | UTILITY TRENCHES | 25454 | CY | 6580.61 | 3.868 | 721945.44 | 112.3986 | 522203.94 | 522203.94 | 15708.6 | 4646 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE | Got numbers from Sully | 721945.44 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-3100 | SGN | 6432 | CY | 1662.8618 | 0 | 182429.2084 |  | 59008.8052 | 0 | 2030.7 | 524.9959 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-3100 | SGS | 3174 | CY | 820.5726 | 0 | 90023.3687 |  | 45262.4589 | 0 | 1557.64 | 402.6959 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-3100 | OGE | 6289 | CY | 1625.8921 | 0 | 178373.3351 |  | 156448.1589 | 0 | 5383.93 | 1391.9048 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-3100 | OGW | 7663 | CY | 1981.1116 | 0 | 217343.7537 |  | 147447.9141 | 0 | 5074.2 | 1311.8304 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-3100 | S8 | 1000 | CY | 258.5295 | 0 | 28362.7501 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 33-3200 | FENCES & PLATES @ TRENCHES (THIS WILL BE DIFFERENT | 0 | EA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-3300 | ADD''L CRANE FOR SUBCONTRACTORS SUPPORT | 12 | MO | 2112 | 0.0056818 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-3300 | SGN | 2.5 | MO | 440 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-3300 | SGS | 2.5 | MO | 440 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-3300 | OGE | 2.5 | MO | 440 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-3300 | OGW | 2.5 | MO | 440 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-3300 | S8 | 2.5 | MO | 440 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-5000 | FURNISH CW, HW, STEAM & CONDENSATE PIPE | 7796 | LF | 0 | 1 | 879382.81 | 0.78915 | 693964.05 | 891502.41 | 0 | 0 | 0 | 6152.2055 | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | TRUE |  | FALSE |  | 0 | 0 | 0 | 879382.81 | 0 | 0
0 | Sully | 33-5100 | FURNISH 2 COPPER WATER PIPE | 675 | LF | 0 | 1 | 115654.5 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 115654.5 | 0 | 0
0 | Sully | 33-5200 | FURNISH DIP DRAINAGE PIPE | 3799 | LF | 0 | 1 | 195314.32 | 0.18678 | 36480.09 | 195314.32 | 0 | 0 | 0 | 709.5632 | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 195314.32 | 0 | 0
0 | Sully | 33-5300 | FURNISH PRECAST AREA DRAINS & MHS | 89 | EA | 0 | 1 | 126016 | 0.077014 | 9705 | 43507.31 | 0 | 0 | 0 | 6.8542 | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 126016 | 0 | 0
0 | 0 | 33-5400 | FURNISH PRECAST ELECTRICAL MANHOLES | 6 | EA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-5500 | FURNISH DETENTION TANK | 1 | EA | 0 | 1 | 3500 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 0 | 3500 | 0 | 0
0 | Sully | 33-5600 | CHLORINATION | 0 | NA | 0 | 1 | 100000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 0 | 100000 | 0 | 0 | 0
0 | Sully | 33-6000 | UNDERGROUND UTILITY MATERIAL DELIVERY | 8000 | LF | 214.98 | 37.2128 | 25000 | 114.0146 | 20750.65 | 20750.65 | 7300.5 | 182 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 25000 | 0 | 0 | 0 | 0 | 0
0 | Sully | 33-6010 | UTILITY PIPE PLACEMENT IN TRENCH | 8000 | LF | 607.44 | 13.17 | 75000 | 123.1251 | 65810.37 | 65810.37 | 5014 | 534.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 75000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 33-7000 | WELDING MATERIALS | 1 | LS | 0 | 1 | 32664 |  | 10566.44 | 11214.07 | 0.29 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 32664 | 0 | 0 | 0
0 | Brian | 33-9000 | GAS LINE DAMAGE | 14 | HR | 14 | 1 | 1607.9 | 114.85 | 1607.9 | 1607.9 | 14 | 14 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 1607.9 | 0 | 0 | 0 | 0 | 0
0 | Brian | 97-6000 | Bulk ACM removal, hose wire insulation | 1 | LF | 0 | 1 | 25 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 25 | 0 | 0 | 0 | 0
0 | Brian | 97-6100 | Bulk ACM removal, pipe mold joint and pipe insulat | 1 | LF | 0 | 1 | 74 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 74 | 0 | 0 | 0 | 0
0 | Brian | 97-6200 | Bulk ACM removal, pipe insulation and assoc jack | 1 | LF | 0 | 1 | 42 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 42 | 0 | 0 | 0 | 0
0 | Brian | 97-6300 | Bulk ACM removal, pipe insulation and braided wire | 1 | LF | 0 | 1 | 42 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 42 | 0 | 0 | 0 | 0
0 | Brian | 97-6400 | Bulk ACM removal, ACM Contamined Debris | 1 | SF | 0 | 1 | 25 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 25 | 0 | 0 | 0 | 0
0 | Brian | 97-6500 | Bulk ACM removal, ACM Contamined Debris at Pump an | 1 | SF | 0 | 1 | 30 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 30 | 0 | 0 | 0 | 0
0 | Brian | 97-6600 | Hazardous waste cleanup/pickup/disposal, solid pic | 1 | CY | 0 | 1 | 400 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 400 | 0 | 0 | 0 | 0
0 | Brian | 97-6700 | Bulk ACM removal, ACM Fibrous un-identified gasket | 1 | SF | 0 | 1 | 750 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 750 | 0 | 0 | 0 | 0
0 | Brian | 97-6800 | Bulk ACM removal, ACM Fibrous Slate at Window Sill | 1 | SF | 0 | 1 | 85 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 85 | 0 | 0 | 0 | 0
0 | Brian | 97-7000 | TESTING, HANDLING, DISPOSAL OF PETROLIUM CONT SOIL | 1 | CY | 0 | 1 | 60 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 60 | 0 | 0 | 0 | 0
0 | Brian | 98-1000 | ALLOWANCE -CON EDISON ELEC UTILITY SERVICE FEE | 1 | LS | 0 | 1 | 51926.66 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 51926.66 | 0 | 0 | 0 | 0
0 | Brian | 98-1100 | ALLOWANCE - NATIONAL GRID GAS UTILITY SERVICE FEE | 1 | LS | 0 | 1 | 141408 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 141408 | 0 | 0 | 0 | 0
0 | Brian | 99-1000 | Supervision | 37 | MO | 86699.54 | 0.00042676 | 6505000 | 78.8683 | 3590333.45 | 3590421.76 | 15 | 45523.13 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 6440000 | 0 | 65000 | 0 | 0 | 0
0 | Brian | 99-1010 | CLAIMS CONSULTANT | 0 | NA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-1020 | LEGAL COSTS | 0 | NA | 0 | 1 | 50000 |  | 3530 | 3530 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | FALSE | FALSE |  | FALSE |  | 0 | 0 | 50000 | 0 | 0 | 0
0 | Brian | 99-1100 | TEAMSTER | 18 | MO | 3150 | 0.0057143 | 315000 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 315000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-1200 | OPER ENG MASTER MECH | 24 | MO | 6000 | 0.004 | 600000 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 600000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-1300 | OPER ENG MECH | 24 | MO | 4800 | 0.005 | 480000 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 480000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-2000 | SURVEY SUB | 9 | EA | 0 | 1 | 464129 |  | 287311 | 355038.25 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 442829 | 21300 | 0 | 0 | 0
0 | Brian | 99-3000 | SECURITY SUB | 37 | MO | 0 | 1 | 648295.5 |  | 0 | 0 | 8 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 648295.5 | 0 | 0 | 0 | 0
0 | Brian | 99-3100 | CONTAINERS - 30 CY | 400 | EA | 0 | 1 | 602492.6 |  | 469060.96 | 667548.22 | 80 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | TRUE |  | FALSE |  | 0 | 0 | 602492.6 | 0 | 0 | 0
0 | Brian | 99-4000 | YARD W/ TEMP ELECT | 72.59 | LS | 535.04 | 0.13567 | 138034 | 271.6718 | 100926.09 | 100926.09 | 72.59 | 371.5 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 55815.7 | 0 | 82218.3 | 0 | 0 | 0
0 | Brian | 99-4050 | COMPUTER/SOFTWARE | 8 | EA | 0 | 1 | 75328 |  | 70675.7 | 70675.7 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 75328 | 0 | 0 | 0
0 | Brian | 99-4100 | STATIONWORK DESK | 8 | EA | 0 | 1 | 8710.4 |  | 6193.68 | 6193.68 | 7 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 8710.4 | 0 | 0 | 0
0 | Brian | 99-4150 | IT SUPPORT | 37 | MO | 0 | 1 | 0 |  | 0 | 0 | 15 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-4200 | PHONE EQUIPMENT | 8 | EA | 0 | 1 | 0 |  | 0 | 0 | 7 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-4250 | PHONE SYSTEM | 271 | UM | 0 | 1 | 0 |  | 0 | 0 | 50.65 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-4300 | PRINTERS/PLOTTER | 37 | MO | 0 | 1 | 60428.4 |  | 29177.84 | 29177.84 | 15 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 60428.4 | 0 | 0 | 0
0 | Brian | 99-4350 | SUPPLIES | 271 | UM | 0 | 1 | 50000 |  | 38650.2 | 38650.2 | 14.65 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 50000 | 0 | 0 | 0
0 | Brian | 99-4400 | TELEPHONE | 37 | MO | 0 | 1 | 18500 |  | 0 | 0 | 8 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 18500 | 0 | 0 | 0
0 | Brian | 99-4450 | CELL PHONES | 271 | UM | 0 | 1 | 29506.48 |  | 15925.44 | 15925.44 | 14.65 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 29506.48 | 0 | 0 | 0
0 | Brian | 99-4500 | ELECTRIC | 37 | MO | 0 | 1 | 18500 |  | 0 | 0 | 8 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 18500 | 0 | 0 | 0
0 | Brian | 99-4550 | SANITATION | 37 | MO | 0 | 1 | 140000 |  | 59841.64 | 163854.72 | 15 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | TRUE |  | FALSE |  | 0 | 0 | 140000 | 0 | 0 | 0
0 | Brian | 99-4560 | SITE MAINTENANCE | 5501.9 | HR | 5501.91 | 1 | 576000 | 105.3825 | 452618.05 | 452618.05 | 4193 | 4295 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 576000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-4570 | BASEMENT MAINTENANCE | 960 | HR | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-4600 | VEHICLES | 180 | MO | 36 | 5 | 276079.76 | 13806.36 | 41419.08 | 47845.66 | 15 | 3 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 8951.52 | 0 | 259125.74 | 0 | 0 | 8002.5
0 | Brian | 99-4650 | FUEL | 180 | MO | 0 | 1 | 270000 |  | 65740.55 | 185950.35 | 15 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 270000 | 0 | 0 | 0
0 | Brian | 99-4700 | PETTY CASH | 37 | MO | 0 | 1 | 111000 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 111000 | 0 | 0 | 0
0 | Brian | 99-5000 | OFFICE RENT | 222 | UM | 0 | 1 | 561000 |  | 346706.64 | 354839.6 | 12 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 561000 | 0 | 0 | 0
0 | Brian | 99-5100 | NYCHA OFFICE FURNITURE | 1 | LS | 62.5 | 0.016 | 55000 | 616.5718 | 38535.74 | 39815.74 | 0.67 | 62.5 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 5278.48 | 0 | 49721.52 | 0 | 0 | 7.276e-12
0 | Brian | 99-6000 | SMALL TOOLS | 37 | MO | 0 | 1 | 468000 |  | 436297 | 585126.09 | 15 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | TRUE |  | FALSE |  | 0 | 0 | 468000 | 0 | 0 | 0
0 | Brian | 99-7000 | LABOR ESCAL | 1 | LS | 10000 | 0.0001 | 1000000 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 1000000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-7100 | PREMIUM COST | 1 | LS | 5000 | 0.0002 | 500000 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 500000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-7200 | HOLIDAY PAY | 1 | LS | 1306.61 | 0.00076534 | 150000 | 114.4261 | 112824.18 | 112824.18 | 0.67 | 986 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | TRUE | FALSE |  | FALSE |  | 149567.44 | 0 | 432.56 | 0 | 0 | -2.3306e-12
0 | Brian | 99-7300 | LOST TIME | 1 | LS | 1500 | 0.00066667 | 150000 | 124.7376 | 39042.88 | 39042.88 | 0.26 | 313 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 150000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-7400 | PERMITS | 1 | LS | 0 | 1 | 15000 |  | 10323.7 | 12648.7 | 0.79 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 15000 | 0 | 0 | 0
0 | Brian | 99-7500 | ENGINEERING SUB | 1 | LS | 0 | 1 | 183350 |  | 156801.29 | 171495.35 | 0.86 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | TRUE | FALSE |  | FALSE |  | 0 | 183350 | 0 | 0 | 0 | 0
0 | Brian | 99-7510 | CADD SERVICES | 9 | EA | 0 | 1 | 12600 |  | 8018.23 | 9675.93 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 12600 | 0 | 0 | 0
0 | Brian | 99-7600 | SECTION 3 ADMINISTRATOR SUB | 1 | LS | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-8000 | EQUIPMENT | 1 | LS | 0 | 1 | 1561716.25 |  | 746909.31 | 990268.78 | 0.38 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 79841.59 | 0 | 1466386.33 | 15488.33
0 | Brian | 99-8050 | AID TO SUBS | 1 | LS | 2500 | 0.0004 | 250000 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 250000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-8100 | PROJECT SIGNS | 1 | EA | 0 | 1 | 4000 |  | 2854.7 | 2854.71 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | TRUE | FALSE |  | FALSE |  | 0 | 0 | 4000 | 0 | 0 | 0
0 | Brian | 99-8200 | PUNCH LIST | 1 | LS | 2500 | 0.0004 | 250000 | #DIV/0! | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE |  | 250000 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-9000 | BOND | 1 | LS | 0 | 1 | 1170144 |  | 759012.08 | 759012.08 | 0.48 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | TRUE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 1170144 | 0 | 0 | 0
0 | Brian | 99-9100 | INSURANCE | 1 | LS | 0 | 1 | 3248000 |  | 836851 | 836851 | 0.2 | 0 |  |  | 0% | 0 | 0 | FALSE | TRUE | FALSE | FALSE | FALSE |  | FALSE |  | 0 | 0 | 40000 | 0 | 0 | 3208000
0 | Brian | 99-9999 | Accruals | 0 | NA | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | #DIV/0! | FALSE |  | FALSE |  | 0 | 0 | 0 | 0 | 0 | 0
0 | Brian | 99-NY0001 | Supervision- Do Not Use | 0 | NA | 248 | 0 | 22408.12 | 90.3553 | 22408.12 | 22408.12 | 0 | 248 |  |  | 0% | 0 | 0 | FALSE | #DIV/0! | #DIV/0! | TRUE | FALSE |  | FALSE |  | 16208.12 | 0 | 6200 | 0 | 0 | 1.819e-12