## Coney Island Sites-Sandy Work C
Item # | Description | Current Commitment | Total | This Period Requested | Actuals Approved | Total | Award/Funding | SOV Level 1 | SOV Level 2 | Notes | Percent Complete | Sub | Resp | Total>Commitment? | Approved<Requested?
11 | Mobilization | 4000000 | 4000000 |  |  | 4000000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
12 | Bond | 1170144 | 1170144 |  |  | 1170144 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
13 | Insurance | 1057256 | 383997.2581 | 2593.4288 |  | 386590.6869 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions | percentage of completion | 36.57% | General Conditions | Brian | FALSE | TRUE | FALSE
14 | Project Management | 7740000 | 2811181.7377 | 18986.0726 |  | 2830167.8102 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions | percentage of completion | 36.57% | General Conditions | Brian | FALSE | TRUE | FALSE
15 | Noise Reduction Plan | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
16 | Lead Safe Work Practice Plan | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
17 | Rodent Control | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
18 | Waste Management Plan | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
19 | Site Specific Safety Plan | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
20 | Site Safety Plan | 30000 | 30000 |  |  | 30000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
21 | Quality Plan | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
22 | CPM - Baseline | 40000 | 40000 |  |  | 40000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
23 | CPM - Monthly Updates | 36000 | 12906.43 | 88.3073 |  | 12994.7373 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions | percentage of completion | 36.1% | General Conditions | Brian | FALSE | TRUE | FALSE
24 | Field Office - Set Up | 40000 | 40000 |  |  | 40000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
25 | Field Office - Rent, Maintenance and Supplies | 36000 | 12906.43 | 88.3073 |  | 12994.7373 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions | percentage of completion | 36.1% | General Conditions | Brian | FALSE | TRUE | FALSE
26 | Yard - Set Up | 30000 | 30000 |  |  | 30000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
27 | Yard - Maintenance | 36000 | 12906.43 | 88.3073 |  | 12994.7373 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions | percentage of completion | 36.1% | General Conditions | Brian | FALSE | TRUE | FALSE
28 | Photos | 36000 | 12906.43 | 88.3073 |  | 12994.7373 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions | percentage of completion | 36.1% | General Conditions | Brian | FALSE | TRUE | FALSE
29 | Filing Alt1 permits | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
30 | Filing Alt2 permits | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
31 | Filing NB permits | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
32 | Filing CCD1 for Fence | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
33 | Filing Fence Permit | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
34 | Filing dewatering permits | 10000 | 8190 |  |  | 8190 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 81.9% | General Conditions | Brian | FALSE | FALSE | TRUE
35 | Filing DOT permits | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
36 | Filing Demo Permit | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
37 | Filing Asbestos permits | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
38 | Filing Electrical Permits | 10000 | 10000 |  |  | 10000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
39 | Shop Drawings / Submittals (exc O&M, As-Built and Warranty) | 218350 | 174680 |  |  | 174680 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 80% | General Conditions | Brian | FALSE | TRUE | TRUE
40 | O&M, As-Built and Warranty | 155650 | 0 |  |  | 0 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 0% | General Conditions | Brian | FALSE | FALSE | TRUE
41 | Survey | 24000 | 8604.2866 | 58.8715 |  | 8663.1582 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions | percentage of completion | 36.1% | General Conditions | Brian | FALSE | TRUE | FALSE
42 | Engineering | 36000 | 12906.43 | 88.3073 |  | 12994.7373 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions | percentage of completion | 36.1% | General Conditions | Brian | FALSE | TRUE | FALSE
43 | Demobilization/Project Closeout | 36850 | 0 |  |  | 0 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 0% | General Conditions | Brian | FALSE | FALSE | TRUE
44 | Soil Testing and Management Plan | 5000 | 5000 |  |  | 5000 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 100% | General Conditions | Brian | FALSE | FALSE | TRUE
45 | Punchlist | 51150 | 0 |  |  | 0 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 0% | General Conditions | Brian | FALSE | FALSE | TRUE
46 | Training | 61600 | 0 |  |  | 0 | 01- RESAND: General Conditions | A- General Conditions | 001 - General Conditions |  | 0% | General Conditions | Brian | FALSE | FALSE | TRUE
47 | Gaskets | 22500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
48 | Wire Insulation | 37500 | 37500 |  |  | 37500 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
49 | Assumed Flooring Material (Slab Penetrations) | 10800 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
50 | Pipe Insulation | 132300 | 132300 |  |  | 132300 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
51 | Duct Seal | 43200 | 43200 |  |  | 43200 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
52 | Vinyl Membrane and Mastic | 36720 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
53 | Caulk | 110250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
54 | Fibrous Slate | 12240 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
55 | Waterproofing | 4971 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
56 | Underground Utility Materials | 46800 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
57 | Remove existing paint and plaster - cellar | 60000 | 60000 |  |  | 60000 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
58 | Remove sump pump - cellar | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
59 | Remove existing vent / window and frame - cellar | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
60 | Remove existing door, frame and hardware - cellar and 1st floor | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
61 | Remove Areaway slab and drain - cellar | 60000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
62 | Remove Areaway grate - cellar | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
63 | Sawcut and remove portion of areaway wall - cellar | 60000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
64 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
65 | Remove window sill - 1st floor | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
66 | Remove existing stair - 1st floor | 80000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
67 | Remove Existing Ramp - 1st floor | 80000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
68 | Existing Ramp railing to be be removed - 1st floor | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 002 - SG1 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
69 | FORM FLOOD BARRIER FOUNDATIONS - SG-1 | 50095 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 003 - SG1 - Division 3 |  | 0% | MLJ | Brian | FALSE | FALSE | TRUE
70 | DRILL & GROUT DOWELS - SG-1 | 6278 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 003 - SG1 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
71 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-1 | 30151 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 003 - SG1 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
72 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-1 | 33906 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 003 - SG1 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
73 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-1 | 18856 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 003 - SG1 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
74 | Footing/Pier | 17434 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 003 - SG1 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
75 | Retaining Walls | 4571 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 003 - SG1 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
76 | Entrance Slab | 21380 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 003 - SG1 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
77 | Concrete Shelf | 4895 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 003 - SG1 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
78 | New Concrete Curb Next to Existing Wall | 297 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 003 - SG1 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
79 | GFRP Sikawrap 100 G | 58344 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 003 - SG1 - Division 3 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
80 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-1 | 360 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 004 - SG1 - Division 4 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
81 | Overhead protection for Masonry | 10175 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 004 - SG1 - Division 4 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
82 | 6" vertically reinforced CMU | 230912 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 004 - SG1 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
83 | 2" Face brick | 597520 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 004 - SG1 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
84 | 2" rigid Insulation | 39424 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 004 - SG1 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
85 | Coping Stone C1/A-300 | 13200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 004 - SG1 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
86 | MATERIAL AND FABRICATION | 5824 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 005 - SG1 - Division 5 | No structural steel to be installed in SG1; Will bill in line with other existing buildings | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
87 | INSTALLATION | 6600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 005 - SG1 - Division 5 | No structural steel to be installed in SG1; Will bill in line with other existing buildings | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
88 | Temporary Aluminum Over Pass Stairs | 57196 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 005 - SG1 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
89 | PENETRATION FIRESTOPPING EXTG BLDG - SG-1 | 11505 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 006 - SG1 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
90 | JOINT SEALANTS EXTG BLDGS - SG-1 | 11505 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 006 - SG1 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
91 | Bituthene 4000 waterproofing membrane | 37752 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 006 - SG1 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
92 | GE Elemax 2600 Silicone air and vapor barrier | 31416 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 006 - SG1 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
93 | Crystalline Waterproofing at perimeter walls | 37260 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 006 - SG1 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
94 | Waterproofing at foundation walls | 17250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 006 - SG1 - Division 7 |  | 0% | DStar | Ricky | FALSE | FALSE | TRUE
95 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-1 | 1200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 007 - SG1 - Division 8 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
96 | Doors, Frames & Hardware - Labor | 6672 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 007 - SG1 - Division 8 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
97 | Furnish Doors | 2091 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 008 - SG1 - Division 9 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
98 | Layout | 2829 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 008 - SG1 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
99 | Loading | 3858 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 008 - SG1 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
100 | Framing & Drywall - Materials | 2829 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 008 - SG1 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
101 | Framing- Labor | 4629 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 008 - SG1 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
102 | Drywall - Labor | 4629 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 008 - SG1 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
103 | Tape/ Spackle finishes | 3086 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 008 - SG1 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
104 | Stucco | 10183 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 008 - SG1 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
105 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-1 | 70001 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 009 - SG1 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
106 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - SG-1 | 31714 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 009 - SG1 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
107 | WINDOW FLOODGATES (8.06 AND 8.14) - SG-1 | 68909 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 009 - SG1 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
108 | Temporary Egress Stair Storage Sign | 2640 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 009 - SG1 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
109 | Address Signs | 4950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 009 - SG1 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
110 | Switches and Receptacles | 10950 | 1095 |  |  | 1095 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 10% | Five Star | Kurston | FALSE | FALSE | TRUE
111 | Switchgear & Panelboard Energization | 19163 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
112 | Switchgear & Panelboard Installation | 229950 | 114975 |  |  | 114975 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 50% | Five Star | Kurston | FALSE | FALSE | TRUE
113 | Switchgear & Panelboard Terminations | 19163 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
114 | Switchgear & Panelboard Testing | 19163 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
115 | Temp Light & Power | 54750 | 41062.5 |  |  | 41062.5 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 75% | Five Star | Kurston | FALSE | FALSE | TRUE
116 | Fire Alarm Conduit | 68438 | 47906.6 |  |  | 47906.6 | 02- RESAND: Surfside Gardens | G- SG6 | 081 - SG6 - Division 28 |  | 70% | Five Star | Kurston | FALSE | FALSE | TRUE
117 | Fire Alarm Wiring | 65700 | 16425 |  |  | 16425 | 02- RESAND: Surfside Gardens | G- SG6 | 081 - SG6 - Division 28 |  | 25% | Five Star | Kurston | FALSE | FALSE | TRUE
118 | Fire Alarm Devices | 93075 | 13961.25 |  |  | 13961.25 | 02- RESAND: Surfside Gardens | G- SG6 | 081 - SG6 - Division 28 |  | 15% | Five Star | Kurston | FALSE | FALSE | TRUE
119 | Fire Alarm Programming & Pretest | 2738 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 081 - SG6 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
120 | Clean and refurbish landing device components in the pit | 4000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
121 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 081 - SG6 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
122 | EXCAVATION NEW BLDGS - SG-6 | 38439 | 38439 |  |  | 38439 | 02- RESAND: Surfside Gardens | G- SG6 | 082 - SG6 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
123 | BACKFILL NEW BLDGS - SG-6 | 18099 | 18099 |  |  | 18099 | 02- RESAND: Surfside Gardens | G- SG6 | 082 - SG6 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
124 | DEWATERING COVERAGE FOR NEW BUILDINGS - SG-6 | 42088 | 42088 |  |  | 42088 | 02- RESAND: Surfside Gardens | G- SG6 | 082 - SG6 - Division 31 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
125 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - SG-6 | 27148 | 27148 |  |  | 27148 | 02- RESAND: Surfside Gardens | G- SG6 | 082 - SG6 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
126 | DRIVE PILES AND INSTALL LAGGING FOR SOE - SG-6 | 34172 | 34172 |  |  | 34172 | 02- RESAND: Surfside Gardens | G- SG6 | 082 - SG6 - Division 31 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
127 | FORMWORK NEW BUILDING - SG-7 | 353185 | 353185 |  |  | 353185 | 02- RESAND: Surfside Gardens | H- SG7 | 083 - SG7 - Division 3 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
128 | SET ANCHOR BOLTS FOR STEEL COLUMNS - SG-7 | 5411 | 5411 |  |  | 5411 | 02- RESAND: Surfside Gardens | H- SG7 | 083 - SG7 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
129 | POUR CONCRETE NEW BUILDINGS - SG-7 | 220248 | 209235.6 |  |  | 209235.6 | 02- RESAND: Surfside Gardens | H- SG7 | 083 - SG7 - Division 3 |  | 95% | MLJ | Ricky | FALSE | FALSE | TRUE
130 | FINISH SLABS - SG-7 | 17896 | 4474 |  |  | 4474 | 02- RESAND: Surfside Gardens | H- SG7 | 083 - SG7 - Division 3 | plumbing shaft slab | 25% | MLJ | Ricky | FALSE | FALSE | TRUE
131 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
132 | Footing/Pier | 174820 | 174820 |  |  | 174820 | 02- RESAND: Surfside Gardens | H- SG7 | 083 - SG7 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
133 | Floor Slabs | 31988 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 083 - SG7 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
134 | Cellar Pit First Floor Slab | 490 | 490 |  |  | 490 | 02- RESAND: Surfside Gardens | H- SG7 | 083 - SG7 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
135 | Cellar Pit Second Floor Slab | 544 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 083 - SG7 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
136 | Meter Room Second Floor Slab | 762 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 083 - SG7 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
137 | Cellar Pit | 47722 | 47721.4 |  |  | 47721.4 | 02- RESAND: Surfside Gardens | H- SG7 | 083 - SG7 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
138 | Gas Meter Room | 12726 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 083 - SG7 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
139 | WWM-Slabs | 6648 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 083 - SG7 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
140 | 8" CMU (3 hour rated) | 171133 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 084 - SG7 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
141 | 4" CMU | 39402 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 084 - SG7 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
142 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
143 | 6" CMU (2 hour rated) | 38214 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 084 - SG7 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
144 | Face Brick 3-5/8" | 235521 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 084 - SG7 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
145 | 3-1/8" Rigid insulation | 30712 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 084 - SG7 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
146 | Cast Stone with SS letters | 8521 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 084 - SG7 - Division 4 |  | 0% | S & D | Stefon | FALSE | FALSE | TRUE
147 | Steel Channel | 16720 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
148 | Cont. Shelf angle | 9240 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
149 | STEEL (MATERIAL ONLY) | 178532 | 117831.12 |  |  | 117831.12 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 66% | Weir Welding | Ricky | FALSE | FALSE | TRUE
150 | FABRICATION COSTS | 303034 | 200002.44 |  |  | 200002.44 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 66% | Weir Welding | Ricky | FALSE | FALSE | TRUE
151 | METAL DECK (BUY-OUT) | 15270 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
152 | ANCHORS & EMBEDS | 9398 | 6202.68 |  |  | 6202.68 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 66% | Weir Welding | Ricky | FALSE | FALSE | TRUE
153 | Replace oil buffers | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
154 | SURVEYING | 14096 | 14096 |  |  | 14096 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 | Steel Shop drawings | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
155 | STEEL & DECK ERECTION | 610764 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
156 | BOLTS AND HARDWARE | 23492 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
157 | TRUCKING | 11746 | 7752.36 |  |  | 7752.36 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 66% | Weir Welding | Ricky | FALSE | FALSE | TRUE
158 | Dunnage Grating Galvanized | 64556 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
159 | Dunnage Guard Rail | 30415 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
160 | Dunnage Stair and Guard Rail | 13035 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
161 | Stair B: First Floor to Roof with Landing and Hand & Guard Rail | 128548 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
162 | 1st to 2nd Floor Ship Ladder with Cages | 25750 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
163 | Bulkhead Ship Ladder to Roof at 2 Locations | 12383 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 085 - SG7 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
164 | Replace compensation guidance system per dwgs | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
165 | Layout | 8028 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 086 - SG7 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
166 | Loading | 15326 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 086 - SG7 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
167 | Exterior Framing, Insulation & Drywall - Materials | 67511 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 086 - SG7 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
168 | Exterior Framing- Labor | 58049 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 086 - SG7 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
169 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - SG-7 | 7236 | 7236 |  |  | 7236 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
170 | PENETRATION FIRESTOPPING NEW BLDG - SG-7 | 11505 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
171 | JOINT SEALANTS NEW BLDGS - S7 | 11505 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
172 | Air Film | 19195 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
173 | Insulation- Labor | 7798 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
174 | Crystalline Waterproofing at plumbing shaft | 4474 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
175 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
176 | Waterproofing at foundation | 8522 | 5113.2 |  |  | 5113.2 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 | waterproof concrete additive has been used in shaft | 60% | DStar | Ricky | FALSE | FALSE | TRUE
177 | Layout | 87373 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
178 | Framing | 198097 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
179 | Insulation | 35480 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
180 | Cladding Install | 248360 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
181 | Fireproofing | 41800 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | SIG | Ricky | FALSE | FALSE | TRUE
182 | P&I Cold Applied Roof Membrane | 99622 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
183 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 101829 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
184 | P&I Aluminum Coping | 7458 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 087 - SG7 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
185 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S7 | 10270 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 088 - SG7 - Division 8 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
186 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
187 | Doors, Frames & Hardware - Labor | 18070 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 088 - SG7 - Division 8 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
188 | Louvers Install | 61948 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 088 - SG7 - Division 8 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
189 | Furnish Doors | 18815 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 089 - SG7 - Division 9 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
190 | Sheathing & Drywall - Labor | 49634 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 089 - SG7 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
191 | Tape/ Spackle finishes | 14144 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 089 - SG7 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
192 | ACT ceilings - Materials | 3858 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 089 - SG7 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
193 | ACT ceilings - Labor | 12788 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 089 - SG7 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
194 | Direct Applied Stucco | 53251 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 089 - SG7 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
195 | Painting SG-7 | 110000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 089 - SG7 - Division 9 |  | 0% | GG Paint | Stefon | FALSE | FALSE | TRUE
196 | Cermic Tile and Base - SG-7 | 5490 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 089 - SG7 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | FALSE | TRUE
197 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
198 | FIRE EXTINGUISHERS NEW BLDGS - SG-7 | 733 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 090 - SG7 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
199 | TOILET ACCESSORIES NEW BLDGS - SG-7 | 2830 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 090 - SG7 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
200 | Stair Identification Sign | 1650 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 090 - SG7 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
201 | Stairway Floor number and ID Sign | 1650 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 090 - SG7 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
202 | Room Sign | 2200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 090 - SG7 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
203 | Exit Sign | 550 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 090 - SG7 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
204 | Public Unisex Toilet Sign | 550 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 090 - SG7 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
205 | Stairway Flood Access Door | 550 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 090 - SG7 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
206 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 517.6 |  |  | 517.6 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 10% | Vital | Kurston | FALSE | FALSE | TRUE
207 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 264 |  |  | 264 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 5% | Vital | Kurston | FALSE | FALSE | TRUE
208 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
209 | ESCUTCHEONS FOR PLUMBING PIPING | 2178 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
210 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 22000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
211 | HANGERS AND SUPPORTS | 21648 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
212 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2728 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
213 | DOMESTIC WATER PIPING | 255409 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
214 | DOMESTIC WATER PIPING SPECIALTIES | 30184 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
215 | DOMESTIC WATER PUMPING SYSTEMS | 82500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
216 | SANITARY WASTE PIPING | 104439 | 26109.75 |  |  | 26109.75 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 25% | Vital | Kurston | FALSE | FALSE | TRUE
217 | SANITARY WASTE PIPING SPECIALTIES | 20504 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
218 | STORM DRAINAGE PIPING SPECIALTIES | 53504 | 13376 |  |  | 13376 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 25% | Vital | Kurston | FALSE | FALSE | TRUE
219 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
220 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 21824 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
221 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 322085 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
222 | GAS SERVICE AND PIPING | 271645 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
223 | PLUMBING FIXTURES | 18392 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
224 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 78682 | 70813.8 |  |  | 70813.8 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
225 | Plumbing Pipe Insulation | 2374 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
226 | Heat Trace | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 091 - SG7 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
227 | Survey | 66000 | 66000 |  |  | 66000 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 | Sheet metal shop drawings submitted (submittal no 2322), mechanical still required | 100% | Welkin | Sully | FALSE | FALSE | TRUE
228 | Exhaust Fans: Furnish | 6600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
229 | Exhaust Fans: Install | 18700 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
230 | Wire brush sills and support (at the first floor only) | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
231 | Electric Unit Heaters: Furnish | 4950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
232 | Steam Unit Heaters: Furnish | 3300 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
233 | Steam Unit Heaters: Install | 32175 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
234 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
235 | Heating and Ventilation Unit: Install | 26675 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
236 | Condensate Return Unit: Furnish | 7700 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
237 | Condensate Return Unit: Install | 25575 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
238 | Steam Traps: Furnish | 1540 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
239 | Steam Traps: Install | 14300 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
240 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 157465 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
241 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
242 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 271700 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
243 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 88000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
244 | Mechanical Pipe: Hydrostatic Testing | 2035 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
245 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 19250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
246 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 38500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
247 | HVAC Ductwork: Testing & Balancing | 2200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
248 | Controls: Furnish and Install: Devices | 110000 | 11000 |  |  | 11000 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 10% | Welkin | Sully | FALSE | FALSE | TRUE
249 | Controls: Furnish and Install: Controls Conduit | 49500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
250 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
251 | Controls: Connect to Final Termination Points | 11000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
252 | Replace pit lights and outlets | 3000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
253 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
254 | Insulation: Furnish and Install: Ductwork Insulation | 18150 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
255 | Insulation: Furnish and Install: Piping Insulation | 30250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
256 | Insulation: Furnish and Install: Equipment Insulation | 18150 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 092 - SG7 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
257 | ATS Energization | 24638 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
258 | ATS Installation | 344925 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
259 | ATS Terminations | 24638 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
260 | ATS Testing | 24638 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
261 | Cabling - Interior Branch (1/0 & Smaller) | 100000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
262 | Cabling - Risers & Feeders (2/0 & Larger) | 591300 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
263 | Replace all pit stop switches and light switches | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
264 | Conduit - Branch Circuits (1 1/2" & Smaller) | 123188 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
265 | Conduit - In-Slab | 162608 | 1626.08 |  |  | 1626.08 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 1% | Five Star | Kurston | FALSE | FALSE | TRUE
266 | Conduit - Risers (2" & Larger) | 591300 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
267 | Firestopping | 5250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
268 | Foundation Coring | 10500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
269 | Generator Delivery | 78750 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
270 | Generator Release | 472500 | 472500 |  |  | 472500 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
271 | Generator Terminations | 78750 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
272 | Generator Test | 78750 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
273 | Lighting Controls | 11550 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
274 | Repair/replace pit access doors and hardware | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
275 | Lighting Install | 82125 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
276 | Lighting Rough | 82125 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
277 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
278 | Lightning Protection | 21900 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
279 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
280 | Survey | 54750 | 54750 |  |  | 54750 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
281 | Switches and Receptacles | 10950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
282 | Switchgear & Panelboard Energization | 49275 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
283 | Switchgear & Panelboard Installation | 591300 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
284 | Switchgear & Panelboard Terminations | 49275 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
285 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
286 | Switchgear & Panelboard Testing | 49275 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
287 | Temp Light & Power | 54750 | 13687.5 |  |  | 13687.5 | 02- RESAND: Surfside Gardens | H- SG7 | 093 - SG7 - Division 26 |  | 25% | Five Star | Kurston | FALSE | FALSE | TRUE
288 | Fire Alarm Conduit | 32850 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 094 - SG7 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
289 | Fire Alarm Wiring | 32850 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 094 - SG7 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
290 | Fire Alarm Devices | 53655 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 094 - SG7 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
291 | Fire Alarm Programming & Pretest | 2738 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 094 - SG7 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
292 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 094 - SG7 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
293 | EXCAVATION NEW BLDGS - SG-7 | 42812 | 42812 |  |  | 42812 | 02- RESAND: Surfside Gardens | H- SG7 | 095 - SG7 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
294 | BACKFILL NEW BLDGS - SG-7 | 18057 | 16057 |  |  | 16057 | 02- RESAND: Surfside Gardens | H- SG7 | 095 - SG7 - Division 31 |  | 88.92% | MLJ | Ricky | FALSE | FALSE | TRUE
295 | DEWATERING COVERAGE FOR NEW BUILDINGS - SG-7 | 42088 | 42088 |  |  | 42088 | 02- RESAND: Surfside Gardens | H- SG7 | 095 - SG7 - Division 31 | Building out of water table, no more dewatering requried | 100% | MLJ | Brian | FALSE | FALSE | TRUE
296 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
297 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - SG-7 | 27148 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | H- SG7 | 095 - SG7 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
298 | DRIVE PILES AND INSTALL LAGGING FOR SOE - SG-7 | 34172 | 34172 |  |  | 34172 | 02- RESAND: Surfside Gardens | H- SG7 | 095 - SG7 - Division 31 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
299 | EROSION CONTROL FABRIC - SGN | 71660 | 69660 | 2000 |  | 71660 | 02- RESAND: Surfside Gardens | I- SGN | 096 - SGN - Division 2 | All areas now fenced and set up | 100% | MLJ | Brian | FALSE | TRUE | FALSE
300 | INLET PROTECTION - SGN | 31100 | 29100 | 2000 |  | 31100 | 02- RESAND: Surfside Gardens | I- SGN | 096 - SGN - Division 2 | All areas now fenced and set up | 100% | MLJ | Brian | FALSE | TRUE | FALSE
301 | SILT FENCE - SGN | 22950 | 20950 | 2000 |  | 22950 | 02- RESAND: Surfside Gardens | I- SGN | 096 - SGN - Division 2 | All areas now fenced and set up | 100% | MLJ | Brian | FALSE | TRUE | FALSE
302 | STABILIZED CONSTRUCTION ENTRANCE - SGN | 48300 | 48300 | 0 |  | 48300 | 02- RESAND: Surfside Gardens | I- SGN | 096 - SGN - Division 2 | All areas now fenced and set up | 100% | MLJ | Brian | FALSE | FALSE | TRUE
303 | MANTAIN EROSION CONTROL - SGN | 42735 | 40735 | 2000 |  | 42735 | 02- RESAND: Surfside Gardens | I- SGN | 096 - SGN - Division 2 | All areas now fenced and set up | 100% | MLJ | Brian | FALSE | TRUE | FALSE
304 | REMOVE EROSION CONTROL - SGN | 29979 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 096 - SGN - Division 2 |  | 0% | MLJ | Brian | FALSE | FALSE | TRUE
305 | REMOVE FENCE - SGN | 23500 | 23500 | 0 |  | 23500 | 02- RESAND: Surfside Gardens | I- SGN | 096 - SGN - Division 2 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
306 | REMOVE FULL DEPTH ASPHALT PVMT - SGN | 18750 | 18750 | 0 |  | 18750 | 02- RESAND: Surfside Gardens | I- SGN | 096 - SGN - Division 2 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
307 | Clean and paint buffer inspection ladders | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
308 | REMOVE SITE FURNISHING - SGN | 181360 | 181360 | 0 |  | 181360 | 02- RESAND: Surfside Gardens | I- SGN | 096 - SGN - Division 2 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
309 | REMOVE CONCRETE CURB & STEPS - SGN | 40100 | 36090 |  |  | 36090 | 02- RESAND: Surfside Gardens | I- SGN | 096 - SGN - Division 2 |  | 90% | MLJ | Brian | FALSE | FALSE | TRUE
310 | REMOVE PVMTS - SGN | 151850 | 151850 | 0 |  | 151850 | 02- RESAND: Surfside Gardens | I- SGN | 096 - SGN - Division 2 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
311 | FORMWORK SITE CONCRETE - SGN | 55661 | 18368.13 |  |  | 18368.13 | 02- RESAND: Surfside Gardens | I- SGN | 097 - SGN - Division 3 | 33% is for concrete ductbanks, 33% for retaining walls, 33% for site furnishings | 33% | MLJ | Brian | FALSE | FALSE | TRUE
312 | CONCRETE FOOTING FOR SITE FURNISHING - SGN | 5947 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 097 - SGN - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
313 | CONCRETE DUCTBANKS - SGN | 40284 | 40284 |  |  | 40284 | 02- RESAND: Surfside Gardens | I- SGN | 097 - SGN - Division 3 |  | 100% | MLJ | Sully | FALSE | FALSE | TRUE
314 | CONCRETE SITE RETAINING WALL AND FOOTINGS - SGN | 25224 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 097 - SGN - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
315 | EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - SGN | 24647 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 098 - SGN - Division 11 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
316 | Crackle Corn | 22000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 098 - SGN - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
317 | Jet Spray | 44000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 098 - SGN - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
318 | Clean out pit of all dirt and debris | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
319 | 2-5 year play equipment | 88000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 098 - SGN - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
320 | 5-12 year play equipment | 88000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 098 - SGN - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
321 | Splash Pad | 22000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 098 - SGN - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
322 | Install Water Play Equipment and Piping | 55000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 098 - SGN - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
323 | Manhole Installation | 54750 | 54750 |  |  | 54750 | 02- RESAND: Surfside Gardens | I- SGN | 099 - SGN - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
324 | Site Lighting - Cable | 54750 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 099 - SGN - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
325 | Site Lighting - Conduit | 65700 | 6570 |  |  | 6570 | 02- RESAND: Surfside Gardens | I- SGN | 099 - SGN - Division 26 |  | 10% | Five Star | Kurston | FALSE | FALSE | TRUE
326 | Site Lighting - Fixtures | 55407 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 099 - SGN - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
327 | Survey | 54750 | 54750 |  |  | 54750 | 02- RESAND: Surfside Gardens | I- SGN | 099 - SGN - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
328 | Underground Electric Service - Cable | 821250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 099 - SGN - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
329 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 010 - SG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
330 | Underground Electric Service - Conduit | 657000 | 657000 |  |  | 657000 | 02- RESAND: Surfside Gardens | I- SGN | 099 - SGN - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
331 | TREE PROTECTION - SGN | 14532 | 13532 |  |  | 13532 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 |  | 93.12% | MLJ | Sully | FALSE | FALSE | TRUE
332 | HAND EXCAVATION AS NEEDED - SGN | 19751 | 19751 |  |  | 19751 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 |  | 100% | MLJ | Sully | FALSE | FALSE | TRUE
333 | EXCAVATION FOR SITE FURNISHING FOOTINGS - SGN | 4025 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
334 | BACKFILL - SGN | 153869 | 61547.6 |  |  | 61547.6 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 | Backfill of Electrical completed, some backfill of water & steam. No backfill of sewer. Assume electrical 33%, steam and water 33% and sewer 33% | 40% | MLJ | Sully | FALSE | FALSE | TRUE
335 | SITE FURNISHINGS - SGN | 37275 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
336 | DRINKING FOUNTAIN - SGN | 16059 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
337 | LANDSCAPE BOULDERS - SGN | 22319 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
338 | Dewatering Permits | 15178 | 15178 | 0 |  | 15178 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 | No more dewatering required | 100% | MLJ | Brian | FALSE | FALSE | TRUE
339 | Furnish and Install Deep Wells | 146250 | 146250 | 0 |  | 146250 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 | No more dewatering required | 100% | MLJ | Brian | FALSE | FALSE | TRUE
340 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 8165.4 |  |  | 8165.4 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 60% | Vital | Kurston | FALSE | FALSE | TRUE
341 | Furnish and Install Pumps and Piping | 160800 | 158800 | 2000 |  | 160800 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 | No more dewatering required | 100% | MLJ | Brian | FALSE | TRUE | FALSE
342 | Power for Dewatering | 109091 | 107091 | 2000 |  | 109091 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 | No more dewatering required | 100% | MLJ | Brian | FALSE | TRUE | FALSE
343 | Installation Support | 120000 | 118000 | 2000 |  | 120000 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 | No more dewatering required | 100% | MLJ | Brian | FALSE | TRUE | FALSE
344 | Dewatering expenses | 218182 | 216182 | 2000 |  | 218182 | 02- RESAND: Surfside Gardens | I- SGN | 100 - SGN - Division 31 | No more dewatering required | 100% | MLJ | Brian | FALSE | TRUE | FALSE
345 | 4' Steel Bar Fence with Double Gates | 88000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | Atlas | Ricky | FALSE | FALSE | TRUE
346 | 6' Chain Link Fence | 12650 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | Atlas | Ricky | FALSE | FALSE | TRUE
347 | 8' High Temporary Fence | 242250 | 242250 |  |  | 242250 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 100% | Atlas | Ricky | FALSE | FALSE | TRUE
348 | 4" CONCRETE | 100100 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
349 | 7" CONCRETE RAMP | 3080 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
350 | 5" POROUS CONCRETE | 462000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
351 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1100 | 1100 |  |  | 1100 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 100% | Vital | Kurston | FALSE | FALSE | TRUE
352 | 5" COLOR CONCRETE | 77000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
353 | CONCRETE CURB | 18480 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
354 | SFC -STELL FACING CURB | 18480 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
355 | Asphalt Parking | 1161 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | Citywide Paving | Sully | FALSE | FALSE | TRUE
356 | Deciduous Trees | 14884 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
357 | Evergreen Trees | 3544 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
358 | Deciduous Shrubs | 2940 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
359 | Evergreen Shrubs | 1040 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
360 | Perennials | 8080 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
361 | Grasses | 18295 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
362 | ESCUTCHEONS FOR PLUMBING PIPING | 1096 | 548 |  |  | 548 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
363 | Tree Removal | 41580 | 41580 |  |  | 41580 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 100% | Aspen | Adam | FALSE | FALSE | TRUE
364 | Lawn Seeding (not including topsoil) | 14810 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
365 | Soil Erosion Mat | 2791 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
366 | Topsoil Stockpile/Spread | 101317 | 65856.05 |  |  | 65856.05 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 65% | Aspen | Adam | FALSE | FALSE | TRUE
367 | Maintenance | 2678 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | I- SGN | 101 - SGN - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
368 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - SGN | 16286 | 16286 | 0 |  | 16286 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 | Excavation now complete so not more protection required | 100% | MLJ | Brian | FALSE | FALSE | TRUE
369 | TERMINATE AND DEMOLISH EXISTING UTILITIES - SGN | 25018 | 20014.4 | 1250.9 |  | 21265.3 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 |  | 85% | MLJ | Brian | FALSE | TRUE | FALSE
370 | INSTALL HW, CW PIPE - SGN | 403279 | 403279 |  |  | 403279 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 | Install and test complete, backfill still required | 100% | Welkin | Sully | FALSE | FALSE | TRUE
371 | TEST HW, CW - SGN | 17587 | 17587 |  |  | 17587 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 | Install and test complete, backfill still required | 100% | MLJ | Sully | FALSE | FALSE | TRUE
372 | INSTALL CONDENSATE AND STEAM PIPE - SGN | 308238 | 92471.4 |  |  | 92471.4 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 |  | 30% | Welkin | Sully | FALSE | FALSE | TRUE
373 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3300 | 2475 |  |  | 2475 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
374 | TEST CONDENSATE, STEAM - SGN | 12947 | 12947 |  |  | 12947 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 | Steam from SG6-SG4 tested | 100% | MLJ | Sully | FALSE | FALSE | TRUE
375 | DEWATERING COVERAGE FOR UTILITY WORK - SGN | 56118 | 54118 | 2000 |  | 56118 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 | No more dewatering required | 100% | MLJ | Brian | FALSE | TRUE | FALSE
376 | SEWER / DRAINAGE PIPE - SGN | 150607 | 15060.7 |  |  | 15060.7 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 | Piping material has arrived on site | 10% | MLJ | Sully | FALSE | FALSE | TRUE
377 | CATCH BASIN DRAINS AND CONNECTIONS - SGN | 165979 | 82989.5 |  |  | 82989.5 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 | Manholes stored on site | 50% | MLJ | Sully | FALSE | FALSE | TRUE
378 | REMOVE AREA DRAINS - SGN | 23320 | 10494 |  |  | 10494 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 |  | 45% | MLJ | Sully | FALSE | FALSE | TRUE
379 | ELECTRICAL MANHOLES - SGN | 6377 | 6377 |  |  | 6377 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
380 | ELECTRICAL CONDUIT TRENCHES - SGN | 45340 | 45340 |  |  | 45340 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 | SG6 to SG4 run is complete. SG6 to SG5 run complete; building to manhole trenching started but not complete | 100% | MLJ | Sully | FALSE | FALSE | TRUE
381 | Equipment SUPPORT FOR SITE - SGN | 167754 | 167754 | 0 |  | 167754 | 02- RESAND: Surfside Gardens | I- SGN | 102 - SGN - Division 33 | Ongoing work on site using equipment. Bill 5% per month | 100% | MLJ | Brian | FALSE | FALSE | TRUE
382 | EROSION CONTROL FABRIC - SGS | 71650 | 46572.5 | 3582.5 |  | 50155 | 02- RESAND: Surfside Gardens | J- SGS | 103 - SGS - Division 2 | fencing set up around SG7 and other areas in SGS | 70% | MLJ | Brian | FALSE | TRUE | FALSE
383 | INLET PROTECTION - SGS | 23325 | 15161.25 | 1166.25 |  | 16327.5 | 02- RESAND: Surfside Gardens | J- SGS | 103 - SGS - Division 2 | fencing set up around SG7 and other areas in SGS | 70% | MLJ | Brian | FALSE | TRUE | FALSE
384 | HANGERS AND SUPPORTS | 11526 | 9220.8 |  |  | 9220.8 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 80% | Vital | Kurston | FALSE | FALSE | TRUE
385 | SILT FENCE - SGS | 29100 | 18915 | 1455 |  | 20370 | 02- RESAND: Surfside Gardens | J- SGS | 103 - SGS - Division 2 | fencing set up around SG7 and other areas in SGS | 70% | MLJ | Brian | FALSE | TRUE | FALSE
386 | STABILIZED CONSTRUCTION ENTRANCE - SGS | 48390 | 48390 |  |  | 48390 | 02- RESAND: Surfside Gardens | J- SGS | 103 - SGS - Division 2 | Constrcution entrances set up | 100% | MLJ | Brian | FALSE | FALSE | TRUE
387 | MANTAIN EROSION CONTROL - SGS | 42735 | 34188 | 2136.75 |  | 36324.75 | 02- RESAND: Surfside Gardens | J- SGS | 103 - SGS - Division 2 |  | 85% | MLJ | Brian | FALSE | TRUE | FALSE
388 | REMOVE EROSION CONTROL - SGS | 29979 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 103 - SGS - Division 2 |  | 0% | MLJ | Brian | FALSE | FALSE | TRUE
389 | REMOVE FENCE - SGS | 24400 | 24400 |  |  | 24400 | 02- RESAND: Surfside Gardens | J- SGS | 103 - SGS - Division 2 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
390 | REMOVE FULL DEPTH ASPHALT PVMT - SGS | 68825 | 58825 |  |  | 58825 | 02- RESAND: Surfside Gardens | J- SGS | 103 - SGS - Division 2 |  | 85.47% | MLJ | Brian | FALSE | FALSE | TRUE
391 | REMOVE SITE FURNISHING - SGS | 64615 | 54615 |  |  | 54615 | 02- RESAND: Surfside Gardens | J- SGS | 103 - SGS - Division 2 |  | 84.52% | MLJ | Brian | FALSE | FALSE | TRUE
392 | REMOVE CONCRETE CURB & STEPS - SGS | 60250 | 53250 |  |  | 53250 | 02- RESAND: Surfside Gardens | J- SGS | 103 - SGS - Division 2 |  | 88.38% | MLJ | Brian | FALSE | FALSE | TRUE
393 | REMOVE PVMTS - SGS | 100625 | 85468.75 | 10125 |  | 95593.75 | 02- RESAND: Surfside Gardens | J- SGS | 103 - SGS - Division 2 |  | 95% | MLJ | Brian | FALSE | TRUE | FALSE
394 | FORMWORK SITE CONCRETE - SGS | 55661 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 104 - SGS - Division 3 |  | 0% | MLJ | Brian | FALSE | FALSE | TRUE
395 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
396 | CONCRETE FOOTING FOR SITE FURNISHING - SGS | 5947 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 104 - SGS - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
397 | CONCRETE DUCTBANKS - SGS | 59916 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 104 - SGS - Division 3 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
398 | Manhole Work | 54750 | 10950 |  |  | 10950 | 02- RESAND: Surfside Gardens | J- SGS | 105 - SGS - Division 26 |  | 20% | Five Star | Kurston | FALSE | FALSE | TRUE
399 | Site Lighting - Cable | 49275 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 105 - SGS - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
400 | Site Lighting - Conduit | 65700 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 105 - SGS - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
401 | Site Lighting - Fixtures | 62963 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 105 - SGS - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
402 | Survey | 70080 | 70080 |  |  | 70080 | 02- RESAND: Surfside Gardens | J- SGS | 105 - SGS - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
403 | Underground Electric Service - Cable | 821250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 105 - SGS - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
404 | Underground Electric Service - Conduit | 657000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 105 - SGS - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
405 | TREE PROTECTION - SGS | 5882 | 4705.6 |  |  | 4705.6 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 |  | 80% | MLJ | Sully | FALSE | FALSE | TRUE
406 | DOMESTIC WATER PIPING | 126720 | 95040 |  |  | 95040 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
407 | HAND EXCAVATION AS NEEDED - SGS | 21068 | 21068 |  |  | 21068 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 | Test pitting complete, used around existing gas, steam and electrical line and against buidling for POE's | 100% | MLJ | Sully | FALSE | FALSE | TRUE
408 | EXCAVATION FOR SITE FURNISHING FOOTINGS - SGS | 4025 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
409 | BACKFILL - SGS | 195501 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
410 | SITE FURNISHINGS - SGS | 74550 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
411 | BOLLARDS - SGS | 15581 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
412 | DRINKING FOUNTAIN - SGS | 8030 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
413 | Dewatering Permits | 15178 | 11383.5 |  |  | 11383.5 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 |  | 75% | MLJ | Brian | FALSE | FALSE | TRUE
414 | Furnish and Install Deep Wells | 135000 | 108000 | 6750 |  | 114750 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 | 50% for building, 50% for utilities. Building complete, utilities 50% | 85% | MLJ | Brian | FALSE | TRUE | FALSE
415 | Furnish and Install Pumps and Piping | 7800 | 6240 | 390 |  | 6630 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 | 50% for building, 50% for utilities. Building complete, utilities 50% | 85% | MLJ | Brian | FALSE | TRUE | FALSE
416 | Power for Dewatering | 109091 | 87272.8 | 5454.55 |  | 92727.35 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 | 50% for building, 50% for utilities. Building complete, utilities 50% | 85% | MLJ | Brian | FALSE | TRUE | FALSE
417 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 12210 |  |  | 12210 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
418 | Installation Support | 120000 | 96000 | 6000 |  | 102000 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 | 50% for building, 50% for utilities. Building complete, utilities 50% | 85% | MLJ | Brian | FALSE | TRUE | FALSE
419 | Dewatering expenses | 218182 | 174545.6 | 10909.1 |  | 185454.7 | 02- RESAND: Surfside Gardens | J- SGS | 106 - SGS - Division 31 | 50% for building, 50% for utilities. Building complete, utilities 50% | 85% | MLJ | Brian | FALSE | TRUE | FALSE
420 | 8' High Temporary Fence | 372400 | 336200 |  |  | 336200 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 90.28% | Atlas | Ricky | FALSE | FALSE | TRUE
421 | Ametco Fence | 138050 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | Atlas | Ricky | FALSE | FALSE | TRUE
422 | 4" CONCRETE | 71500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
423 | 5"POROUS CONCRETE | 466620 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
424 | 5" COLOR CONCRETE | 154000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
425 | CONCRETE CURB | 38500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
426 | SFC -STELL FACING CURB | 13200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
427 | Deciduous Trees | 27642 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
428 | SANITARY WASTE PIPING | 118800 | 95040 |  |  | 95040 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 80% | Vital | Kurston | FALSE | FALSE | TRUE
429 | Evergreen Trees | 2127 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
430 | Deciduous Shrubs | 1470 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
431 | Perennials | 4429 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
432 | Grasses | 7980 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
433 | Tree Removal | 48246 | 44246 |  |  | 44246 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 91.71% | Aspen | Adam | FALSE | FALSE | TRUE
434 | Lawn Seeding (not including topsoil) | 14012 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
435 | Topsoil Stockpile/Spread | 96170 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
436 | Maintenance | 2678 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 107 - SGS - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
437 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - SGS | 16286 | 13028.8 | 814.3 |  | 13843.1 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 | hand digging around existing services completed this period | 85% | MLJ | Brian | FALSE | TRUE | FALSE
438 | TERMINATE AND DEMOLISH EXISTING UTILITIES - SGS | 25860 | 12930 | 1293 |  | 14223 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 | Protect utility work by SGS | 55% | MLJ | Brian | FALSE | TRUE | FALSE
439 | SANITARY WASTE PIPING SPECIALTIES | 30070 | 27063 |  |  | 27063 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
440 | INSTALL HW, CW PIPE - SGS | 504915 | 378686.25 |  |  | 378686.25 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 | Sg3 to SG7 & SG7 to SG1 complete. SG7 to SG2 remains | 75% | Welkin | Sully | FALSE | FALSE | TRUE
441 | TEST HW, CW - SGS | 21983 | 16487.25 |  |  | 16487.25 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 | Sg3 to SG7 & SG7 to SG1 tested. SG7 to SG2 remains | 75% | MLJ | Sully | FALSE | FALSE | TRUE
442 | INSTALL CONDENSATE AND STEAM PIPE - SGS | 516372 | 247858.56 |  |  | 247858.56 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 |  | 48% | Welkin | Sully | FALSE | FALSE | TRUE
443 | TEST CONDENSATE, STEAM - SGS | 19421 | 8545.24 |  |  | 8545.24 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 |  | 44% | MLJ | Sully | FALSE | FALSE | TRUE
444 | DEWATERING COVERAGE FOR UTILITY WORK - SGS | 5612 | 2806 | 280.6 |  | 3086.6 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 | trench near SG3 completed this period | 55% | MLJ | Brian | FALSE | TRUE | FALSE
445 | SEWER / DRAINAGE PIPE - SGS | 132508 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
446 | CATCH BASIN DRAINS AND CONNECTIONS - SGS | 78622 | 39311 |  |  | 39311 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 | Manholes stored on site | 50% | MLJ | Sully | FALSE | FALSE | TRUE
447 | REMOVE AREA DRAINS - SGS | 23320 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
448 | ELECTRICAL MANHOLES - SGS | 31811 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
449 | ELECTRICAL CONDUIT TRENCHES - SGS | 61478 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
450 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 9900 |  |  | 9900 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 30% | Vital | Kurston | FALSE | FALSE | TRUE
451 | Equipment SUPPORT FOR SITE - SGS | 167754 | 109040.1 | 8387.7 |  | 117427.8 | 02- RESAND: Surfside Gardens | J- SGS | 108 - SGS - Division 33 | Ongoing work on site using equipment. Bill 5% per month | 70% | MLJ | Brian | FALSE | TRUE | FALSE
452 | Gaskets | 45000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
453 | Wire Insulation | 37500 | 37500 |  |  | 37500 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
454 | Assumed Flooring Material (Slab Penetrations) | 61200 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
455 | Pipe Insulation | 151200 | 151200 |  |  | 151200 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
456 | Tank Insulation | 9750 | 9750 |  |  | 9750 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
457 | Fireproofing | 171120 | 171120 |  |  | 171120 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
458 | Fibrous Slate | 9180 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
459 | Waterproofing | 4971 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
460 | Underground Utility Materials | 11544 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
461 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 253000 | 37950 |  |  | 37950 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 15% | Vital | Kurston | FALSE | FALSE | TRUE
462 | Remove existing paint and plaster - cellar | 60000 | 60000 |  |  | 60000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
463 | Remove existing vent / window and frame | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 | cellar windows | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
464 | Remove existing door, frame and hardware | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
465 | Remove Areaway slab and drain | 60000 | 12000 |  |  | 12000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 20% | MLJ | Ricky | FALSE | FALSE | TRUE
466 | Remove Areaway grate | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
467 | Sawcut and remove portion of areaway wall | 60000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
468 | Prepare existing wall surface for paint - 1st floor | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
469 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
470 | Remove existing AC units and sleeves - 1st floor | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
471 | Remove window sill - 1st floor | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
472 | GAS SERVICE AND PIPING | 2112 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
473 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
474 | Remove floor finish - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
475 | Remove stove - 2nd floor | 4000 | 4000 |  |  | 4000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
476 | Remove CMU wall - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
477 | Remove sinks - 2nd floor | 4000 | 4000 |  |  | 4000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
478 | Remove interior walls - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
479 | Patch floor and make smooth - 2nd floor | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
480 | Cut openings in slab - 2nd floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 0% | MLJ | RIcky | FALSE | FALSE | TRUE
481 | Remove existing windows - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
482 | Remove appliances - 2nd floor | 6000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
483 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 |  |  | 5357 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 100% | Vital | Kurston | FALSE | FALSE | TRUE
484 | Remove ceiling finishes - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
485 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 109 - OG1 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
486 | FORM FLOOD BARRIER FOUNDATIONS - OG-1 | 30105 | 15052.5 | 15052.5 |  | 30105 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 |  | 100% | MLJ | Brian | FALSE | TRUE | FALSE
487 | DRILL & GROUT DOWELS - OG-1 | 3745 | 1872.5 |  |  | 1872.5 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 | for curb wall | 50% | MLJ | Ricky | FALSE | FALSE | TRUE
488 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-1 | 27638 | 27638 |  |  | 27638 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
489 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-1 | 18434 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
490 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-1 | 15427 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
491 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-1 | 3113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
492 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-1 | 50274 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
493 | Footing/Pier | 8892 | 4446 |  |  | 4446 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 |  | 50% | Tonage | Ricky | FALSE | FALSE | TRUE
494 | Plumbing Pipe Insulation | 34034 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
495 | Retaining Walls | 1428 | 714 |  |  | 714 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 |  | 50% | Tonage | Ricky | FALSE | FALSE | TRUE
496 | Entrance Slab | 11730 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
497 | Concrete Shelf | 6432 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
498 | New Concrete Curb Next to Existing Wall | 234 | 234 |  |  | 234 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
499 | GFRP Sikawrap 100 G | 27456 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 110 - OG1 - Division 3 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
500 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-1 | 396 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 111 - OG1 - Division 4 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
501 | Overhead protection for Masonry | 5088 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 111 - OG1 - Division 4 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
502 | 2" Face brick | 153384 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 111 - OG1 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
503 | 6" vertically reinforced CMU | 38368 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 111 - OG1 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
504 | 2" rigid Insulation | 6715 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 111 - OG1 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
505 | Heat Trace | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 011 - SG1 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
506 | Coping stone C1/A-300 | 24909 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 111 - OG1 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
507 | MATERIAL AND FABRICATION | 16765 | 16765 |  |  | 16765 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 112 - OG1 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
508 | INSTALLATION | 19800 | 19800 |  |  | 19800 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 112 - OG1 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
509 | Temporary Aluminum Over Pass Stairs | 28598 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 112 - OG1 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
510 | PENETRATION FIRESTOPPING EXTG BLDG - OG-1 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 113 - OG1 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
511 | JOINT SEALANTS EXTG BLDGS - OG-1 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 113 - OG1 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
512 | Bituthene 4000 waterproofing membrane | 10217 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 113 - OG1 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
513 | GE Elemax 2600 Silicone air and vapor barrier | 13728 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 113 - OG1 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
514 | Crystalline Waterproofing at perimeter walls | 30878 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 113 - OG1 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
515 | Waterproofing at foundation walls | 15640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 113 - OG1 - Division 7 |  | 0% | DStar | Ricky | FALSE | FALSE | TRUE
516 | Survey | 66000 | 66000 |  |  | 66000 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
517 | Doors, Frames & Hardware - Labor | 17514 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 114 - OG1 - Division 8 |  | 34.26% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
518 | Furnish Doors | 6272 | 2069.76 |  |  | 2069.76 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 115 - OG1 - Division 9 |  | 33% | MLJ | Kurston | FALSE | FALSE | TRUE
519 | Layout | 5143 | 5143 |  |  | 5143 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 115 - OG1 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
520 | Loading | 7458 | 7458 |  |  | 7458 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 115 - OG1 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
521 | Framing & Drywall - Materials | 12087 | 12087 |  |  | 12087 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 115 - OG1 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
522 | Framing- Labor | 12601 | 12601 |  |  | 12601 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 115 - OG1 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
523 | Drywall - Labor | 18260 | 18260 |  |  | 18260 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 115 - OG1 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
524 | Tape/ Spackle finishes | 12344 | 9258 |  |  | 9258 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 115 - OG1 - Division 9 |  | 75% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
525 | Stucco | 10183 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 115 - OG1 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
526 | Resilient Flooring and base - OG-1 | 12880 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 115 - OG1 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | FALSE | TRUE
527 | Exhaust Fans: Furnish | 1320 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
528 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-1 | 57648 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 116 - OG1 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
529 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-1 | 63427 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 116 - OG1 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
530 | Temporary Egress Stair Storage Sign | 2640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 116 - OG1 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
531 | Address Signs | 4675 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 116 - OG1 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
532 | Clean and refurbish landing device components in the pit | 4000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
533 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
534 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
535 | Replace oil buffers | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
536 | Replace compensation guidance system per dwgs | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
537 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
538 | Exhaust Fans: Install | 4565 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
539 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
540 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
541 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
542 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
543 | Wire brush sills and support (at the first floor only) | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
544 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
545 | Replace pit lights and outlets | 3000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
546 | Replace all pit stop switches and light switches | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
547 | Repair/replace pit access doors and hardware | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
548 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
549 | Steam Unit Heaters: Furnish | 3300 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
550 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
551 | Clean and paint buffer inspection ladders | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
552 | Clean out pit of all dirt and debris | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
553 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 117 - OG1 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
554 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 9526.3 |  |  | 9526.3 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 70% | Vital | Kurston | FALSE | FALSE | TRUE
555 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 550 | 495 |  |  | 495 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
556 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 1100 |  |  | 1100 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 100% | Vital | Kurston | FALSE | FALSE | TRUE
557 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2420 | 1815 |  |  | 1815 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
558 | HANGERS AND SUPPORTS | 11551 | 8663.25 |  |  | 8663.25 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
559 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
560 | Steam Unit Heaters: Install | 23100 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
561 | DOMESTIC WATER PIPING | 108020 | 81015 |  |  | 81015 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
562 | DOMESTIC WATER PIPING SPECIALTIES | 19183 | 14387.25 |  |  | 14387.25 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
563 | SANITARY WASTE PIPING | 95172 | 80896.2 |  |  | 80896.2 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 85% | Vital | Kurston | FALSE | FALSE | TRUE
564 | SANITARY WASTE PIPING SPECIALTIES | 34188 | 32478.6 |  |  | 32478.6 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 95% | Vital | Kurston | FALSE | FALSE | TRUE
565 | STORM DRAINAGE PIPING SPECIALTIES | 34188 | 17094 |  |  | 17094 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
566 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 187000 | 93500 |  |  | 93500 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
567 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 |  |  | 5357 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 | Material on site | 100% | Vital | Kurston | FALSE | FALSE | TRUE
568 | Plumbing Pipe Insulation | 41899 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
569 | Heat Trace | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 118 - OG1 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
570 | Survey | 66000 | 66000 |  |  | 66000 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
571 | Condensate Return Unit: Furnish | 7700 | 7700 |  |  | 7700 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
572 | Exhaust Fans: Furnish | 5280 | 5280 |  |  | 5280 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 | On-site in welkin's yard | 100% | Welkin | Sully | FALSE | FALSE | TRUE
573 | Exhaust Fans: Install | 8360 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
574 | Steam Unit Heaters: Furnish | 1100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
575 | Steam Unit Heaters: Install | 9900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
576 | Condensate Return Unit: Furnish | 7700 | 7700 |  |  | 7700 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
577 | Condensate Return Unit: Install | 16500 | 16500 |  |  | 16500 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
578 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
579 | Heating and Ventilation Unit: Install | 17600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
580 | Steam Traps: Furnish | 1980 | 1980 |  |  | 1980 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
581 | Steam Traps: Install | 14300 | 11122.54 |  |  | 11122.54 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 77.78% | Welkin | Sully | FALSE | FALSE | TRUE
582 | Condensate Return Unit: Install | 16500 | 16500 |  |  | 16500 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
583 | Vacuum Pump Unit: Furnish | 17600 | 17600 |  |  | 17600 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
584 | Vacuum Pump Unit: Install | 19800 | 19800 |  |  | 19800 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
585 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 89100 | 80190 |  |  | 80190 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
586 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 121000 | 108900 |  |  | 108900 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
587 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 38500 | 34650 |  |  | 34650 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
588 | Mechanical Pipe: Hydrostatic Testing | 2200 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
589 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9900 | 6930 |  |  | 6930 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 70% | Welkin | Sully | FALSE | FALSE | TRUE
590 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 17600 | 12320 |  |  | 12320 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 70% | Welkin | Sully | FALSE | FALSE | TRUE
591 | HVAC Ductwork: Testing & Balancing | 1100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
592 | Controls: Furnish and Install: Devices | 77000 | 48510 |  |  | 48510 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 63% | Welkin | Sully | FALSE | FALSE | TRUE
593 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
594 | Controls: Furnish and Install: Controls Conduit | 38500 | 33110 |  |  | 33110 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 86% | Welkin | Sully | FALSE | FALSE | TRUE
595 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
596 | Controls: Connect to Final Termination Points | 7700 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
597 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
598 | Insulation: Furnish and Install: Ductwork Insulation | 9900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
599 | Insulation: Furnish and Install: Piping Insulation | 17600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
600 | Insulation: Furnish and Install: Equipment Insulation | 9900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 119 - OG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
601 | ATS Energization | 13688 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
602 | ATS Installation | 191625 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
603 | ATS Terminations | 13688 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
604 | Heating and Ventilation Unit: Install | 17600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
605 | ATS Testing | 13688 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
606 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
607 | Cabling - Interior Branch (1/0 & Smaller) | 200000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
608 | Cabling - Risers & Feeders (2/0 & Larger) | 591300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
609 | Conduit - Branch Circuits (1 1/2" & Smaller) | 246375 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
610 | Conduit - Risers (2" & Larger) | 591300 | 59130 |  |  | 59130 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 10% | Five Star | Kurston | FALSE | FALSE | TRUE
611 | Demolition/Temp Light & Power | 54750 | 30112.5 |  |  | 30112.5 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 55% | Five Star | Kurston | FALSE | FALSE | TRUE
612 | Firestopping | 5250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
613 | Foundation Coring | 21000 | 10500 |  |  | 10500 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 50% | Five Star | Kurston | FALSE | FALSE | TRUE
614 | Lighting Controls | 25200 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
615 | Steam Traps: Furnish | 1760 | 1320 |  |  | 1320 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 75% | Welkin | Sully | FALSE | FALSE | TRUE
616 | Lighting Remove & Re-install | 39420 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
617 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
618 | Mechanical Terminations(Dampers, Heaters, Motors) | 65700 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
619 | Survey | 65700 | 65700 |  |  | 65700 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
620 | Switches and Receptacles | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
621 | Switchgear & Panelboard Energization | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
622 | Switchgear & Panelboard Installation | 361350 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
623 | Switchgear & Panelboard Terminations | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
624 | Switchgear & Panelboard Testing | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 120 - OG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
625 | Fire Alarm Conduit | 21900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 121 - OG1 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
626 | Steam Traps: Install | 13200 | 9900 |  |  | 9900 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 75% | Welkin | Sully | FALSE | FALSE | TRUE
627 | Fire Alarm Wiring | 19710 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 121 - OG1 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
628 | Fire Alarm Devices | 24090 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 121 - OG1 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
629 | Fire Alarm Programming & Pretest | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 121 - OG1 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
630 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 121 - OG1 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
631 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-1 | 11300 | 10735 |  |  | 10735 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 122 - OG1 - Division 31 |  | 95% | MLJ | Ricky | FALSE | FALSE | TRUE
632 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-1 | 3981 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 122 - OG1 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
633 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-1 | 1181 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | K- OG1 | 122 - OG1 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
634 | Gaskets | 45000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
635 | Wire Insulation | 37500 | 37500 |  |  | 37500 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
636 | Assumed Flooring Material (Slab Penetrations) | 57600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
637 | Vacuum Pump Unit: Furnish | 17600 | 17600 |  |  | 17600 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
638 | Pipe Insulation | 113400 | 113400 |  |  | 113400 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 | Pipe insulation completed | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
639 | Fibrous Slate | 9180 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
640 | Waterproofing | 4971 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
641 | Underground Utility Materials | 11544 | 11544 |  |  | 11544 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 | Plumbing delivered last month; steam delivered this month | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
642 | Remove existing paint and plaster - cellar | 60000 | 60000 |  |  | 60000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
643 | Remove sump pump - cellar | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
644 | Remove existing vent / window and frame | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 | cellar windows | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
645 | Remove existing door, frame and hardware | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
646 | Remove Areaway slab and drain | 60000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 10% | MLJ | Ricky | FALSE | FALSE | TRUE
647 | Remove Areaway grate | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
648 | Vacuum Pump Unit: Install | 19800 | 15000 |  |  | 15000 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 75.76% | Welkin | Sully | FALSE | FALSE | TRUE
649 | Sawcut and remove portion of areaway wall | 60000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
650 | Prepare existing wall surface for paint - 1st floor | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
651 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
652 | Remove existing AC units and sleeves - 1st floor | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
653 | Remove window sill - 1st floor | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
654 | Sawcut slab opening for mechanical - 1st floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
655 | Remove floor finish - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
656 | Remove stove - 2nd floor | 4000 | 4000 |  |  | 4000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
657 | Remove CMU wall - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
658 | Remove sinks - 2nd floor | 4000 | 4000 |  |  | 4000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
659 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 88688 | 79819.2 |  |  | 79819.2 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
660 | Remove interior walls - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
661 | Patch floor and make smooth - 2nd floor | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
662 | Cut openings in slab - 2nd floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 0% | MLJ | RIcky | FALSE | FALSE | TRUE
663 | Remove existing windows - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
664 | Remove appliances - 2nd floor | 6000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
665 | Remove ceiling finishes - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
666 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 123 - OG2 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
667 | FORM FLOOD BARRIER FOUNDATIONS - OG-2 | 30704 | 21492.8 | 9211.2 |  | 30704 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 |  | 100% | MLJ | Brian | FALSE | TRUE | FALSE
668 | DRILL & GROUT DOWELS - OG-2 | 3745 | 1872.5 |  |  | 1872.5 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 | for curb wall | 50% | MLJ | Ricky | FALSE | FALSE | TRUE
669 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-2 | 27638 | 27638 |  |  | 27638 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
670 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 126500 | 113850 |  |  | 113850 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
671 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-2 | 18763 | 14072.25 |  |  | 14072.25 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 |  | 75% | MLJ | Ricky | FALSE | FALSE | TRUE
672 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-2 | 15427 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
673 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-2 | 3113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
674 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-2 | 50274 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
675 | Footing/Pier | 9009 | 7657.65 |  |  | 7657.65 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 |  | 85% | Tonage | Ricky | FALSE | FALSE | TRUE
676 | Retaining Walls | 1428 | 714 |  |  | 714 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 |  | 50% | Tonage | Ricky | FALSE | FALSE | TRUE
677 | Entrance Slab | 12342 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
678 | Concrete Shelf | 6624 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
679 | New Concrete Curb Next to Existing Wall | 234 | 234 |  |  | 234 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
680 | GFRP Sikawrap 100 G | 26400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 124 - OG2 - Division 3 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
681 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 45100 | 40590 |  |  | 40590 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
682 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-2 | 396 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 125 - OG2 - Division 4 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
683 | Overhead protection for Masonry | 5088 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 125 - OG2 - Division 4 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
684 | 6" vertically reinforced CMU | 38368 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 125 - OG2 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
685 | 2" Face brick | 153384 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 125 - OG2 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
686 | 2" rigid Insulation | 6715 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 125 - OG2 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
687 | Coping stone C1/A-300 | 25245 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 125 - OG2 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
688 | MATERIAL AND FABRICATION | 16765 | 16765 |  |  | 16765 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 126 - OG2 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
689 | INSTALLATION | 19800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 126 - OG2 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
690 | Temporary Aluminum Over Pass Stairs | 28598 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 126 - OG2 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
691 | PENETRATION FIRESTOPPING EXTG BLDG - OG-2 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 127 - OG2 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
692 | Mechanical Pipe: Hydrostatic Testing | 1513 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
693 | JOINT SEALANTS EXTG BLDGS - OG-2 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 127 - OG2 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
694 | Bituthene 4000 waterproofing membrane | 10217 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 127 - OG2 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
695 | GE Elemax 2600 Silicone air and vapor barrier | 13728 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 127 - OG2 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
696 | Crystalline Waterproofing at perimeter walls | 30878 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 127 - OG2 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
697 | Waterproofing at foundation walls | 15640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 127 - OG2 - Division 7 |  | 0% | DStar | Ricky | FALSE | FALSE | TRUE
698 | Doors, Frames & Hardware - Labor | 17514 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 128 - OG2 - Division 8 |  | 34.26% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
699 | Furnish Doors | 6272 | 2069.76 |  |  | 2069.76 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 129 - OG2 - Division 9 |  | 33% | MLJ | Kurston | FALSE | FALSE | TRUE
700 | Layout | 5143 | 5143 |  |  | 5143 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 129 - OG2 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
701 | Loading | 6686 | 6686 |  |  | 6686 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 129 - OG2 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
702 | Framing & Drywall - Materials | 12087 | 12087 |  |  | 12087 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 129 - OG2 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
703 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9900 | 6930 |  |  | 6930 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 70% | Welkin | Sully | FALSE | FALSE | TRUE
704 | Framing- Labor | 12601 | 12601 |  |  | 12601 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 129 - OG2 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
705 | Drywall - Labor | 18260 | 18260 |  |  | 18260 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 129 - OG2 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
706 | Tape/ Spackle finishes | 12344 | 6172 |  |  | 6172 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 129 - OG2 - Division 9 |  | 50% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
707 | Stucco | 10183 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 129 - OG2 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
708 | Resilient Flooring and base - OG-2 | 12880 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 129 - OG2 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | FALSE | TRUE
709 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-2 | 57648 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 130 - OG2 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
710 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-2 | 63427 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 130 - OG2 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
711 | Temporary Egress Stair Storage Sign | 1320 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 130 - OG2 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
712 | Address Signs | 4675 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 130 - OG2 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
713 | Clean and refurbish landing device components in the pit | 4000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
714 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 17600 | 12320 |  |  | 12320 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 70% | Welkin | Sully | FALSE | FALSE | TRUE
715 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
716 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
717 | Replace oil buffers | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
718 | Replace compensation guidance system per dwgs | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
719 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
720 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
721 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
722 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
723 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
724 | Wire brush sills and support (at the first floor only) | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
725 | HVAC Ductwork: Testing & Balancing | 1100 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
726 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
727 | Replace pit lights and outlets | 3000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
728 | Replace all pit stop switches and light switches | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
729 | Repair/replace pit access doors and hardware | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
730 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
731 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
732 | Clean and paint buffer inspection ladders | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
733 | Clean out pit of all dirt and debris | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
734 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 131 - OG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
735 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 6804.5 |  |  | 6804.5 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
736 | Controls: Furnish and Install: Devices | 71500 | 34984.95 |  |  | 34984.95 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 48.93% | Welkin | Sully | FALSE | FALSE | TRUE
737 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 550 | 495 |  |  | 495 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
738 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 550 |  |  | 550 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
739 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3739 | 1869.5 |  |  | 1869.5 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
740 | HANGERS AND SUPPORTS | 11551 | 8663.25 |  |  | 8663.25 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
741 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
742 | DOMESTIC WATER PIPING | 113740 | 85305 |  |  | 85305 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
743 | DOMESTIC WATER PIPING SPECIALTIES | 19183 | 14387.25 |  |  | 14387.25 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
744 | SANITARY WASTE PIPING | 98230 | 63849.5 |  |  | 63849.5 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 65% | Vital | Kurston | FALSE | FALSE | TRUE
745 | SANITARY WASTE PIPING SPECIALTIES | 30063 | 27056.7 |  |  | 27056.7 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
746 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 16500 |  |  | 16500 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
747 | Controls: Furnish and Install: Controls Conduit | 33000 | 7920 |  |  | 7920 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 24% | Welkin | Sully | FALSE | FALSE | TRUE
748 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 264000 | 79200 |  |  | 79200 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 30% | Vital | Kurston | FALSE | FALSE | TRUE
749 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 |  |  | 5357 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 | Material on site | 100% | Vital | Kurston | FALSE | FALSE | TRUE
750 | Plumbing Pipe Insulation | 28886 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
751 | Heat Trace | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 132 - OG2 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
752 | Survey | 66000 | 66000 |  |  | 66000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
753 | Exhaust Fans: Furnish | 5280 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
754 | Exhaust Fans: Install | 8910 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
755 | Steam Unit Heaters: Furnish | 1100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
756 | Steam Unit Heaters: Install | 10450 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
757 | Condensate Return Unit: Furnish | 7700 | 7700 |  |  | 7700 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
758 | Controls: Furnish and Install: Controls Wiring | 9900 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
759 | Condensate Return Unit: Install | 17050 | 17050 |  |  | 17050 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
760 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
761 | Heating and Ventilation Unit: Install | 18150 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
762 | Steam Traps: Furnish | 1760 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
763 | Steam Traps: Install | 12100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
764 | Vacuum Pump Unit: Furnish | 17600 | 17600 |  |  | 17600 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
765 | Vacuum Pump Unit: Install | 20350 | 20350 |  |  | 20350 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
766 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 86048 | 77443.2 |  |  | 77443.2 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
767 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 116050 | 104445 |  |  | 104445 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
768 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 34100 | 30690 |  |  | 30690 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
769 | Controls: Connect to Final Termination Points | 6600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
770 | Mechanical Pipe: Hydrostatic Testing | 3053 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
771 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 38500 | 25410 |  |  | 25410 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 66% | Welkin | Sully | FALSE | FALSE | TRUE
772 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 77000 | 50820 |  |  | 50820 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 66% | Welkin | Sully | FALSE | FALSE | TRUE
773 | HVAC Ductwork: Testing & Balancing | 4400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
774 | Controls: Furnish and Install: Devices | 77000 | 50050 |  |  | 50050 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 65% | Welkin | Sully | FALSE | FALSE | TRUE
775 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 |  |  | 41800 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 95% | Welkin | Sully | FALSE | FALSE | TRUE
776 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
777 | Controls: Connect to Final Termination Points | 8800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
778 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
779 | Insulation: Furnish and Install: Ductwork Insulation | 9900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
780 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
781 | Insulation: Furnish and Install: Piping Insulation | 17600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
782 | Insulation: Furnish and Install: Equipment Insulation | 9900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 133 - OG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
783 | ATS Energization | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
784 | ATS Installation | 153300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
785 | ATS Terminations | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
786 | ATS Testing | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
787 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
788 | Cabling - Interior Branch (1/0 & Smaller) | 125000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
789 | Cabling - Risers & Feeders (2/0 & Larger) | 394200 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
790 | Conduit - Branch Circuits (1 1/2" & Smaller) | 232688 | 5000 |  |  | 5000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 2.149% | Five Star | Kurston | FALSE | FALSE | TRUE
791 | Insulation: Furnish and Install: Ductwork Insulation | 9900 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
792 | Conduit - Risers (2" & Larger) | 394200 | 118260 |  |  | 118260 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 30% | Five Star | Kurston | FALSE | FALSE | TRUE
793 | Demolition/Temp Light & Power | 54750 | 16425 |  |  | 16425 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 30% | Five Star | Kurston | FALSE | FALSE | TRUE
794 | Firestopping | 5250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
795 | Foundation Coring | 21000 | 21000 |  |  | 21000 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
796 | Lighting Controls | 32550 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
797 | Lighting Remove & Re-install | 40406 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
798 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
799 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
800 | Survey | 65700 | 65700 |  |  | 65700 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
801 | Switches and Receptacles | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
802 | Insulation: Furnish and Install: Piping Insulation | 17600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
803 | Switchgear & Panelboard Energization | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
804 | Switchgear & Panelboard Installation | 361350 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
805 | Switchgear & Panelboard Terminations | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
806 | Switchgear & Panelboard Testing | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 134 - OG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
807 | Fire Alarm Conduit | 21900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 135 - OG2 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
808 | Fire Alarm Wiring | 16425 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 135 - OG2 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
809 | Fire Alarm Devices | 22995 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 135 - OG2 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
810 | Fire Alarm Programming & Pretest | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 135 - OG2 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
811 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 135 - OG2 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
812 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-2 | 11300 | 9040 |  |  | 9040 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 136 - OG2 - Division 31 |  | 80% | MLJ | Ricky | FALSE | FALSE | TRUE
813 | Insulation: Furnish and Install: Equipment Insulation | 9900 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 012 - SG1 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
814 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-2 | 3981 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 136 - OG2 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
815 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-2 | 1181 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | L- OG2 | 136 - OG2 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
816 | Gaskets | 78750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
817 | Wire Insulation | 37500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
818 | Assumed Flooring Material (Slab Penetrations) | 46800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
819 | Duct Seal | 3600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
820 | Fibrous Slate | 9180 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
821 | Waterproofing | 4971 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
822 | Underground Utility Materials | 11388 | 11388 |  |  | 11388 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 | Material on site | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
823 | Remove existing paint and plaster - cellar | 60000 | 60000 |  |  | 60000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
824 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 13867.5 |  |  | 13867.5 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 50.66% | Five Star | Kurston | FALSE | FALSE | TRUE
825 | Remove sump pump - cellar | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
826 | Remove existing vent / window and frame | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 | cellar windows | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
827 | Remove existing door, frame and hardware | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
828 | Remove Areaway slab and drain | 60000 | 30000 |  |  | 30000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 | 3 of 6 removed | 50% | MLJ | Ricky | FALSE | FALSE | TRUE
829 | Remove Areaway grate | 20000 | 10000 |  |  | 10000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 | 3 of 6 removed | 50% | MLJ | Ricky | FALSE | FALSE | TRUE
830 | Sawcut and remove portion of areaway wall | 60000 | 30000 |  |  | 30000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 | 3 of 6 removed | 50% | MLJ | Ricky | FALSE | FALSE | TRUE
831 | Remove existing AC units and sleeves - 1st floor | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
832 | Remove window sill - 1st floor | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
833 | Sawcut slab opening for mechanical - 1st floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
834 | Remove floor finish - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
835 | Cabling - Interior Branch (1/0 & Smaller) | 150000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
836 | Remove stove - 2nd floor | 4000 | 4000 |  |  | 4000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
837 | Remove CMU wall - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
838 | Remove sinks - 2nd floor | 4000 | 4000 |  |  | 4000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
839 | Remove interior walls - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
840 | Patch floor and make smooth - 2nd floor | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
841 | Cut openings in slab - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 100% | MLJ | RIcky | FALSE | FALSE | TRUE
842 | Remove existing windows - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
843 | Remove appliances - 2nd floor | 6000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
844 | Remove ceiling finishes - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
845 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 137 - OG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
846 | Cabling - Risers & Feeders (2/0 & Larger) | 295650 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
847 | FORM FLOOD BARRIER FOUNDATIONS - OG-3 | 30704 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 |  | 0% | MLJ | Brian | FALSE | FALSE | TRUE
848 | DRILL & GROUT DOWELS - OG-3 | 3745 | 1872.5 |  |  | 1872.5 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 | for curb wall | 50% | MLJ | Ricky | FALSE | FALSE | TRUE
849 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-3 | 27638 | 13819 |  |  | 13819 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 | All windows removed; none have been infilled yet | 50% | MLJ | Ricky | FALSE | FALSE | TRUE
850 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-3 | 18763 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
851 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-3 | 15427 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
852 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-3 | 3113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
853 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-3 | 50274 | 50274 |  |  | 50274 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
854 | Footing/Pier | 9009 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
855 | Retaining Walls | 1428 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
856 | Entrance Slab | 11730 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
857 | Conduit - Branch Circuits (1 1/2" & Smaller) | 246375 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
858 | Concrete Shelf | 6768 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
859 | New Concrete Curb Next to Existing Wall | 234 | 234 |  |  | 234 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
860 | GFRP Sikawrap 100 G | 27456 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 138 - OG3 - Division 3 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
861 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-3 | 396 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 139 - OG3 - Division 4 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
862 | Overhead protection for Masonry | 5088 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 139 - OG3 - Division 4 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
863 | 6" vertically reinforced CMU | 38368 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 139 - OG3 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
864 | 2" Face brick | 153384 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 139 - OG3 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
865 | 2" rigid Insulation | 6715 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 139 - OG3 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
866 | Coping stone C1/A-300 | 25245 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 139 - OG3 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
867 | MATERIAL AND FABRICATION | 16765 | 16765 |  |  | 16765 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 140 - OG3 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
868 | Conduit - Risers (2" & Larger) | 295650 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
869 | INSTALLATION | 19800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 140 - OG3 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
870 | Temporary Aluminum Over Pass Stairs | 28598 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 140 - OG3 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
871 | PENETRATION FIRESTOPPING EXTG BLDG - OG-3 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 141 - OG3 - Divisiono 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
872 | JOINT SEALANTS EXTG BLDGS - OG-3 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 141 - OG3 - Divisiono 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
873 | Bituthene 4000 waterproofing membrane | 10217 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 141 - OG3 - Divisiono 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
874 | GE Elemax 2600 Silicone air and vapor barrier | 14784 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 141 - OG3 - Divisiono 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
875 | Crystalline Waterproofing at perimeter walls | 29843 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 141 - OG3 - Divisiono 7 |  | 0% | DStar | Ricky | FALSE | FALSE | TRUE
876 | Waterproofing at foundation walls | 15640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 141 - OG3 - Divisiono 7 |  | 0% | DStar | Ricky | FALSE | FALSE | TRUE
877 | Doors, Frames & Hardware - Labor | 17514 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 142 - OG3 - Division 8 |  | 34.26% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
878 | Furnish Doors | 6272 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 143 - OG3 - Division 9 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
879 | Demolition/Temp Light & Power | 54750 | 16425 |  |  | 16425 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 30% | Five Star | Kurston | FALSE | FALSE | TRUE
880 | Layout | 5401 | 5401 |  |  | 5401 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 143 - OG3 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
881 | Loading | 6686 | 6686 |  |  | 6686 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 143 - OG3 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
882 | Framing & Drywall - Materials | 11829 | 11829 |  |  | 11829 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 143 - OG3 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
883 | Framing- Labor | 13629 | 13629 |  |  | 13629 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 143 - OG3 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
884 | Drywall - Labor | 18260 | 18260 |  |  | 18260 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 143 - OG3 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
885 | Tape/ Spackle finishes | 12344 | 6172 |  |  | 6172 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 143 - OG3 - Division 9 |  | 50% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
886 | Stucco | 10183 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 143 - OG3 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
887 | Resilient Flooring and base - OG-3 | 15640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 143 - OG3 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | FALSE | TRUE
888 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-3 | 57648 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 144 - OG3 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
889 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-3 | 63427 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 144 - OG3 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
890 | Firestopping | 5250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
891 | Temporary Egress Stair Storage Sign | 2640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 144 - OG3 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
892 | Address Signs | 4675 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 144 - OG3 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
893 | Clean and refurbish landing device components in the pit | 4000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
894 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
895 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
896 | Replace oil buffers | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
897 | Replace compensation guidance system per dwgs | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
898 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
899 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
900 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
901 | Foundation Coring | 21000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
902 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
903 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
904 | Wire brush sills and support (at the first floor only) | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
905 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
906 | Replace pit lights and outlets | 3000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
907 | Replace all pit stop switches and light switches | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
908 | Repair/replace pit access doors and hardware | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
909 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
910 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
911 | Clean and paint buffer inspection ladders | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
912 | Lighting Controls | 26250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
913 | Clean out pit of all dirt and debris | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
914 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 145 - OG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
915 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 6804.5 |  |  | 6804.5 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
916 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 786 | 550.2 |  |  | 550.2 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 70% | Vital | Kurston | FALSE | FALSE | TRUE
917 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 330 |  |  | 330 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 30% | Vital | Kurston | FALSE | FALSE | TRUE
918 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2637 | 1582.2 |  |  | 1582.2 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 60% | Vital | Kurston | FALSE | FALSE | TRUE
919 | HANGERS AND SUPPORTS | 11526 | 9797.1 |  |  | 9797.1 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 85% | Vital | Kurston | FALSE | FALSE | TRUE
920 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
921 | DOMESTIC WATER PIPING | 128777 | 109460.45 |  |  | 109460.45 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 85% | Vital | Kurston | FALSE | FALSE | TRUE
922 | DOMESTIC WATER PIPING SPECIALTIES | 19183 | 18223.85 |  |  | 18223.85 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 95% | Vital | Kurston | FALSE | FALSE | TRUE
923 | Lighting Remove & Re-install | 27972 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
924 | SANITARY WASTE PIPING | 147017 | 95561.05 |  |  | 95561.05 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 65% | Vital | Kurston | FALSE | FALSE | TRUE
925 | SANITARY WASTE PIPING SPECIALTIES | 33792 | 30412.8 |  |  | 30412.8 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
926 | STORM DRAINAGE PIPING SPECIALTIES | 33792 | 16896 |  |  | 16896 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
927 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 264000 | 66000 |  |  | 66000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 25% | Vital | Kurston | FALSE | FALSE | TRUE
928 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 9317 | 8851.15 |  |  | 8851.15 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 95% | Vital | Kurston | FALSE | FALSE | TRUE
929 | Plumbing Pipe Insulation | 35464 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
930 | Heat Trace | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 146 - OG3 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
931 | Survey | 66000 | 66000 |  |  | 66000 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
932 | Exhaust Fans: Furnish | 5280 | 5280 |  |  | 5280 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
933 | Exhaust Fans: Install | 14960 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
934 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
935 | Steam Unit Heaters: Furnish | 1100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
936 | Steam Unit Heaters: Install | 16500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
937 | Condensate Return Unit: Furnish | 7700 | 7700 |  |  | 7700 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
938 | Condensate Return Unit: Install | 23100 | 23100 |  |  | 23100 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
939 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
940 | Heating and Ventilation Unit: Install | 24200 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
941 | Steam Traps: Furnish | 2200 | 2200 |  |  | 2200 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
942 | Steam Traps: Install | 25025 | 15015 |  |  | 15015 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 60% | Welkin | Sully | FALSE | FALSE | TRUE
943 | Vacuum Pump Unit: Furnish | 17600 | 17600 |  |  | 17600 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
944 | Vacuum Pump Unit: Install | 26400 | 26400 |  |  | 26400 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
945 | Mechanical Terminations(Dampers, Heaters, Motors) | 39420 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
946 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 331045 | 314492.75 |  |  | 314492.75 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 | Cellar complete - 90%, 1st floor remaining - 10% | 95% | Welkin | Sully | FALSE | FALSE | TRUE
947 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 421300 | 400235 |  |  | 400235 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 | Header compelted, pipes prefabbed but still to be installed. Header is most expensive item so allow 40%, 10% for materials and remaining 50% for pipe insall | 95% | Welkin | Sully | FALSE | FALSE | TRUE
948 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 143000 | 135850 |  |  | 135850 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 95% | Welkin | Sully | FALSE | FALSE | TRUE
949 | Mechanical Pipe: Hydrostatic Testing | 4455 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
950 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 33000 | 29700 |  |  | 29700 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 | Cellar complete - 90%, 1st floor remaining - 10% | 90% | Welkin | Sully | FALSE | FALSE | TRUE
951 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 66000 | 59400 |  |  | 59400 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 | Cellar complete - 90%, 1st floor remaining - 10% | 90% | Welkin | Sully | FALSE | FALSE | TRUE
952 | HVAC Ductwork: Testing & Balancing | 3300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
953 | Controls: Furnish and Install: Devices | 77000 | 50050 |  |  | 50050 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 65% | Welkin | Sully | FALSE | FALSE | TRUE
954 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 |  |  | 41800 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 95% | Welkin | Sully | FALSE | FALSE | TRUE
955 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
956 | Survey | 65700 | 65700 |  |  | 65700 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
957 | Controls: Connect to Final Termination Points | 8800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
958 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
959 | Insulation: Furnish and Install: Ductwork Insulation | 19800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
960 | Insulation: Furnish and Install: Piping Insulation | 39600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
961 | Insulation: Furnish and Install: Equipment Insulation | 19800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 147 - OG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
962 | ATS Energization | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
963 | ATS Installation | 153300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
964 | ATS Terminations | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
965 | ATS Testing | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
966 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
967 | Switches and Receptacles | 10950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
968 | Cabling - Interior Branch (1/0 & Smaller) | 150000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
969 | Cabling - Risers & Feeders (2/0 & Larger) | 394200 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
970 | Conduit - Branch Circuits (1 1/2" & Smaller) | 219000 | 87600 |  |  | 87600 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 40% | Five Star | Kurston | FALSE | FALSE | TRUE
971 | Conduit - Risers (2" & Larger) | 394200 | 295650 |  |  | 295650 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 75% | Five Star | Kurston | FALSE | FALSE | TRUE
972 | Demolition/Temp Light & Power | 54750 | 27375 |  |  | 27375 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 50% | Five Star | Kurston | FALSE | FALSE | TRUE
973 | Firestopping | 5250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
974 | Foundation Coring | 10500 | 10500 |  |  | 10500 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
975 | Lighting Controls | 33600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
976 | Lighting Remove & Re-install | 39420 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
977 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
978 | Switchgear & Panelboard Energization | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
979 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
980 | Survey | 65700 | 65700 |  |  | 65700 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
981 | Switches and Receptacles | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
982 | Switchgear & Panelboard Energization | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
983 | Switchgear & Panelboard Installation | 361350 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
984 | Switchgear & Panelboard Terminations | 30525 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
985 | Switchgear & Panelboard Testing | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 148 - OG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
986 | Fire Alarm Conduit | 21900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 149 - OG3 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
987 | Fire Alarm Wiring | 16425 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 149 - OG3 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
988 | Fire Alarm Devices | 20805 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 149 - OG3 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
989 | Switchgear & Panelboard Installation | 65700 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
990 | Fire Alarm Programming & Pretest | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 149 - OG3 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
991 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 149 - OG3 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
992 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-3 | 11300 | 2825 |  |  | 2825 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 150 - OG3 - Division 31 |  | 25% | MLJ | Ricky | FALSE | FALSE | TRUE
993 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-3 | 3981 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 150 - OG3 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
994 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-3 | 1181 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | M- OG3 | 150 - OG3 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
995 | Gaskets | 22500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
996 | Wire Insulation | 37500 | 35625 |  |  | 35625 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 95% | ATCO | Kurston | FALSE | FALSE | TRUE
997 | Assumed Flooring Material (Slab Penetrations) | 75600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
998 | Pipe Insulation | 126000 | 120000 |  |  | 120000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 | Tank room is 50lf, other is 1000lf. All completed except for tank room | 95.24% | ATCO | Kurston | FALSE | FALSE | TRUE
999 | Tank Insulation | 9750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1000 | Switchgear & Panelboard Terminations | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1001 | Fireproofing | 32550 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1002 | Fibrous Slate | 9180 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1003 | Waterproofing | 4971 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1004 | Underground Utility Materials | 11388 | 11388 |  |  | 11388 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 | Material on site | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
1005 | Remove existing paint and plaster - cellar | 60000 | 60000 |  |  | 60000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1006 | Remove sump pump - cellar | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1007 | Remove existing vent / window and frame | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1008 | Remove existing door, frame and hardware | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1009 | Remove Areaway slab and drain | 60000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 10% | MLJ | Ricky | FALSE | FALSE | TRUE
1010 | Remove Areaway grate | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1011 | Switchgear & Panelboard Testing | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 013 - SG1 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1012 | Sawcut and remove portion of areaway wall | 60000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1013 | Prepare existing wall surface for paint - 1st floor | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1014 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1015 | Remove existing AC units and sleeves - 1st floor | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1016 | Remove window sill - 1st floor | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1017 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1018 | Remove floor finish - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1019 | Remove stove - 2nd floor | 4000 | 4000 |  |  | 4000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1020 | Remove CMU wall - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1021 | Remove sinks - 2nd floor | 4000 | 4000 |  |  | 4000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1022 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-1 | 20834 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 014 - SG1 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1023 | Remove interior walls - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1024 | Patch floor and make smooth - 2nd floor | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1025 | Cut openings in slab - 2nd floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 0% | MLJ | RIcky | FALSE | FALSE | TRUE
1026 | Remove existing windows - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1027 | Remove appliances - 2nd floor | 6000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1028 | Remove ceiling finishes - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1029 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 151 - OG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1030 | FORM FLOOD BARRIER FOUNDATIONS - OG-4 | 30704 | 0 | 15352 |  | 15352 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 |  | 50% | MLJ | Brian | FALSE | TRUE | FALSE
1031 | DRILL & GROUT DOWELS - OG-4 | 3745 | 3745 |  |  | 3745 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 | for curb wall | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1032 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-4 | 25126 | 12563 |  |  | 12563 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 | All windows removed; none have been infilled yet | 50% | MLJ | Ricky | FALSE | FALSE | TRUE
1033 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-1 | 7542 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 014 - SG1 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1034 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-4 | 18763 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1035 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-4 | 15427 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1036 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-4 | 3232 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1037 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-4 | 50274 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1038 | Footing/Pier | 9009 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1039 | Retaining Walls | 1428 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1040 | Entrance Slab | 12342 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1041 | Concrete Shelf | 6528 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1042 | New Concrete Curb Next to Existing Wall | 234 | 234 |  |  | 234 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1043 | GFRP Sikawrap 100 G | 41184 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 152 - OG4 - Division 3 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1044 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-1 | 1320 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | B- SG1 | 014 - SG1 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1045 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-4 | 396 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 153 - OG4 - Division 4 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1046 | Overhead protection for Masonry | 5088 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 153 - OG4 - Division 4 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1047 | 6" vertically reinforced CMU | 44875 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 153 - OG4 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1048 | 2" Face brick | 198275 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 153 - OG4 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1049 | 2" rigid Insulation | 7662 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 153 - OG4 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1050 | Coping stone C1/A-300 | 28328 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 153 - OG4 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1051 | MATERIAL AND FABRICATION | 16765 | 16765 |  |  | 16765 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 154 - OG4 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1052 | INSTALLATION | 19800 | 19800 |  |  | 19800 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 154 - OG4 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1053 | Temporary Aluminum Over Pass Stairs | 28598 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 154 - OG4 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1054 | PENETRATION FIRESTOPPING EXTG BLDG - OG 4 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 155 - OG4 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1055 | Gaskets | 22500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1056 | JOINT SEALANTS EXTG BLDGS - OG-4 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 155 - OG4 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1057 | Bituthene 4000 waterproofing membrane | 7491 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 155 - OG4 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1058 | GE Elemax 2600 Silicone air and vapor barrier | 22176 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 155 - OG4 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1059 | Crystalline Waterproofing at perimeter walls | 30360 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 155 - OG4 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
1060 | Waterproofing at foundation walls | 15640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 155 - OG4 - Division 7 |  | 0% | DStar | Ricky | FALSE | FALSE | TRUE
1061 | Doors, Frames & Hardware - Labor | 17514 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 156 - OG4 - Division 8 |  | 34.26% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1062 | Furnish Doors | 6272 | 2069.76 |  |  | 2069.76 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 157 - OG4 - Division 9 |  | 33% | MLJ | Kurston | FALSE | FALSE | TRUE
1063 | Layout | 5401 | 5401 |  |  | 5401 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 157 - OG4 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1064 | Loading | 6686 | 6686 |  |  | 6686 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 157 - OG4 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1065 | Framing & Drywall - Materials | 12601 | 12601 |  |  | 12601 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 157 - OG4 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1066 | Wire Insulation | 37500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1067 | Framing- Labor | 13372 | 12034.8 |  |  | 12034.8 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 157 - OG4 - Division 9 |  | 90% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1068 | Drywall - Labor | 15687 | 14118.3 |  |  | 14118.3 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 157 - OG4 - Division 9 |  | 90% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1069 | Tape/ Spackle finishes | 12344 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 157 - OG4 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1070 | Stucco | 10183 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 157 - OG4 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1071 | Resilient Flooring and base - OG-4 | 15640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 157 - OG4 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | FALSE | TRUE
1072 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-4 | 57648 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 158 - OG4 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1073 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-4 | 63427 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 158 - OG4 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1074 | Temporary Egress Stair Storage Sign | 2640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 158 - OG4 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1075 | Address Signs | 4950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 158 - OG4 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1076 | Clean and refurbish landing device components in the pit | 4000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1077 | Assumed Flooring Material (Slab Penetrations) | 10800 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1078 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1079 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1080 | Replace oil buffers | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1081 | Replace compensation guidance system per dwgs | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1082 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1083 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1084 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1085 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1086 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1087 | Wire brush sills and support (at the first floor only) | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1088 | Pipe Insulation | 113400 | 97776 |  |  | 97776 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 | 776 of 900 of complete | 86.22% | ATCO | Kurston | FALSE | FALSE | TRUE
1089 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1090 | Replace pit lights and outlets | 3000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1091 | Replace all pit stop switches and light switches | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1092 | Repair/replace pit access doors and hardware | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1093 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1094 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1095 | Clean and paint buffer inspection ladders | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1096 | Clean out pit of all dirt and debris | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1097 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 159 - OG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1098 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 4082.7 |  |  | 4082.7 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 30% | Vital | Kurston | FALSE | FALSE | TRUE
1099 | Tank Insulation | 15600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1100 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 786 | 235.8 |  |  | 235.8 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 30% | Vital | Kurston | FALSE | FALSE | TRUE
1101 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 440 |  |  | 440 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 40% | Vital | Kurston | FALSE | FALSE | TRUE
1102 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3282 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1103 | HANGERS AND SUPPORTS | 11539 | 5769.5 |  |  | 5769.5 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
1104 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1105 | DOMESTIC WATER PIPING | 125548 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1106 | DOMESTIC WATER PIPING SPECIALTIES | 19183 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1107 | SANITARY WASTE PIPING | 106914 | 90876.9 |  |  | 90876.9 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 85% | Vital | Kurston | FALSE | FALSE | TRUE
1108 | SANITARY WASTE PIPING SPECIALTIES | 30067 | 27060 |  |  | 27060 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
1109 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 16500 |  |  | 16500 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
1110 | Duct Seal | 18000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1111 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 187000 | 56100 |  |  | 56100 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 30% | Vital | Kurston | FALSE | FALSE | TRUE
1112 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 9306 | 8375.4 |  |  | 8375.4 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 | Material on site | 90% | Vital | Kurston | FALSE | FALSE | TRUE
1113 | Plumbing Pipe Insulation | 35464 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
1114 | Heat Trace | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 160 - OG4 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1115 | Survey | 66000 | 66000 |  |  | 66000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1116 | Exhaust Fans: Furnish | 5280 | 5280 |  |  | 5280 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1117 | Exhaust Fans: Install | 13860 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1118 | Steam Unit Heaters: Furnish | 1100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1119 | Steam Unit Heaters: Install | 15400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1120 | Condensate Return Unit: Furnish | 7700 | 7700 |  |  | 7700 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1121 | Vinyl Membrane and Mastic | 36720 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1122 | Condensate Return Unit: Install | 22000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1123 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1124 | Heating and Ventilation Unit: Install | 23100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1125 | Steam Traps: Furnish | 1980 | 1980 |  |  | 1980 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1126 | Steam Traps: Install | 23100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1127 | Vacuum Pump Unit: Furnish | 17600 | 17600 |  |  | 17600 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1128 | Vacuum Pump Unit: Install | 25300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1129 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 270930 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1130 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 352000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1131 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 132000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1132 | Caulk | 112500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1133 | Mechanical Pipe: Hydrostatic Testing | 4070 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1134 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 27500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1135 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 55000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1136 | HVAC Ductwork: Testing & Balancing | 3300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1137 | Controls: Furnish and Install: Devices | 77000 | 16701.3 |  |  | 16701.3 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 21.69% | Welkin | Sully | FALSE | FALSE | TRUE
1138 | Controls: Furnish and Install: Controls Conduit | 44000 | 39600 |  |  | 39600 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
1139 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1140 | Controls: Connect to Final Termination Points | 8800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1141 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1142 | Insulation: Furnish and Install: Ductwork Insulation | 18150 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1143 | Fibrous Slate | 14025 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1144 | Insulation: Furnish and Install: Piping Insulation | 37950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1145 | Insulation: Furnish and Install: Equipment Insulation | 18150 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 161 - OG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1146 | ATS Energization | 13688 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1147 | ATS Installation | 191625 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1148 | ATS Terminations | 13688 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1149 | ATS Testing | 13688 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1150 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1151 | Cabling - Interior Branch (1/0 & Smaller) | 200000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1152 | Cabling - Risers & Feeders (2/0 & Larger) | 591300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1153 | Conduit - Branch Circuits (1 1/2" & Smaller) | 260063 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1154 | Waterproofing | 4971 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1155 | Conduit - Risers (2" & Larger) | 492750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1156 | Demolition/Temp Light & Power | 54750 | 32850 |  |  | 32850 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 60% | Five Star | Kurston | FALSE | FALSE | TRUE
1157 | Firestopping | 5250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1158 | Foundation Coring | 21000 | 21000 |  |  | 21000 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
1159 | Lighting Controls | 26250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1160 | Lighting Remove & Re-install | 39420 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1161 | Lighting System Program & Energize | 5550 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1162 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1163 | Survey | 65700 | 65700 |  |  | 65700 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
1164 | Switches and Receptacles | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1165 | Underground Utility Materials | 46800 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1166 | Switchgear & Panelboard Energization | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1167 | Switchgear & Panelboard Installation | 361350 | 180675 |  |  | 180675 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 50% | Five Star | Kurston | FALSE | FALSE | TRUE
1168 | Switchgear & Panelboard Terminations | 30525 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1169 | Switchgear & Panelboard Testing | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 162 - OG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1170 | Fire Alarm Conduit | 27375 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 163 - OG4 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1171 | Fire Alarm Wiring | 19710 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 163 - OG4 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1172 | Fire Alarm Devices | 21900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 163 - OG4 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1173 | Fire Alarm Programming & Pretest | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 163 - OG4 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1174 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 163 - OG4 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1175 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-4 | 11300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 164 - OG4 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1176 | Remove existing paint and plaster - cellar | 60000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1177 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-4 | 3981 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 164 - OG4 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1178 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-4 | 1181 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | N- OG4 | 164 - OG4 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1179 | Gaskets | 45000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1180 | Wire Insulation | 37500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1181 | Assumed Flooring Material (Slab Penetrations) | 57600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1182 | Pipe Insulation | 113400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1183 | Tank Insulation | 9750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1184 | Fireproofing | 127875 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1185 | Fibrous Slate | 9180 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1186 | Waterproofing | 4971 | 4971 |  |  | 4971 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
1187 | Remove sump pump - cellar | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1188 | Underground Utility Materials | 11388 | 9110.4 |  |  | 9110.4 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 80% | ATCO | Kurston | FALSE | FALSE | TRUE
1189 | Remove existing paint and plaster - cellar | 60000 | 60000 |  |  | 60000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1190 | Remove sump pump - cellar | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1191 | Remove existing vent / window and frame | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1192 | Remove existing door, frame and hardware | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1193 | Remove Areaway slab and drain | 60000 | 12000 |  |  | 12000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 20% | MLJ | Ricky | FALSE | FALSE | TRUE
1194 | Remove Areaway grate | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1195 | Sawcut and remove portion of areaway wall | 60000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1196 | Prepare existing wall surface for paint - 1st floor | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1197 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1198 | Remove existing vent / window and frame - cellar | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1199 | Remove existing AC units and sleeves - 1st floor | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1200 | Remove window sill - 1st floor | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1201 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1202 | Remove floor finish - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1203 | Remove stove - 2nd floor | 4000 | 4000 |  |  | 4000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1204 | Remove CMU wall - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1205 | Remove sinks - 2nd floor | 4000 | 4000 |  |  | 4000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1206 | Remove interior walls - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1207 | Patch floor and make smooth - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1208 | Cut openings in slab - 2nd floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 0% | MLJ | RIcky | FALSE | FALSE | TRUE
1209 | Remove existing door, frame and hardware - cellar | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1210 | Remove existing windows - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1211 | Remove appliances - 2nd floor | 6000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1212 | Remove ceiling finishes - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1213 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 165 - OG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1214 | FORM FLOOD BARRIER FOUNDATIONS - OG-5 | 30704 | 0 | 15352 |  | 15352 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 |  | 50% | MLJ | Brian | FALSE | TRUE | FALSE
1215 | DRILL & GROUT DOWELS - OG-5 | 3745 | 1872.5 |  |  | 1872.5 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 | for curb wall | 50% | MLJ | Ricky | FALSE | FALSE | TRUE
1216 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-5 | 25126 | 12563 |  |  | 12563 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 | All windows removed; none have been infilled yet | 50% | MLJ | Ricky | FALSE | FALSE | TRUE
1217 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-5 | 18763 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1218 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-5 | 15427 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1219 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-5 | 3113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1220 | Remove Areaway slab and drain - cellar | 60000 | 6000 |  |  | 6000 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 10% | MLJ | Ricky | FALSE | FALSE | TRUE
1221 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-5 | 50274 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1222 | Footing/Pier | 14820 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1223 | Retaining Walls | 1428 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1224 | Entrance Slab | 12342 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1225 | Concrete Shelf | 6576 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1226 | New Concrete Curb Next to Existing Wall | 234 | 234 |  |  | 234 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1227 | GFRP Sikawrap 100 G | 41184 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 166 - OG5 - Division 3 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1228 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-5 | 396 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 167 - OG5 - Division 4 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1229 | Overhead protection for Masonry | 5088 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 167 - OG5 - Division 4 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1230 | 6" vertically reinforced CMU | 44875 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 167 - OG5 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1231 | Remove Areaway grate - cellar | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1232 | 2" Face brick | 198275 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 167 - OG5 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1233 | 2" rigid Insulation | 7662 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 167 - OG5 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1234 | Coping stone C1/A-300 | 28002 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 167 - OG5 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1235 | MATERIAL AND FABRICATION | 16765 | 16765 |  |  | 16765 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 168 - OG5 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1236 | INSTALLATION | 19800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 168 - OG5 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1237 | Temporary Aluminum Over Pass Stairs | 28598 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 168 - OG5 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1238 | PENETRATION FIRESTOPPING EXTG BLDG - OG 5 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 169 - OG5 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1239 | JOINT SEALANTS EXTG BLDGS - OG-5 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 169 - OG5 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1240 | Bituthene 4000 waterproofing membrane | 7491 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 169 - OG5 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1241 | GE Elemax 2600 Silicone air and vapor barrier | 22176 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 169 - OG5 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1242 | Sawcut and remove portion of areaway wall - cellar | 60000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1243 | Crystalline Waterproofing at perimeter walls | 29440 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 169 - OG5 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
1244 | Waterproofing at foundation walls | 15640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 169 - OG5 - Division 7 |  | 0% | DStar | Ricky | FALSE | FALSE | TRUE
1245 | Doors, Frames & Hardware - Labor | 17514 | 13135.5 |  |  | 13135.5 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 170 - OG5 - Division 8 |  | 75% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1246 | Furnish Doors | 6272 | 2069.76 |  |  | 2069.76 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 171 - OG5 - Division 9 |  | 33% | MLJ | Kurston | FALSE | FALSE | TRUE
1247 | Layout | 3858 | 3858 |  |  | 3858 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 171 - OG5 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1248 | Loading | 6686 | 6686 |  |  | 6686 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 171 - OG5 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1249 | Framing & Drywall - Materials | 11829 | 10646.1 |  |  | 10646.1 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 171 - OG5 - Division 9 |  | 90% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1250 | Framing- Labor | 12601 | 11340.9 |  |  | 11340.9 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 171 - OG5 - Division 9 |  | 90% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1251 | Drywall - Labor | 16715 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 171 - OG5 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1252 | Tape/ Spackle finishes | 12087 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 171 - OG5 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1253 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1254 | Stucco | 10183 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 171 - OG5 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1255 | Resilient Flooring and base - OG-5 | 15640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 171 - OG5 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | FALSE | TRUE
1256 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-5 | 57648 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 172 - OG5 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1257 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-5 | 63427 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 172 - OG5 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1258 | Temporary Egress Stair Storage Sign | 2640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 172 - OG5 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1259 | Address Signs | 4950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 172 - OG5 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1260 | Clean and refurbish landing device components in the pit | 4000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1261 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1262 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1263 | Replace oil buffers | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1264 | Remove window sill - 1st floor | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1265 | Replace compensation guidance system per dwgs | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1266 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1267 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1268 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1269 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1270 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1271 | Wire brush sills and support (at the first floor only) | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1272 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1273 | Replace pit lights and outlets | 3000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1274 | Replace all pit stop switches and light switches | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1275 | Remove Existing Ramp - 1st floor | 80000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1276 | Repair/replace pit access doors and hardware | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1277 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1278 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1279 | Clean and paint buffer inspection ladders | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1280 | Clean out pit of all dirt and debris | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1281 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 173 - OG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1282 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 10206.75 |  |  | 10206.75 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
1283 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 550 | 440 |  |  | 440 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 80% | Vital | Kurston | FALSE | FALSE | TRUE
1284 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 825 |  |  | 825 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
1285 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2860 | 1430 |  |  | 1430 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
1286 | Existing Ramp railing to be be removed - 1st fllor | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 015 - SG2 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1287 | HANGERS AND SUPPORTS | 11541 | 11541 |  |  | 11541 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 100% | Vital | Kurston | FALSE | FALSE | TRUE
1288 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1289 | DOMESTIC WATER PIPING | 120919 | 120919 |  |  | 120919 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 100% | Vital | Kurston | FALSE | FALSE | TRUE
1290 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 12210 |  |  | 12210 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
1291 | SANITARY WASTE PIPING | 111989 | 89591.2 |  |  | 89591.2 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 80% | Vital | Kurston | FALSE | FALSE | TRUE
1292 | SANITARY WASTE PIPING SPECIALTIES | 30069 | 27062.1 |  |  | 27062.1 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
1293 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 16500 |  |  | 16500 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
1294 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 186998 | 56099.4 |  |  | 56099.4 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 30% | Vital | Kurston | FALSE | FALSE | TRUE
1295 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 4821.3 |  |  | 4821.3 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 | Material on site | 90% | Vital | Kurston | FALSE | FALSE | TRUE
1296 | Plumbing Pipe Insulation | 35464 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
1297 | FORM FLOOD BARRIER FOUNDATIONS - SG-2 | 33187 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 016 - SG2 - Division 3 |  | 0% | MLJ | Brian | FALSE | FALSE | TRUE
1298 | Heat Trace | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 174 - OG5 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1299 | Survey | 66000 | 66000 |  |  | 66000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1300 | Exhaust Fans: Furnish | 5280 | 5280 |  |  | 5280 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1301 | Exhaust Fans: Install | 17160 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1302 | Steam Unit Heaters: Furnish | 1100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1303 | Steam Unit Heaters: Install | 18700 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1304 | Condensate Return Unit: Furnish | 7700 | 7700 |  |  | 7700 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1305 | Condensate Return Unit: Install | 25300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1306 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1307 | Heating and Ventilation Unit: Install | 26400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1308 | DRILL & GROUT DOWELS - SG-2 | 3359 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 016 - SG2 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1309 | Steam Traps: Furnish | 2200 | 2200 |  |  | 2200 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1310 | Steam Traps: Install | 25300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1311 | Vacuum Pump Unit: Furnish | 17600 | 17600 |  |  | 17600 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1312 | Vacuum Pump Unit: Install | 28600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1313 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 350570 | 70114 |  |  | 70114 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 | Refer drawing | 20% | Welkin | Sully | FALSE | FALSE | TRUE
1314 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 451000 | 135300 |  |  | 135300 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 | Refer drawing + 10% for header on site but not installed | 30% | Welkin | Sully | FALSE | FALSE | TRUE
1315 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 220000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1316 | Mechanical Pipe: Hydrostatic Testing | 5830 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1317 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 38500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1318 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 77000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1319 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-2 | 25126 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 016 - SG2 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1320 | HVAC Ductwork: Testing & Balancing | 4400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1321 | Controls: Furnish and Install: Devices | 77000 | 34650 |  |  | 34650 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 45% | Welkin | Sully | FALSE | FALSE | TRUE
1322 | Controls: Furnish and Install: Controls Conduit | 44000 | 17600 |  |  | 17600 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 40% | Welkin | Sully | FALSE | FALSE | TRUE
1323 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1324 | Controls: Connect to Final Termination Points | 8800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1325 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1326 | Insulation: Furnish and Install: Ductwork Insulation | 22000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1327 | Insulation: Furnish and Install: Piping Insulation | 44000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1328 | Insulation: Furnish and Install: Equipment Insulation | 22000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 175 - OG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1329 | ATS Energization | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1330 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-2 | 25018 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 016 - SG2 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1331 | ATS Installation | 153300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1332 | ATS Terminations | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1333 | ATS Testing | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1334 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 6843.75 |  |  | 6843.75 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 25% | Five Star | Kurston | FALSE | FALSE | TRUE
1335 | Cabling - Interior Branch (1/0 & Smaller) | 125000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1336 | Cabling - Risers & Feeders (2/0 & Larger) | 492750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1337 | Conduit - Branch Circuits (1 1/2" & Smaller) | 232688 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1338 | Conduit - Risers (2" & Larger) | 492750 | 73912.5 |  |  | 73912.5 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 15% | Five Star | Kurston | FALSE | FALSE | TRUE
1339 | Demolition/Temp Light & Power | 54750 | 21900 |  |  | 21900 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 40% | Five Star | Kurston | FALSE | FALSE | TRUE
1340 | Firestopping | 5250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1341 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-2 | 24855 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 016 - SG2 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1342 | Foundation Coring | 21000 | 21000 |  |  | 21000 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
1343 | Lighting Controls | 32550 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1344 | Lighting Remove & Re-install | 39420 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1345 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1346 | Mechanical Terminations(Dampers, Heaters, Motors) | 65700 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1347 | Survey | 65700 | 65700 |  |  | 65700 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
1348 | Switches and Receptacles | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1349 | Switchgear & Panelboard Energization | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1350 | Switchgear & Panelboard Installation | 366300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1351 | Switchgear & Panelboard Terminations | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1352 | Footing/Pier | 11409 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 016 - SG2 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1353 | Switchgear & Panelboard Testing | 30113 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 176 - OG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1354 | Fire Alarm Conduit | 21900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 177 - OG5 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1355 | Fire Alarm Wiring | 19710 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 177 - OG5 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1356 | Fire Alarm Devices | 20805 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 177 - OG5 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1357 | Fire Alarm Programming & Pretest | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 177 - OG5 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1358 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 177 - OG5 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1359 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-5 | 11300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 178 - OG5 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1360 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-5 | 3981 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 178 - OG5 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1361 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-5 | 1181 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | O- OG5 | 178 - OG5 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1362 | Gaskets | 58500 | 43875 |  |  | 43875 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 75% | ATCO | Kurston | FALSE | FALSE | TRUE
1363 | Retaining Walls | 3047 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 016 - SG2 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1364 | Wire Insulation | 75000 | 75000 |  |  | 75000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
1365 | Assumed Flooring Material (Slab Penetrations) | 64800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1366 | Pipe Insulation | 90720 | 90720 |  |  | 90720 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
1367 | Duct Seal | 3600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1368 | Asbestos Panels | 37500 | 37500 |  |  | 37500 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 | External panels at overhang | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
1369 | Fibrous Slate | 14280 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1370 | Waterproofing | 9942 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
1371 | Underground Utility Materials | 11388 | 11388 |  |  | 11388 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 | Materials on site | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
1372 | Remove existing paint and plaster - cellar and basement | 60000 | 48000 |  |  | 48000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 80% | MLJ | Kurston | FALSE | FALSE | TRUE
1373 | Remove sump pump - cellar | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1374 | Entrance Slab | 17178 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 016 - SG2 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1375 | Remove existing vent / window and frame- cellar and basement | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1376 | Remove existing door, frame and hardware - basement | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1377 | Remove Areaway slab and drain - basement | 60000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 10% | MLJ | Ricky | FALSE | FALSE | TRUE
1378 | Remove Areaway grate - cellar and basement | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1379 | Sawcut and remove portion of areaway wall - basement | 60000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1380 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1381 | Remove existing AC units and sleeves - 1st floor | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1382 | Remove window sill - 1st floor | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1383 | Sawcut slab opening for mechanical - 1st floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1384 | Remove floor finish - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1385 | Concrete Shelf | 5241 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 016 - SG2 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1386 | Remove stove - 2nd floor | 4000 | 4000 |  |  | 4000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1387 | Remove CMU wall - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1388 | Remove sinks - 2nd floor | 4000 | 4000 |  |  | 4000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1389 | Remove interior walls - 2nd floor | 40000 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1390 | Patch floor and make smooth - 2nd floor | 20000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1391 | Cut openings in slab - 2nd floor | 40000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 0% | MLJ | RIcky | FALSE | FALSE | TRUE
1392 | Remove existing windows - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1393 | Remove appliances - 2nd floor | 6000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1394 | Remove ceiling finishes - 2nd floor | 20000 | 20000 |  |  | 20000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1395 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 179 - OG6 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
1396 | New Concrete Curb Next to Existing Wall | 297 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 016 - SG2 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1397 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - OG-6 | 196219 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 | 25% for boiler room wall | 0% | MLJ | Brian | FALSE | FALSE | TRUE
1398 | DRILL & GROUT DOWELS - OG-6 | 42646 | 4264.6 |  |  | 4264.6 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 | for curb wall | 10% | MLJ | Ricky | FALSE | FALSE | TRUE
1399 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-6 | 57788 | 14447 |  |  | 14447 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 |  | 25% | MLJ | Ricky | FALSE | FALSE | TRUE
1400 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-6 | 56948 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1401 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-6 | 11142 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1402 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-6 | 3927 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1403 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-6 | 50274 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1404 | Footing/Pier | 13845 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1405 | Retaining Walls | 1275 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1406 | Entrance Slab | 23358 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1407 | GFRP Sikawrap 100 G | 44616 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 016 - SG2 - Division 3 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1408 | Concrete Shelf | 5472 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1409 | New Concrete Curb Next to Existing Wall | 234 | 234 |  |  | 234 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1410 | Boiler Room Walls | 18288 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1411 | GFRP Sikawrap 100 G | 32604 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 180 - OG6 - Division 3 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1412 | Overhead protection for Masonry | 15262 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 181 - OG6 - Division 4 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1413 | 6" vertically reinforced CMU | 34760 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 181 - OG6 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1414 | 2" Face brick | 161546 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 181 - OG6 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1415 | 2" rigid Insulation | 6083 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 181 - OG6 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1416 | Coping stone C1/A-300 | 12375 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 181 - OG6 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1417 | MATERIAL AND FABRICATION | 16765 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 182 - OG6 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1418 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-2 | 324 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 017 - SG2 - Division 4 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1419 | INSTALLATION | 19800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 182 - OG6 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1420 | Temporary Aluminum Over Pass Stairs | 28598 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 182 - OG6 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1421 | PENETRATION FIRESTOPPING EXTG BLDG - OG-6 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 183 - OG6 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1422 | JOINT SEALANTS EXTG BLDGS - OG 6 | 33516 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 183 - OG6 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1423 | Bituthene 4000 waterproofing membrane | 9485 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 183 - OG6 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1424 | GE Elemax 2600 Silicone air and vapor barrier | 18810 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 183 - OG6 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1425 | Crystalline Waterproofing at perimeter walls | 54338 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 183 - OG6 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
1426 | Waterproofing at foundation walls | 22080 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 183 - OG6 - Division 7 |  | 0% | DStar | Ricky | FALSE | FALSE | TRUE
1427 | ALUMINUM WINDOWS | 19222 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 184 - OG6 - Division 8 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1428 | Doors, Frames & Hardware - Labor | 17514 | 13135.5 |  |  | 13135.5 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 184 - OG6 - Division 8 |  | 75% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1429 | Overhead protection for Masonry | 5088 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 017 - SG2 - Division 4 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1430 | Furnish Doors | 14634 | 4829.22 |  |  | 4829.22 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 185 - OG6 - Division 9 |  | 33% | MLJ | Kurston | FALSE | FALSE | TRUE
1431 | Layout | 3858 | 3858 |  |  | 3858 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 185 - OG6 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1432 | Loading | 6686 | 6686 |  |  | 6686 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 185 - OG6 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1433 | Framing & Drywall - Materials | 11829 | 11829 |  |  | 11829 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 185 - OG6 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1434 | Framing- Labor | 12601 | 11340.9 |  |  | 11340.9 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 185 - OG6 - Division 9 |  | 90% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1435 | Drywall - Labor | 18260 | 16434 |  |  | 16434 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 185 - OG6 - Division 9 |  | 90% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1436 | Tape/ Spackle finishes | 11829 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 185 - OG6 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1437 | Stucco | 10183 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 185 - OG6 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1438 | Resilient Flooring and base - OG-6 | 15640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 185 - OG6 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | FALSE | TRUE
1439 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-6 | 111178 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 186 - OG6 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1440 | 6" vertically reinforced CMU | 125840 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 017 - SG2 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1441 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-6 | 63427 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 186 - OG6 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1442 | Temporary Egress Stair Storage Sign | 2640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 186 - OG6 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1443 | Address Signs | 4950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 186 - OG6 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1444 | Clean and refurbish landing device components in the pit | 4000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1445 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1446 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1447 | Replace oil buffers | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1448 | Replace compensation guidance system per dwgs | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1449 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1450 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1451 | 2" Face brick | 357280 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 017 - SG2 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1452 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1453 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1454 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1455 | Wire brush sills and support (at the first floor only) | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1456 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1457 | Replace pit lights and outlets | 3000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1458 | Replace all pit stop switches and light switches | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1459 | Repair/replace pit access doors and hardware | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1460 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1461 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1462 | 2" rigid Insulation | 18876 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 017 - SG2 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1463 | Clean and paint buffer inspection ladders | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1464 | Clean out pit of all dirt and debris | 2000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1465 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 187 - OG6 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1466 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 8165.4 |  |  | 8165.4 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 60% | Vital | Kurston | FALSE | FALSE | TRUE
1467 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 2634 | 1317 |  |  | 1317 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
1468 | ESCUTCHEONS FOR PLUMBING PIPING | 1650 | 825 |  |  | 825 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
1469 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 4171 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1470 | HANGERS AND SUPPORTS | 11526 | 6715.6 |  |  | 6715.6 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 58.26% | Vital | Kurston | FALSE | FALSE | TRUE
1471 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1472 | DOMESTIC WATER PIPING | 195822 | 92000 |  |  | 92000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 46.98% | Vital | Kurston | FALSE | FALSE | TRUE
1473 | Coping Stone C1/A-300 | 30958 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 017 - SG2 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1474 | DOMESTIC WATER PIPING SPECIALTIES | 16279 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1475 | SANITARY WASTE PIPING | 37529 | 31899.65 |  |  | 31899.65 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 85% | Vital | Kurston | FALSE | FALSE | TRUE
1476 | SANITARY WASTE PIPING SPECIALTIES | 162217 | 145995.3 |  |  | 145995.3 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
1477 | STORM DRAINAGE PIPING SPECIALTIES | 53592 | 26796 |  |  | 26796 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
1478 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 231000 | 115500 |  |  | 115500 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
1479 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 13277 | 13277 |  |  | 13277 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 | Material on site | 100% | Vital | Kurston | FALSE | FALSE | TRUE
1480 | Plumbing Pipe Insulation | 35464 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
1481 | Heat Trace | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 188 - OG6 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1482 | Survey | 66000 | 66000 |  |  | 66000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1483 | Exhaust Fans: Furnish | 3960 | 3960 |  |  | 3960 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1484 | MATERIAL AND FABRICATION | 5824 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 018 - SG2 - Division 5 | There is no structrual steel for SG2; will bill in line with other existing buildings | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1485 | Exhaust Fans: Install | 12595 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1486 | Steam Unit Heaters: Furnish | 1100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1487 | Steam Unit Heaters: Install | 15400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1488 | Condensate Return Unit: Furnish | 7700 | 7700 |  |  | 7700 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1489 | Condensate Return Unit: Install | 22000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1490 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1491 | Heating and Ventilation Unit: Install | 23100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1492 | Steam Traps: Furnish | 2860 | 2860 |  |  | 2860 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1493 | Steam Traps: Install | 27500 | 14808.75 |  |  | 14808.75 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 53.85% | Welkin | Sully | FALSE | FALSE | TRUE
1494 | Vacuum Pump Unit: Furnish | 17600 | 17600 |  |  | 17600 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1495 | INSTALLATION | 6600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 018 - SG2 - Division 5 | There is no structrual steel for SG2; will bill in line with other existing buildings | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1496 | Vacuum Pump Unit: Install | 25300 | 6325 |  |  | 6325 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 25% | Welkin | Sully | FALSE | FALSE | TRUE
1497 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 263780 | 145079 |  |  | 145079 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 55% | Welkin | Sully | FALSE | FALSE | TRUE
1498 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 341000 | 170500 |  |  | 170500 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 50% | Welkin | Sully | FALSE | FALSE | TRUE
1499 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 165000 | 33000 |  |  | 33000 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 20% | Welkin | Sully | FALSE | FALSE | TRUE
1500 | Mechanical Pipe: Hydrostatic Testing | 5720 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1501 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 27500 | 24750 |  |  | 24750 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
1502 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 55000 | 49500 |  |  | 49500 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
1503 | HVAC Ductwork: Testing & Balancing | 3300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1504 | Controls: Furnish and Install: Devices | 71500 | 35750 |  |  | 35750 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 50% | Welkin | Sully | FALSE | FALSE | TRUE
1505 | Controls: Furnish and Install: Controls Conduit | 38500 | 36575 |  |  | 36575 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 95% | Welkin | Sully | FALSE | FALSE | TRUE
1506 | Temporary Aluminum Over Pass Stairs | 28598 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 018 - SG2 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1507 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1508 | Controls: Connect to Final Termination Points | 7700 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1509 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1510 | Insulation: Furnish and Install: Ductwork Insulation | 18150 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1511 | Insulation: Furnish and Install: Piping Insulation | 33000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1512 | Insulation: Furnish and Install: Equipment Insulation | 18150 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 189 - OG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1513 | ATS Energization | 13688 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1514 | ATS Installation | 191625 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1515 | ATS Terminations | 13688 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1516 | ATS Testing | 13688 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1517 | PENETRATION FIRESTOPPING EXTG BLDG - SG-2 | 11505 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 019 - SG2 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1518 | Bypass Connections (Misc Panels, Re-routes, etc) | 27750 | 6937.5 |  |  | 6937.5 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 25% | Five Star | Kurston | FALSE | FALSE | TRUE
1519 | Cabling - Interior Branch (1/0 & Smaller) | 136875 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1520 | Cabling - Risers & Feeders (2/0 & Larger) | 591300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1521 | Conduit - Branch Circuits (1 1/2" & Smaller) | 273750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1522 | Conduit - Risers (2" & Larger) | 689850 | 103477.5 |  |  | 103477.5 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 15% | Five Star | Kurston | FALSE | FALSE | TRUE
1523 | Demolition/Temp Light & Power | 55500 | 22200 |  |  | 22200 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 40% | Five Star | Kurston | FALSE | FALSE | TRUE
1524 | Firestopping | 5250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1525 | Foundation Coring | 21000 | 10500 |  |  | 10500 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 50% | Five Star | Kurston | FALSE | FALSE | TRUE
1526 | Lighting Controls | 49350 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1527 | Lighting Remove & Re-install | 40406 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1528 | JOINT SEALANTS EXTG BLDGS - SG-2 | 11505 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 019 - SG2 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1529 | Lighting System Program & Energize | 5550 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1530 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1531 | Survey | 65700 | 65700 |  |  | 65700 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
1532 | Switches and Receptacles | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1533 | Switchgear & Panelboard Energization | 32850 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1534 | Switchgear & Panelboard Installation | 492750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1535 | Switchgear & Panelboard Terminations | 32850 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1536 | Switchgear & Panelboard Testing | 32850 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 190 - OG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1537 | Fire Alarm Conduit | 27375 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 191 - OG6 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1538 | Fire Alarm Wiring | 24638 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 191 - OG6 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1539 | Bituthene 4000 waterproofing membrane | 16940 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 019 - SG2 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1540 | Fire Alarm Devices | 24090 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 191 - OG6 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1541 | Fire Alarm Programming & Pretest | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 191 - OG6 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1542 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 191 - OG6 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1543 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-6 | 19775 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 192 - OG6 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1544 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-6 | 6285 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 192 - OG6 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1545 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-6 | 1181 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | P- OG6 | 192 - OG6 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1546 | Caulk | 9000 | 9000 |  |  | 9000 | 03- RESAND: O'Dwyer Gardens | Q- OG7 | 193 - OG7 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
1547 | Fibrous Slate | 510 | 510 |  |  | 510 | 03- RESAND: O'Dwyer Gardens | Q- OG7 | 193 - OG7 - Division 2 |  | 100% | ATCO | Kurston | FALSE | FALSE | TRUE
1548 | Demo Existing Building/Temp Light & Power | 35150 | 35150 |  |  | 35150 | 03- RESAND: O'Dwyer Gardens | Q- OG7 | 194 - OG7 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
1549 | FORMWORK NEW BUILDING - OG-8 | 751900 | 751900 |  |  | 751900 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 195 - OG8 - Division 3 | foundation complete. Slab poured | 100% | MLJ | Brian | FALSE | FALSE | TRUE
1550 | GE Elemax 2600 Silicone air and vapor barrier | 18876 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 019 - SG2 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1551 | SET ANCHOR BOLTS FOR STEEL COLUMNS - OG-8 | 5411 | 5411 |  |  | 5411 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 195 - OG8 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1552 | POUR CONCRETE NEW BUILDINGS - OG-8 | 402192 | 382082.4 |  |  | 382082.4 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 195 - OG8 - Division 3 | roof remaining | 95% | MLJ | Ricky | FALSE | FALSE | TRUE
1553 | FINISH SLABS - OG-8 | 34800 | 11484 |  |  | 11484 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 195 - OG8 - Division 3 | plumbing shaft slab complete, 1st, 2nd and roof remain | 33% | MLJ | Ricky | FALSE | FALSE | TRUE
1554 | Footing/Pier | 80925 | 80925 |  |  | 80925 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 195 - OG8 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1555 | Grade Beams | 15788 | 15788 |  |  | 15788 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 195 - OG8 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1556 | Floor Slabs | 54000 | 40500 |  |  | 40500 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 195 - OG8 - Division 3 | roof remaining | 75% | Tonage | Ricky | FALSE | FALSE | TRUE
1557 | Equipment Pads | 3855 | 3855 |  |  | 3855 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 195 - OG8 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1558 | Foundation Walls | 8538 | 8538 |  |  | 8538 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 195 - OG8 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1559 | Concrete Stairs | 1122 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 195 - OG8 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
1560 | WWM-Slabs | 13163 | 9872.25 |  |  | 9872.25 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 195 - OG8 - Division 3 | plumbing shaft slab complete, 1st, 2nd and roof remain | 75% | Tonage | Ricky | FALSE | FALSE | TRUE
1561 | Crystalline Waterproofing at perimeter walls | 32200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 019 - SG2 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
1562 | 8" CMU (3 hour rated) | 434720 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 196 - OG8 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1563 | 4" CMU | 151404 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 196 - OG8 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1564 | 6" CMU (2 hour rated) | 8910 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 196 - OG8 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1565 | Face Brick 3-5/8" | 373450 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 196 - OG8 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1566 | 3-1/8" Rigid insulation | 32010 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 196 - OG8 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1567 | Cast Stone with SS letters | 8650 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 196 - OG8 - Division 4 |  | 0% | S & D | Stefon | FALSE | FALSE | TRUE
1568 | Steel Channel | 23642 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1569 | Cont. Shelf angle | 12690 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1570 | STEEL (MATERIAL ONLY) | 245175 | 245175 |  |  | 245175 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1571 | FABRICATION COSTS | 338575 | 338575 |  |  | 338575 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1572 | Waterproofing at foundation walls | 17250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 019 - SG2 - Division 7 |  | 0% | DStar | Ricky | FALSE | FALSE | TRUE
1573 | METAL DECK (BUY-OUT) | 24518 | 24518 |  |  | 24518 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1574 | ANCHORS & EMBEDS | 11676 | 11676 |  |  | 11676 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1575 | SURVEYING | 17514 | 17514 |  |  | 17514 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1576 | STEEL & DECK ERECTION | 817248 | 817248 |  |  | 817248 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1577 | BOLTS AND HARDWARE | 23351 | 23351 |  |  | 23351 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1578 | TRUCKING | 11676 | 11676 |  |  | 11676 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1579 | Dunnage Grating Galvanized | 72626 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1580 | Dunnage Guard Rail | 32588 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1581 | Dunnage Stair and Railing (1) | 13242 | 3310.5 |  |  | 3310.5 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 25% | E&Y | Ricky | FALSE | FALSE | TRUE
1582 | Stair A: 1st, 2nd & 3rd Floor Stair and Landing with Hand & Guard Rail | 172065 | 172065 |  |  | 172065 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 100% | E&Y | Ricky | FALSE | FALSE | TRUE
1583 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-2 | 1200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 020 - SG2 - Division 8 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1584 | Stair B: Stair, Landing and Hand & Guard Rail | 81523 | 20380.75 |  |  | 20380.75 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 | Materials on site | 25% | E&Y | Ricky | FALSE | FALSE | TRUE
1585 | 1st to 2nd Floor Ship Ladder with Cage and Platform Landing | 27106 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1586 | Egress Stair: Stair & Landing with Hand & Guard Rail | 47590 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 197 - OG8 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1587 | Layout | 9195 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 198 - OG8 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1588 | Loading | 26857 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 198 - OG8 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1589 | Exterior Framing, Insulation & Drywall - Materials | 116188 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 198 - OG8 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1590 | Exterior Framing- Labor | 64809 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 198 - OG8 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1591 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG-8 | 24599 | 24599 |  |  | 24599 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1592 | PENETRATION FIRESTOPPING NEW BLDG - OG-8 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1593 | JOINT SEALANTS NEW BLDGS - OG-8 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1594 | Doors, Frames & Hardware - Labor | 7784 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 020 - SG2 - Division 8 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1595 | Air Film | 32010 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1596 | Insulation- Labor | 10399 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1597 | Crystalline Waterproofing at plumbing shaft | 10350 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
1598 | Waterproofing at foundation | 123540 | 123540 |  |  | 123540 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 | Waterproof concrete additive used for this item | 100% | DStar | Ricky | FALSE | FALSE | TRUE
1599 | Layout | 138040 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1600 | Framing | 328661 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1601 | Insulation | 58865 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1602 | Cladding Install | 412052 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1603 | Fireproofing | 66000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | SIG | Ricky | FALSE | FALSE | TRUE
1604 | P&I Cold Applied Roof Membrane | 151996 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
1605 | Furnish Doors | 2091 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 021 - SG2 - Division 9 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1606 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 160693 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
1607 | P&I Aluminum Coping | 9240 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 199 - OG8 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
1608 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG-8 | 14378 | 1437.8 |  |  | 1437.8 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 200 - OG8 - Division 8 | delivered | 10% | MLJ | Ricky | FALSE | FALSE | TRUE
1609 | Doors, Frames & Hardware - Labor | 35030 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 200 - OG8 - Division 8 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1610 | Louvers Install | 102778 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 200 - OG8 - Division 8 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1611 | Overhead Door | 16000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 200 - OG8 - Division 8 |  | 0% | Loading Dock | Ricky | FALSE | FALSE | TRUE
1612 | Furnish Doors | 37629 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 201 - OG8 - Division 9 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1613 | Sheathing & Drywall - Labor | 87184 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 201 - OG8 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1614 | Tape/ Spackle finishes | 41405 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 201 - OG8 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1615 | ACT ceilings - Materials | 1286 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 201 - OG8 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1616 | Layout | 2315 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 021 - SG2 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1617 | ACT ceilings - Labor | 3086 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 201 - OG8 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1618 | Direct Applied Stucco | 26335 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 201 - OG8 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1619 | Painting OG-8 | 110000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 201 - OG8 - Division 9 |  | 0% | GG Paint | Stefon | FALSE | FALSE | TRUE
1620 | Cermic Tile and Base - OG-8 | 5124 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 201 - OG8 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | FALSE | TRUE
1621 | FIRE EXTINGUISHERS NEW BLDGS - S8 | 1466 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 202 - OG8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1622 | TOILET ACCESSORIES NEW BLDGS - OG-8 | 2830 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 202 - OG8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1623 | Stair Identification Sign | 2750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 202 - OG8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1624 | Stairway Floor number and ID Sign | 2750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 202 - OG8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1625 | Room Sign | 4400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 202 - OG8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1626 | Exit Sign | 1650 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 202 - OG8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1627 | Loading | 3601 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 021 - SG2 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1628 | Public Unisex Toilet Sign | 550 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 202 - OG8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1629 | Stairway Flood Access Door | 550 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 202 - OG8 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1630 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 2070.4 |  |  | 2070.4 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 40% | Vital | Kurston | FALSE | FALSE | TRUE
1631 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 3960 |  |  | 3960 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
1632 | ESCUTCHEONS FOR PLUMBING PIPING | 2200 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1633 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 15180 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1634 | HANGERS AND SUPPORTS | 21784 | 3267.6 |  |  | 3267.6 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 15% | Vital | Kurston | FALSE | FALSE | TRUE
1635 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2739 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1636 | DOMESTIC WATER PIPING | 207347 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1637 | DOMESTIC WATER PIPING SPECIALTIES | 14344 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1638 | Framing & Drywall - Materials | 3858 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 021 - SG2 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1639 | SANITARY WASTE PIPING | 146824 | 36706 |  |  | 36706 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 25% | Vital | Kurston | FALSE | FALSE | TRUE
1640 | SANITARY WASTE PIPING SPECIALTIES | 29738 | 25277.3 |  |  | 25277.3 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 85% | Vital | Kurston | FALSE | FALSE | TRUE
1641 | STORM DRAINAGE PIPING SPECIALTIES | 73736 | 18434 |  |  | 18434 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 25% | Vital | Kurston | FALSE | FALSE | TRUE
1642 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 16368 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1643 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 240768 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1644 | GAS SERVICE AND PIPING | 398429 | 39842.9 |  |  | 39842.9 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 10% | Vital | Kurston | FALSE | FALSE | TRUE
1645 | PLUMBING FIXTURES | 18392 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1646 | EMERGENCY PLUMBING FIXTURES | 5104 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1647 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 15101 | 13590.9 |  |  | 13590.9 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
1648 | Plumbing Pipe Insulation | 8895 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
1649 | Framing- Labor | 5658 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 021 - SG2 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1650 | Heat Trace | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 203 - OG8 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1651 | Survey | 66000 | 66000 |  |  | 66000 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 | Drawings Submitted | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1652 | Exhaust Fans: Furnish | 7920 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1653 | Exhaust Fans: Install | 40040 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1654 | Steam Unit Heaters: Furnish | 8800 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1655 | Steam Unit Heaters: Install | 85250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1656 | Electric Heaters: Furnish | 5500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1657 | Condensate Return Unit: Furnish | 15400 | 15400 |  |  | 15400 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1658 | Condensate Return Unit: Install | 58850 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1659 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1660 | Drywall - Labor | 5401 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 021 - SG2 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1661 | Heating and Ventilation Unit: Install | 46750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1662 | Steam Traps: Furnish | 3960 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1663 | Steam Traps: Install | 50600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1664 | Steam Separator: Furnish | 52800 | 26400 |  |  | 26400 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 50% | Welkin | Sully | FALSE | FALSE | TRUE
1665 | Steam Separator: Install | 384450 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1666 | Low Pressure Steam Boilers: Install | 208450 | 52112.5 |  |  | 52112.5 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 25% | Welkin | Sully | FALSE | FALSE | TRUE
1667 | Boiler Feed Unit: Furnish | 82500 | 82500 |  |  | 82500 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1668 | Boiler Feed Unit: Install | 54450 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1669 | Fuel Oil Pump: Furnish | 77000 | 77000 |  |  | 77000 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1670 | Fuel Oil Pump: Install | 54450 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1671 | Tape/ Spackle finishes | 4629 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 021 - SG2 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1672 | Fuel Oil Storage Tank: Furnish | 71500 | 71500 |  |  | 71500 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1673 | Fuel Oil Storage Tank: Install | 65450 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1674 | Rigging | 285450 | 285450 |  |  | 285450 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1675 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 719400 | 71940 |  |  | 71940 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 10% | Welkin | Sully | FALSE | FALSE | TRUE
1676 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 949300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1677 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 379500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1678 | Mechanical Pipe: Furnish and Install: Boiler Exhaust Material | 385000 | 30800 |  |  | 30800 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 8% | Welkin | Sully | FALSE | FALSE | TRUE
1679 | Mechanical Pipe: Hydrostatic Testing | 12100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1680 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 99000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1681 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 192500 | 57750 |  |  | 57750 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 30% | Welkin | Sully | FALSE | FALSE | TRUE
1682 | Stucco | 10183 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 021 - SG2 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1683 | HVAC Ductwork: Testing & Balancing | 11000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1684 | Controls: Furnish and Install: Devices | 275000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1685 | Controls: Furnish and Install: Controls Conduit | 121000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1686 | Controls: Furnish and Install: Controls Wiring | 33000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1687 | Controls: Connect to Final Termination Points | 22000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1688 | Controls: Controls Testing | 19030 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1689 | Insulation: Furnish and Install: Ductwork Insulation | 60500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1690 | Insulation: Furnish and Install: Piping Insulation | 126500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1691 | Insulation: Furnish and Install: Equipment Insulation | 60500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1692 | Furnish and Install: Chemical Feed Equipment | 10230 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1693 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-2 | 43236 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 022 - SG2 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1694 | Chemical Cleaning | 8250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 204 - OG8 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1695 | ATS Energization | 16425 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1696 | ATS Installation | 229950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1697 | ATS Terminations | 16425 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1698 | ATS Testing | 16425 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1699 | Cabling - Interior Branch (1/0 & Smaller) | 219000 | 54750 |  |  | 54750 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 25% | Five Star | Kurston | FALSE | FALSE | TRUE
1700 | Cabling - Risers & Feeders (2/0 & Larger) | 492750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1701 | Conduit - Branch Circuits (1 1/2" & Smaller) | 164250 | 41062.5 |  |  | 41062.5 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 25% | Five Star | Kurston | FALSE | FALSE | TRUE
1702 | Conduit - In-Slab | 216810 | 130086 |  |  | 130086 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 60% | Five Star | Kurston | FALSE | FALSE | TRUE
1703 | Conduit - Risers (2" & Larger) | 443475 | 221737.5 |  |  | 221737.5 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 50% | Five Star | Kurston | FALSE | FALSE | TRUE
1704 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - SG-2 | 31714 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 022 - SG2 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1705 | Firestopping | 5250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1706 | Generator Delivery | 78750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1707 | Generator Release | 472500 | 472500 |  |  | 472500 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
1708 | Generator Terminations | 78750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1709 | Generator Test | 78750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1710 | Lighting Controls | 14700 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1711 | Lighting Install | 144900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1712 | Lighting Rough | 151110 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1713 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1714 | Lightning Protection | 21900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1715 | WINDOW FLOODGATES (8.06 AND 8.14) - SG-2 | 80599 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 022 - SG2 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1716 | Mechanical Terminations(Dampers, Heaters, Motors) | 164250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1717 | Survey | 54750 | 54750 |  |  | 54750 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
1718 | Switches and Receptacles | 21900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1719 | Switchgear & Panelboard Energization | 24638 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1720 | Switchgear & Panelboard Installation | 295650 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1721 | Switchgear & Panelboard Terminations | 24638 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1722 | Switchgear & Panelboard Testing | 24638 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1723 | Temp Light & Power | 54750 | 27375 |  |  | 27375 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 205 - OG8 - Division 26 |  | 50% | Five Star | Kurston | FALSE | FALSE | TRUE
1724 | Fire Alarm Conduit | 68438 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 206 - OG8 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1725 | Fire Alarm Wiring | 65700 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 206 - OG8 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1726 | Temporary Egress Stair Storage Sign | 1320 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 022 - SG2 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1727 | Fire Alarm Devices | 140160 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 206 - OG8 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1728 | Fire Alarm Programming & Pretest | 2750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 206 - OG8 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1729 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 206 - OG8 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1730 | EXCAVATION NEW BLDGS - OG-8 | 86240 | 86240 |  |  | 86240 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 207 - OG8 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1731 | BACKFILL NEW BLDGS - OG-8 | 36868 | 35024.6 |  |  | 35024.6 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 207 - OG8 - Division 31 |  | 95% | MLJ | Ricky | FALSE | FALSE | TRUE
1732 | DEWATERING COVERAGE FOR NEW BUILDINGS - OG-8 | 42088 | 42088 |  |  | 42088 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 207 - OG8 - Division 31 | no more dewatering required for building | 100% | MLJ | Brian | FALSE | FALSE | TRUE
1733 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG-8 | 27148 | 27148 |  |  | 27148 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 207 - OG8 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1734 | DRIVE PILES AND INSTALL LAGGING FOR SOE - OG-8 | 68282 | 68282 |  |  | 68282 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 207 - OG8 - Division 31 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
1735 | STONE FOR FOUNDATION - OG-8 | 7221 | 7221 |  |  | 7221 | 03- RESAND: O'Dwyer Gardens | R- OG8 | 207 - OG8 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1736 | FORMWORK NEW BUILDING - OG-9 | 215221 | 215221 |  |  | 215221 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 208 - OG9 - Division 3 | Below ground and inteior of shaft complete, exterior of shaft remains | 100% | MLJ | Brian | FALSE | FALSE | TRUE
1737 | Address Signs | 4950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 022 - SG2 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1738 | SET ANCHOR BOLTS FOR STEEL COLUMNS - OG-9 | 5411 | 5411 |  |  | 5411 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 208 - OG9 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1739 | POUR CONCRETE NEW BUILDINGS - OG-9 | 102272 | 102272 |  |  | 102272 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 208 - OG9 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1740 | FINISH SLABS - OG-9 | 10493 | 10493 |  |  | 10493 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 208 - OG9 - Division 3 | 1st floor complete, 2nd and roof remain | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1741 | Footing/Pier | 38922 | 38922 |  |  | 38922 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 208 - OG9 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1742 | Grade Beams | 11369 | 11369 |  |  | 11369 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 208 - OG9 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1743 | Floor Slabs | 15984 | 15984 |  |  | 15984 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 208 - OG9 - Division 3 | 1st floor complete, 2nd and roof remain | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1744 | Equipment Pads | 106 | 106 |  |  | 106 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 208 - OG9 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1745 | Second Floor Plumbing Shaft Slab | 528 | 528 |  |  | 528 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 208 - OG9 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1746 | Plumbing Shafts | 23767 | 23767 |  |  | 23767 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 208 - OG9 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1747 | WWM-Slabs | 5262 | 5262 |  |  | 5262 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 208 - OG9 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1748 | Clean and refurbish landing device components in the pit | 4000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1749 | 8" CMU (3 hour rated) | 101420 | 40000 |  |  | 40000 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 209 - OG9 - Division 4 |  | 39.44% | Faxa | Ricky | FALSE | FALSE | TRUE | 0%
1750 | 4" CMU | 13860 | 5544 |  |  | 5544 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 209 - OG9 - Division 4 |  | 40% | Faxa | Ricky | FALSE | FALSE | TRUE | 0%
1751 | 6" CMU (2 hour rated) | 51414 | 20565.6 |  |  | 20565.6 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 209 - OG9 - Division 4 |  | 40% | Faxa | Ricky | FALSE | FALSE | TRUE | 0%
1752 | Face Brick 3-5/8" | 99578 | 9957.8 |  |  | 9957.8 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 209 - OG9 - Division 4 | 25% for half materials on site | 10% | Faxa | Ricky | FALSE | FALSE | TRUE | 0%
1753 | 3-1/8" Rigid insulation | 8415 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 209 - OG9 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1754 | Cast Stone with SS letters | 142454 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 209 - OG9 - Division 4 |  | 0% | S & D | Stefon | FALSE | FALSE | TRUE
1755 | Steel Channel | 24020 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1756 | Cont. Shelf angle | 11330 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1757 | STEEL (MATERIAL ONLY) | 101945 | 101945 |  |  | 101945 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1758 | FABRICATION COSTS | 173771 | 173771 |  |  | 173771 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1759 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1760 | METAL DECK (BUY-OUT) | 7531 | 7531 |  |  | 7531 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1761 | ANCHORS & EMBEDS | 6951 | 6951 |  |  | 6951 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1762 | SURVEYING | 9848 | 9848 |  |  | 9848 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1763 | STEEL & DECK ERECTION | 347540 | 347540 |  |  | 347540 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1764 | BOLTS AND HARDWARE | 6951 | 6951 |  |  | 6951 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1765 | TRUCKING | 5793 | 5793 |  |  | 5793 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1766 | Dunnage Grating | 23588 | 23588 |  |  | 23588 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 100% | E&Y | Ricky | FALSE | FALSE | TRUE
1767 | Railing | 11768 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1768 | Dunnage Stair and Railing | 17380 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1769 | Stair B: First Floor to Roof with Landing and Hand & Guard Rail | 141827 | 141827 |  |  | 141827 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 100% | E&Y | Ricky | FALSE | FALSE | TRUE
1770 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1771 | 1st to 2nd Floor Ship Ladder with Safety Cage and Landing Platform with Rail | 25036 | 2503.6 |  |  | 2503.6 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 10% | E&Y | Ricky | FALSE | FALSE | TRUE
1772 | Ship Ladder Bulkhead Roof | 7035 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 210 - OG9 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1773 | Layout | 3065 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 211 - OG9 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1774 | Loading | 10218 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 211 - OG9 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1775 | Exterior Framing, Insulation & Drywall - Materials | 37221 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 211 - OG9 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1776 | Exterior Framing- Labor | 56196 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 211 - OG9 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1777 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG-9 | 10055 | 10055 |  |  | 10055 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 | Blue insulation around shaft | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1778 | PENETRATION FIRESTOPPING NEW BLDG - OG-9 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1779 | JOINT SEALANTS NEW BLDGS - OG-9 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1780 | Air Film | 8415 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1781 | Replace oil buffers | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1782 | Insulation- Labor | 2906 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1783 | Crystalline Waterproofing at plumbing shaft | 3738 | 3738 |  |  | 3738 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 100% | Dstar | Ricky | FALSE | FALSE | TRUE
1784 | Waterproofing at foundation | 43413 | 43413 |  |  | 43413 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 | Waterproof concrete additive used for this item | 100% | DStar | Ricky | FALSE | FALSE | TRUE
1785 | Layout | 55016 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1786 | Framing | 114716 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1787 | Insulation | 20546 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1788 | Cladding Install | 143823 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1789 | Fireproofing | 29700 | 24000 |  |  | 24000 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 80.81% | SIG | Ricky | FALSE | FALSE | TRUE
1790 | P&I Cold Applied Roof Membrane | 54257 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
1791 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 69054 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
1792 | Replace compensation guidance system per dwgs | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1793 | P&I Aluminum Coping | 6592 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 212 - OG9 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
1794 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG-9 | 12324 | 1232.4 |  |  | 1232.4 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 213 - OG9 - Division 8 | delivered | 10% | MLJ | Ricky | FALSE | FALSE | TRUE
1795 | Doors, Frames & Hardware - Labor | 17514 | 6000 |  |  | 6000 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 213 - OG9 - Division 8 |  | 34.26% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1796 | Louvers Install | 35874 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 213 - OG9 - Division 8 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1797 | Furnish Doors | 22996 | 11000 |  |  | 11000 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 214 - OG9 - Division 9 |  | 47.83% | MLJ | Kurston | FALSE | FALSE | TRUE
1798 | Sheathing & Drywall - Labor | 18774 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 214 - OG9 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1799 | Tape/ Spackle finishes | 9258 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 214 - OG9 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1800 | ACT ceilings - Materials | 2058 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 214 - OG9 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1801 | ACT ceilings - Labor | 4372 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 214 - OG9 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1802 | Direct Applied Stucco | 13167 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 214 - OG9 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1803 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1804 | Painting OG-9 | 110000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 214 - OG9 - Division 9 |  | 0% | GG Paint | Stefon | FALSE | FALSE | TRUE
1805 | Cermic Tile and Base - OG-9 | 7198 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 214 - OG9 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | FALSE | TRUE
1806 | TOILET ACCESSORIES NEW BLDGS - OG-9 | 2830 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 215 - OG9 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1807 | Stair Identification Sign | 2750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 215 - OG9 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1808 | Stairway Floor number and ID Sign | 2750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 215 - OG9 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1809 | Room Sign | 1650 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 215 - OG9 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1810 | Exit Sign | 550 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 215 - OG9 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1811 | Public Unisex Toilet Sign | 550 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 215 - OG9 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1812 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 2070.4 |  |  | 2070.4 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 40% | Vital | Kurston | FALSE | FALSE | TRUE
1813 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 3960 |  |  | 3960 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
1814 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1815 | ESCUTCHEONS FOR PLUMBING PIPING | 2200 | 550 |  |  | 550 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 25% | Vital | Kurston | FALSE | FALSE | TRUE
1816 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 14740 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1817 | HANGERS AND SUPPORTS | 21930 | 10965 |  |  | 10965 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
1818 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2739 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1819 | DOMESTIC WATER PIPING | 169254 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1820 | DOMESTIC WATER PIPING SPECIALTIES | 3432 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1821 | SANITARY WASTE PIPING | 128128 | 115315.2 |  |  | 115315.2 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
1822 | SANITARY WASTE PIPING SPECIALTIES | 19050 | 19050 |  |  | 19050 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 100% | Vital | Kurston | FALSE | FALSE | TRUE
1823 | STORM DRAINAGE PIPING SPECIALTIES | 41052 | 36946.8 |  |  | 36946.8 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
1824 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 10120 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1825 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1826 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 240768 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1827 | GAS SERVICE AND PIPING | 224774 | 11238.7 |  |  | 11238.7 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 5% | Vital | Kurston | FALSE | FALSE | TRUE
1828 | PLUMBING FIXTURES | 14167 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1829 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 38500 | 38500 |  |  | 38500 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 100% | Vital | Kurston | FALSE | FALSE | TRUE
1830 | Plumbing Pipe Insulation | 3175 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
1831 | Heat Trace | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 216 - OG9 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1832 | Survey | 66000 | 66000 |  |  | 66000 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 | Drawings Submitted | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1833 | Exhaust Fans: Furnish | 6600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1834 | Exhaust Fans: Install | 21725 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1835 | Electric Unit Heaters: Furnish | 2750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1836 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1837 | Steam Unit Heater: Furnish | 5500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1838 | Steam Unit Heater: Install | 48400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1839 | Condensate Return Unit: Furnish | 7700 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1840 | Condensate Return Unit: Install | 28600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1841 | Steam Traps: Furnish | 660 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1842 | Steam Traps: Install | 11000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1843 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 181775 | 99976.25 |  |  | 99976.25 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 55% | Welkin | Sully | FALSE | FALSE | TRUE
1844 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 212850 | 117067.5 |  |  | 117067.5 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 55% | Welkin | Sully | FALSE | FALSE | TRUE
1845 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 100650 | 20130 |  |  | 20130 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 20% | Welkin | Sully | FALSE | FALSE | TRUE
1846 | Mechanical Pipe: Hydrostatic Testing | 3025 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1847 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1848 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 18975 | 17077.5 |  |  | 17077.5 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
1849 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 38500 | 34650 |  |  | 34650 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
1850 | HVAC Ductwork: Testing & Balancing | 2200 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1851 | Controls: Furnish and Install: Devices | 99000 | 11880 |  |  | 11880 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 12% | Welkin | Sully | FALSE | FALSE | TRUE
1852 | Controls: Furnish and Install: Controls Conduit | 38500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1853 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1854 | Controls: Connect to Final Termination Points | 7700 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1855 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1856 | Insulation: Furnish and Install: Ductwork Insulation | 12100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1857 | Insulation: Furnish and Install: Piping Insulation | 25300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1858 | Wire brush sills and support (at the first floor only) | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1859 | Insulation: Furnish and Install: Equipment Insulation | 12100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 217 - OG9 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1860 | ATS Energization | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1861 | ATS Installation | 153300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1862 | ATS Terminations | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1863 | ATS Testing | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1864 | Cabling - Interior Branch (1/0 & Smaller) | 75000 | 7500 |  |  | 7500 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 10% | Five Star | Kurston | FALSE | FALSE | TRUE
1865 | Cabling - Risers & Feeders (2/0 & Larger) | 354780 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1866 | Conduit - Branch Circuits (1 1/2" & Smaller) | 83250 | 59950 |  |  | 59950 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 72.01% | Five Star | Kurston | FALSE | FALSE | TRUE
1867 | Conduit - In-Slab | 126473 | 126473 |  |  | 126473 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
1868 | Conduit - Risers (2" & Larger) | 299700 | 274715 |  |  | 274715 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 91.66% | Five Star | Kurston | FALSE | FALSE | TRUE
1869 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1870 | Firestopping | 5250 | 1312.5 |  |  | 1312.5 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 25% | Five Star | Kurston | FALSE | FALSE | TRUE
1871 | Generator Delivery | 52500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1872 | Generator Release | 315000 | 315000 |  |  | 315000 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
1873 | Generator Terminations | 52500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1874 | Generator Test | 52500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1875 | Lighting Controls | 8400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1876 | Lighting Install | 71820 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1877 | Lighting Rough | 74898 | 56173.5 |  |  | 56173.5 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 75% | Five Star | Kurston | FALSE | FALSE | TRUE
1878 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1879 | Lightning Protection | 21900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1880 | Replace pit lights and outlets | 3000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1881 | Mechanical Terminations(Dampers, Heaters, Motors) | 66600 | 9990 |  |  | 9990 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 15% | Five Star | Kurston | FALSE | FALSE | TRUE
1882 | Survey | 54750 | 54750 |  |  | 54750 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
1883 | Switches and Receptacles | 10950 | 1642.5 |  |  | 1642.5 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 15% | Five Star | Kurston | FALSE | FALSE | TRUE
1884 | Switchgear & Panelboard Energization | 19163 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1885 | Switchgear & Panelboard Installation | 229950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1886 | Switchgear & Panelboard Terminations | 19163 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1887 | Switchgear & Panelboard Testing | 19425 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1888 | Temp Light & Power | 54750 | 21900 |  |  | 21900 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 218 - OG9 - Division 26 |  | 40% | Five Star | Kurston | FALSE | FALSE | TRUE
1889 | Fire Alarm Conduit | 27375 | 6843.75 |  |  | 6843.75 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 219 - OG9 - Division 28 |  | 25% | Five Star | Kurston | FALSE | FALSE | TRUE
1890 | Fire Alarm Wiring | 24638 | 2463.8 |  |  | 2463.8 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 219 - OG9 - Division 28 |  | 10% | Five Star | Kurston | FALSE | FALSE | TRUE
1891 | Replace all pit stop switches and light switches | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1892 | Fire Alarm Devices | 36135 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 219 - OG9 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1893 | Fire Alarm Programming & Pretest | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 219 - OG9 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1894 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 219 - OG9 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1895 | EXCAVATION NEW BLDGS - OG-9 | 70840 | 70840 |  |  | 70840 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 220 - OG9 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1896 | BACKFILL NEW BLDGS - OG-9 | 37706 | 37706 |  |  | 37706 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 220 - OG9 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1897 | DEWATERING COVERAGE FOR NEW BUILDINGS - OG-9 | 42088 | 42088 |  |  | 42088 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 220 - OG9 - Division 31 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
1898 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG-9 | 27148 | 27148 |  |  | 27148 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 220 - OG9 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1899 | STONE FOR FOUNDATION - OG-9 | 7221 | 7221 |  |  | 7221 | 03- RESAND: O'Dwyer Gardens | S- OG9 | 220 - OG9 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1900 | FORMWORK NEW BUILDING - OG-10 | 202716 | 202716 |  |  | 202716 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 221 - OG10 - Division 3 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
1901 | SET ANCHOR BOLTS FOR STEEL COLUMNS - OG-10 | 5411 | 5411 |  |  | 5411 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 221 - OG10 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1902 | Repair/replace pit access doors and hardware | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1903 | POUR CONCRETE NEW BUILDINGS - OG-10 | 123339 | 123339 |  |  | 123339 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 221 - OG10 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1904 | FINISH SLABS - OG-10 | 13020 | 13020 |  |  | 13020 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 221 - OG10 - Division 3 | shaft and 1st floor poured, 2nd and roof remain | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1905 | Footing/Pier | 49491 | 49491 |  |  | 49491 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 221 - OG10 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1906 | Grade Beams | 10811 | 10811 |  |  | 10811 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 221 - OG10 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1907 | Floor Slabs | 22032 | 22032 |  |  | 22032 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 221 - OG10 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1908 | First Floor Plumbing Shaft Slab | 1848 | 1848 |  |  | 1848 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 221 - OG10 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1909 | Second Floor Plumbing Shaft Slab | 792 | 792 |  |  | 792 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 221 - OG10 - Division 3 |  | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1910 | Plumbing Shafts | 25269 | 25269 |  |  | 25269 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 221 - OG10 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1911 | WWM-Slabs | 4869 | 4869 |  |  | 4869 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 221 - OG10 - Division 3 | shaft and 1st floor poured, 2nd and roof remain | 100% | Tonage | Ricky | FALSE | FALSE | TRUE
1912 | 8" CMU (3 hour rated) | 112024 | 5000 |  |  | 5000 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 222 - OG10 - Division 4 | 50% for materials on site | 4.463% | Faxa | Ricky | FALSE | FALSE | TRUE | 0%
1913 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1914 | 6" CMU (2 hour rated) | 140624 | 2000 |  |  | 2000 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 222 - OG10 - Division 4 | 50% for materials on site | 1.422% | Faxa | Ricky | FALSE | FALSE | TRUE | 0%
1915 | 4" CMU | 39688 | 1000 |  |  | 1000 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 222 - OG10 - Division 4 | 50% for materials on site | 2.52% | Faxa | Ricky | FALSE | FALSE | TRUE | 0%
1916 | Face Brick 3-5/8" | 93486 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 222 - OG10 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1917 | 3-1/8" Rigid insulation | 7901 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 222 - OG10 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1918 | Cast Stone with SS letters | 6487 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 222 - OG10 - Division 4 |  | 0% | S & D | Stefon | FALSE | FALSE | TRUE
1919 | Steel Channel | 24097 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1920 | Cont. Shelf angle | 12731 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1921 | STEEL (MATERIAL ONLY) | 102320 | 102320 |  |  | 102320 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1922 | FABRICATION COSTS | 226149 | 226149 |  |  | 226149 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1923 | METAL DECK (BUY-OUT) | 11629 | 11629 |  |  | 11629 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1924 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1925 | ANCHORS & EMBEDS | 6978 | 6978 |  |  | 6978 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1926 | SURVEYING | 9884 | 9884 |  |  | 9884 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1927 | STEEL & DECK ERECTION | 348817 | 348817 |  |  | 348817 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1928 | BOLTS AND HARDWARE | 6978 | 6978 |  |  | 6978 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1929 | TRUCKING | 6978 | 6978 |  |  | 6978 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
1930 | Dunnage Grating Galvanized | 19967 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1931 | Dunnage Stair with Guard Railing | 21932 | 21932 |  |  | 21932 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 100% | E&Y | Ricky | FALSE | FALSE | TRUE
1932 | Stair B: First Floor to Roof Stair and Landing with Hand & Guard Rail | 123974 | 61987 |  |  | 61987 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 50% | E&Y | Ricky | FALSE | FALSE | TRUE
1933 | Ship Ladder First Floor to Second Floor with Cage and Upper Platform | 16760 | 10894 |  |  | 10894 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 65% | E&Y | Ricky | FALSE | FALSE | TRUE
1934 | Ship Ladder Bulkhead | 7035 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 223 - OG10 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
1935 | Clean and paint buffer inspection ladders | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1936 | Layout | 6292 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 224 - OG10 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1937 | Loading | 17370 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 224 - OG10 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1938 | Exterior Framing, Insulation & Drywall - Materials | 57656 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 224 - OG10 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1939 | Exterior Framing- Labor | 84514 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 224 - OG10 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1940 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG-10 | 12749 | 12749 |  |  | 12749 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
1941 | PENETRATION FIRESTOPPING NEW BLDG - OG-10 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1942 | JOINT SEALANTS NEW BLDGS - OG-10 | 11505 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
1943 | Air Film | 6584 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
1944 | Insulation- Labor | 4740 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1945 | Crystalline Waterproofing at plumbing shaft | 4888 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
1946 | Clean out pit of all dirt and debris | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1947 | Waterproofing at foundation walls | 49565 | 49565 |  |  | 49565 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 100% | DStar | Ricky | FALSE | FALSE | TRUE
1948 | Layout | 89238 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1949 | Framing | 202902 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1950 | Insulation | 36341 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1951 | Cladding Install | 254386 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1952 | Fireproofing | 37400 | 9000 |  |  | 9000 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 24.06% | SIG | Ricky | FALSE | FALSE | TRUE
1953 | P&I Cold Applied Roof Membrane | 48805 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
1954 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 59708 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
1955 | P&I Aluminum Coping | 6138 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 225 - OG10 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
1956 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG-10 | 8216 | 821.6 |  |  | 821.6 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 226 - OG10 - Division 8 | delivered | 10% | MLJ | Ricky | FALSE | FALSE | TRUE
1957 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 023 - SG2 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
1958 | Doors, Frames & Hardware - Labor | 18906 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 226 - OG10 - Division 8 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1959 | Louvers Install | 63452 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 226 - OG10 - Division 8 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
1960 | Furnish Doors | 25086 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 227 - OG10 - Division 9 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1961 | Sheathing & Drywall - Labor | 36519 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 227 - OG10 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1962 | Tape/ Spackle finishes | 14144 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 227 - OG10 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1963 | ACT ceilings - Materials | 3086 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 227 - OG10 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1964 | ACT ceilings - Labor | 14915 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 227 - OG10 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1965 | Direct Applied Stucco | 41559 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 227 - OG10 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
1966 | Painting OG-10 | 110000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 227 - OG10 - Division 9 |  | 0% | GG Paint | Stefon | FALSE | FALSE | TRUE
1967 | Cermic Tile and Base - OG-10 | 4636 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 227 - OG10 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | FALSE | TRUE
1968 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 6804.5 |  |  | 6804.5 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
1969 | TOILET ACCESSORIES NEW BLDGS - OG-10 | 2830 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 228 - OG10 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1970 | Stair Identification Sign | 1650 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 228 - OG10 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1971 | Stairway Floor number and ID Sign | 1650 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 228 - OG10 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1972 | Room Sign | 2750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 228 - OG10 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1973 | Public Unisex Toilet Sign | 550 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 228 - OG10 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
1974 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 1552.8 |  |  | 1552.8 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 30% | Vital | Kurston | FALSE | FALSE | TRUE
1975 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 2640 |  |  | 2640 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
1976 | ESCUTCHEONS FOR PLUMBING PIPING | 2200 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1977 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 18920 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1978 | HANGERS AND SUPPORTS | 21930 | 6579 |  |  | 6579 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 30% | Vital | Kurston | FALSE | FALSE | TRUE
1979 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1100 | 440 |  |  | 440 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 40% | Vital | Kurston | FALSE | FALSE | TRUE
1980 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2739 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1981 | DOMESTIC WATER PIPING | 219912 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1982 | DOMESTIC WATER PIPING SPECIALTIES | 30184 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1983 | DOMESTIC WATER PUMPING SYSTEMS | 82500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1984 | SANITARY WASTE PIPING | 131989 | 26397.8 |  |  | 26397.8 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 20% | Vital | Kurston | FALSE | FALSE | TRUE
1985 | SANITARY WASTE PIPING SPECIALTIES | 20064 | 12000 |  |  | 12000 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 59.81% | Vital | Kurston | FALSE | FALSE | TRUE
1986 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 19800 |  |  | 19800 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 60% | Vital | Kurston | FALSE | FALSE | TRUE
1987 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 16368 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1988 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 240768 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1989 | GAS SERVICE AND PIPING | 244728 | 24472.8 |  |  | 24472.8 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 10% | Vital | Kurston | FALSE | FALSE | TRUE
1990 | ESCUTCHEONS FOR PLUMBING PIPING | 1096 | 548 |  |  | 548 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
1991 | PLUMBING FIXTURES | 18392 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
1992 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 31900 | 31900 |  |  | 31900 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 100% | Vital | Kurston | FALSE | FALSE | TRUE
1993 | Plumbing Pipe Insulation | 2317 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
1994 | Heat Trace | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 229 - OG10 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
1995 | Survey | 66000 | 66000 |  |  | 66000 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 | Drawings Submitted | 100% | Welkin | Sully | FALSE | FALSE | TRUE
1996 | Exhaust Fans: Furnish | 1320 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1997 | Exhaust Fans: Install | 17325 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1998 | Electric Unit Heaters: Furnish | 3850 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
1999 | Steam Unit Heater: Furnish | 4400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2000 | Steam Unit Heater: Install | 37400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2001 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2860 | 715 |  |  | 715 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 25% | Vital | Kurston | FALSE | FALSE | TRUE
2002 | Condensate Return Unit: Furnish | 7700 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2003 | Condensate Return Unit: Install | 24200 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2004 | Steam Traps: Furnish | 1320 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2005 | Steam Traps: Install | 11550 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2006 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 135795 | 74687.25 |  |  | 74687.25 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 55% | Welkin | Sully | FALSE | FALSE | TRUE
2007 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 154000 | 84700 |  |  | 84700 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 55% | Welkin | Sully | FALSE | FALSE | TRUE
2008 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 82500 | 20625 |  |  | 20625 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 25% | Welkin | Sully | FALSE | FALSE | TRUE
2009 | Mechanical Pipe: Hydrostatic Testing | 1705 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2010 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 13750 | 12375 |  |  | 12375 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
2011 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 27500 | 24750 |  |  | 24750 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
2012 | HANGERS AND SUPPORTS | 11509 | 9782.65 |  |  | 9782.65 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 85% | Vital | Kurston | FALSE | FALSE | TRUE
2013 | HVAC Ductwork: Testing & Balancing | 1650 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2014 | Controls: Furnish and Install: Devices | 99000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2015 | Controls: Furnish and Install: Controls Conduit | 38500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2016 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2017 | Controls: Connect to Final Termination Points | 7700 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2018 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2019 | Insulation: Furnish and Install: Ductwork Insulation | 12100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2020 | Insulation: Furnish and Install: Piping Insulation | 24200 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2021 | Insulation: Furnish and Install: Equipment Insulation | 12100 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 230 - OG10 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2022 | ATS Energization | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2023 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2024 | ATS Installation | 153300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2025 | ATS Terminations | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2026 | ATS Testing | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2027 | Cabling - Interior Branch (1/0 & Smaller) | 75000 | 15000 |  |  | 15000 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 20% | Five Star | Kurston | FALSE | FALSE | TRUE
2028 | Cabling - Risers & Feeders (2/0 & Larger) | 295650 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2029 | Conduit - Branch Circuits (1 1/2" & Smaller) | 82125 | 24637.5 |  |  | 24637.5 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 30% | Five Star | Kurston | FALSE | FALSE | TRUE
2030 | Conduit - In-Slab | 126473 | 126473 |  |  | 126473 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
2031 | Conduit - Risers (2" & Larger) | 315360 | 252288 |  |  | 252288 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 80% | Five Star | Kurston | FALSE | FALSE | TRUE
2032 | Firestopping | 5250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2033 | Generator Delivery | 52500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2034 | DOMESTIC WATER PIPING | 115682 | 98329.7 |  |  | 98329.7 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 85% | Vital | Kurston | FALSE | FALSE | TRUE
2035 | Generator Release | 315000 | 315000 |  |  | 315000 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
2036 | Generator Terminations | 52500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2037 | Generator Test | 52500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2038 | Lighting Controls | 21000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2039 | Lighting Install | 56700 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2040 | Lighting Rough | 59940 | 29970 |  |  | 29970 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 50% | Five Star | Kurston | FALSE | FALSE | TRUE
2041 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2042 | Lightning Protection | 21900 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2043 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2044 | Survey | 54750 | 54750 |  |  | 54750 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
2045 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 13838 |  |  | 13838 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 85% | Vital | Kurston | FALSE | FALSE | TRUE
2046 | Switches and Receptacles | 10950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2047 | Switchgear & Panelboard Energization | 19163 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2048 | Switchgear & Panelboard Installation | 229950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2049 | Switchgear & Panelboard Terminations | 19163 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2050 | Switchgear & Panelboard Testing | 19163 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2051 | Temp Light & Power | 54750 | 30112.5 |  |  | 30112.5 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 231 - OG10 - Division 26 |  | 55% | Five Star | Kurston | FALSE | FALSE | TRUE
2052 | Fire Alarm Conduit | 32850 | 4927.5 |  |  | 4927.5 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 232 - OG10 - Division 28 |  | 15% | Five Star | Kurston | FALSE | FALSE | TRUE
2053 | Fire Alarm Wiring | 32850 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 232 - OG10 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2054 | Fire Alarm Devices | 50370 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 232 - OG10 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2055 | Fire Alarm Programming & Pretest | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 232 - OG10 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2056 | SANITARY WASTE PIPING | 135432 | 115117.2 |  |  | 115117.2 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 85% | Vital | Kurston | FALSE | FALSE | TRUE
2057 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 232 - OG10 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2058 | EXCAVATION NEW BLDGS - OG-10 | 80696 | 80696 |  |  | 80696 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 233 - OG10 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
2059 | BACKFILL NEW BLDGS - OG-10 | 39801 | 39801 |  |  | 39801 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 233 - OG10 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
2060 | DEWATERING COVERAGE FOR NEW BUILDINGS - OG-10 | 42088 | 42088 |  |  | 42088 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 233 - OG10 - Division 31 | Building out of water table ,no more dewatering required | 100% | MLJ | Brian | FALSE | FALSE | TRUE
2061 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG-10 | 27148 | 27148 |  |  | 27148 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 233 - OG10 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
2062 | DRIVE PILES AND INSTALL LAGGING FOR SOE - OG-10 | 34172 | 34172 |  |  | 34172 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 233 - OG10 - Division 31 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
2063 | STONE FOR FOUNDATION - OG-10 | 7221 | 7221 |  |  | 7221 | 03- RESAND: O'Dwyer Gardens | T- OG10 | 233 - OG10 - Division 31 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
2064 | EROSION CONTROL FABRIC - OGE | 184400 | 101420 | 9220 |  | 110640 | 03- RESAND: O'Dwyer Gardens | U- OGE | 234 - OGE - Division 2 | Setup around stockpile and OG10 fence | 60% | MLJ | Brian | FALSE | TRUE | FALSE
2065 | INLET PROTECTION - OGE | 38875 | 21381.25 | 1943.75 |  | 23325 | 03- RESAND: O'Dwyer Gardens | U- OGE | 234 - OGE - Division 2 |  | 60% | MLJ | Brian | FALSE | TRUE | FALSE
2066 | SILT FENCE - OGE | 19290 | 13503 | 964.5 |  | 14467.5 | 03- RESAND: O'Dwyer Gardens | U- OGE | 234 - OGE - Division 2 | Setup around stockpile and OG10 | 75% | MLJ | Brian | FALSE | TRUE | FALSE
2067 | SANITARY WASTE PIPING SPECIALTIES | 19388 | 17449.2 |  |  | 17449.2 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
2068 | STABILIZED CONSTRUCTION ENTRANCE - OGE | 47400 | 47400 |  |  | 47400 | 03- RESAND: O'Dwyer Gardens | U- OGE | 234 - OGE - Division 2 | Fencing & entrance for building foundations complete | 100% | MLJ | Brian | FALSE | FALSE | TRUE
2069 | MANTAIN EROSION CONTROL - OGE | 42735 | 23504.25 | 2136.75 |  | 25641 | 03- RESAND: O'Dwyer Gardens | U- OGE | 234 - OGE - Division 2 |  | 60% | MLJ | Brian | FALSE | TRUE | FALSE
2070 | REMOVE EROSION CONTROL - OGE | 29979 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 234 - OGE - Division 2 |  | 0% | MLJ | Brian | FALSE | FALSE | TRUE
2071 | REMOVE FENCE - OGE | 23930 | 23930 |  |  | 23930 | 03- RESAND: O'Dwyer Gardens | U- OGE | 234 - OGE - Division 2 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
2072 | REMOVE FULL DEPTH ASPHALT PVMT - OGE | 141750 | 134662.5 |  |  | 134662.5 | 03- RESAND: O'Dwyer Gardens | U- OGE | 234 - OGE - Division 2 |  | 95% | MLJ | Brian | FALSE | FALSE | TRUE
2073 | REMOVE SITE FURNISHING - OGE | 98825 | 93883.75 |  |  | 93883.75 | 03- RESAND: O'Dwyer Gardens | U- OGE | 234 - OGE - Division 2 |  | 95% | MLJ | Brian | FALSE | FALSE | TRUE
2074 | REMOVE CONCRETE CURB & STEPS - OGE | 69775 | 66286.25 |  |  | 66286.25 | 03- RESAND: O'Dwyer Gardens | U- OGE | 234 - OGE - Division 2 |  | 95% | MLJ | Brian | FALSE | FALSE | TRUE
2075 | REMOVE PVMTS - OGE | 202600 | 192470 |  |  | 192470 | 03- RESAND: O'Dwyer Gardens | U- OGE | 234 - OGE - Division 2 |  | 95% | MLJ | Brian | FALSE | FALSE | TRUE
2076 | FORMWORK SITE CONCRETE - OGE | 55661 | 13915.25 |  |  | 13915.25 | 03- RESAND: O'Dwyer Gardens | U- OGE | 235 - OGE - Division 3 |  | 25% | MLJ | Brian | FALSE | FALSE | TRUE
2077 | CONCRETE FOOTING FOR SITE FURNISHING - OGE | 3304 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 235 - OGE - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2078 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 13200 |  |  | 13200 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 40% | Vital | Kurston | FALSE | FALSE | TRUE
2079 | CONCRETE DUCTBANKS - OGE | 56347 | 45077.6 |  |  | 45077.6 | 03- RESAND: O'Dwyer Gardens | U- OGE | 235 - OGE - Division 3 | OG10->OG1 & OG5->MH & MH to Street complete | 80% | MLJ | Sully | FALSE | FALSE | TRUE
2080 | CONCRETE SITE RETAINING WALL AND FOOTINGS - OGE | 33106 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 235 - OGE - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2081 | Manhole Work | 54750 | 54750 |  |  | 54750 | 03- RESAND: O'Dwyer Gardens | U- OGE | 236 - OGE - Division 26 | mh near OG5 installed | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
2082 | Site Lighting - Cable | 68438 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 236 - OGE - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2083 | Site Lighting - Conduit | 87600 | 4380 |  |  | 4380 | 03- RESAND: O'Dwyer Gardens | U- OGE | 236 - OGE - Division 26 |  | 5% | Five Star | Kurston | FALSE | FALSE | TRUE
2084 | Site Lighting - Fixtures | 108296 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 236 - OGE - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2085 | Survey | 54750 | 54750 |  |  | 54750 | 03- RESAND: O'Dwyer Gardens | U- OGE | 236 - OGE - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
2086 | Underground Electric Service - Cable | 1040250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 236 - OGE - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2087 | Underground Electric Service - Conduit | 821250 | 780187.5 |  |  | 780187.5 | 03- RESAND: O'Dwyer Gardens | U- OGE | 236 - OGE - Division 26 |  | 95% | Five Star | Kurston | FALSE | FALSE | TRUE
2088 | TREE PROTECTION - OGE | 14532 | 13532 |  |  | 13532 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 |  | 93.12% | MLJ | Sully | FALSE | FALSE | TRUE
2089 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 186998 | 28049.7 |  |  | 28049.7 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 15% | Vital | Kurston | FALSE | FALSE | TRUE
2090 | HAND EXCAVATION AS NEEDED - OGE | 36868 | 34858 |  |  | 34858 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 |  | 94.55% | MLJ | Sully | FALSE | FALSE | TRUE
2091 | EXCAVATION FOR SITE FURNISHING FOOTINGS - OGE | 4025 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2092 | BACKFILL - OGE | 222505 | 111252.5 |  |  | 111252.5 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 |  | 50% | MLJ | Sully | FALSE | FALSE | TRUE
2093 | EXCAVATE FOR ASPHALT PAVEMENTS - OGE | 21187 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2094 | BACKFILL FOR ASPHALT PAVEMENTS - OGE | 9846 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2095 | SITE FURNISHINGS - OGE | 46594 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2096 | DRINKING FOUNTAIN - OGE | 8030 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2097 | Dewatering Permits | 15178 | 14419.1 | 758.9 |  | 15178 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 | 50% building, 50% utilities. Buildings out of water table so 100% compete, Utilities 80% | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2098 | Furnish and Install Deep Wells | 157500 | 149625 | 7875 |  | 157500 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 | 50% building, 50% utilities. Buildings out of water table so 100% compete, Utilities 80% | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2099 | Furnish and Install Pumps and Piping | 128400 | 109140 | 6420 |  | 115560 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 | 50% building, 50% utilities. Buildings out of water table so 100% compete, Utilities 80% | 90% | MLJ | Brian | FALSE | TRUE | FALSE
2100 | GAS SERVICE AND PIPING | 2112 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2101 | Power for Dewatering | 109091 | 98636.45 | 5454.55 |  | 104091 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 | 50% building, 50% utilities. Buildings out of water table so 100% compete, Utilities 80% | 95.42% | MLJ | Brian | FALSE | TRUE | FALSE
2102 | Installation Support | 120000 | 109000 | 6000 |  | 115000 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 | 50% building, 50% utilities. Buildings out of water table so 100% compete, Utilities 80% | 95.83% | MLJ | Brian | FALSE | TRUE | FALSE
2103 | Dewatering expenses | 218182 | 207272.9 | 10909.1 |  | 218182 | 03- RESAND: O'Dwyer Gardens | U- OGE | 237 - OGE - Division 31 | 50% building, 50% utilities. Buildings out of water table so 100% compete, Utilities 80% | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2104 | 4' Chain Link Fence | 23650 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Atlas | Ricky | FALSE | FALSE | TRUE
2105 | 10' Chain Link Fence | 24750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Atlas | Ricky | FALSE | FALSE | TRUE
2106 | 8' High Temporary Fence | 242250 | 242250 |  |  | 242250 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 | Fence installed to contract requirements | 100% | Atlas | Ricky | FALSE | FALSE | TRUE
2107 | Ametco Fence | 136950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Atlas | Ricky | FALSE | FALSE | TRUE
2108 | 4" CONCRETE | 49500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2109 | 5"POROUS CONCRETE | 551320 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2110 | 5" COLOR CONCRETE | 38500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2111 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 2678.5 |  |  | 2678.5 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 50% | Vital | Kurston | FALSE | FALSE | TRUE
2112 | CONCRETE CURB | 38500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2113 | SFC -STELL FACING CURB | 4400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2114 | CONCRETE STEPS | 36960 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2115 | Asphalt Parking | 291050 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Citywide Paving | Sully | FALSE | FALSE | TRUE
2116 | Pavement Marking for Parking | 4641 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Citywide Paving | Sully | FALSE | FALSE | TRUE
2117 | Pavement Marking for Basketball Court | 6195 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Citywide Paving | Sully | FALSE | FALSE | TRUE
2118 | Deciduous Trees | 14175 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2119 | Evergreen Trees | 2835 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2120 | Deciduous Shrubs | 441 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2121 | Tree Removal | 34914 | 34914 |  |  | 34914 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 100% | Aspen | Adam | FALSE | FALSE | TRUE
2122 | Plumbing Pipe Insulation | 35464 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
2123 | Lawn Seeding (not including topsoil) | 9671 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2124 | Soil Erosion Mat | 6707 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2125 | Topsoil Stockpile/Spread | 67996 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2126 | Maintenance | 2678 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 238 - OGE - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2127 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - OGE | 16286 | 15471.7 | 814.3 |  | 16286 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 | in line with undeground utilities | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2128 | TERMINATE AND DEMOLISH EXISTING UTILITIES - OGE | 8796 | 8356.2 | 439.8 |  | 8796 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 |  | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2129 | INSTALL HW, CW PIPE - OGE | 231845 | 231845 |  |  | 231845 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
2130 | TEST HW, CW - OGE | 8794 | 8794 |  |  | 8794 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 |  | 100% | MLJ | Sully | FALSE | FALSE | TRUE
2131 | INSTALL CONDENSATE AND STEAM PIPE - OGE | 427171 | 333193.38 |  |  | 333193.38 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 |  | 78% | Welkin | Sully | FALSE | FALSE | TRUE
2132 | TEST CONDENSATE, STEAM - OGE | 19421 | 13594.7 |  |  | 13594.7 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 | Tested Steam OG6 > OG1. 5 more tests remaining for OGE | 70% | MLJ | Sully | FALSE | FALSE | TRUE
2133 | Heat Trace | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 024 - SG2 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2134 | DEWATERING COVERAGE FOR UTILITY WORK - OGE | 56118 | 53312.1 | 2805.9 |  | 56118 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 | in line with undeground utilities | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2135 | SEWER / DRAINAGE PIPE - OGE | 221493 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2136 | CATCH BASIN DRAINS AND CONNECTIONS - OGE | 157243 | 15724.3 |  |  | 15724.3 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 | delivery | 10% | MLJ | Sully | FALSE | FALSE | TRUE
2137 | DRAINAGE MANHOLES - OGE | 33988 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2138 | REMOVE AREA DRAINS - OGE | 58300 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2139 | ELECTRICAL MANHOLES - OGE | 12725 | 12725 |  |  | 12725 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 | mh installed near OG5 | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
2140 | ELECTRICAL CONDUIT TRENCHES - OGE | 91065 | 81958.5 |  |  | 81958.5 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 |  | 90% | MLJ | Sully | FALSE | FALSE | TRUE
2141 | Equipment SUPPORT FOR SITE - OGE | 167754 | 159366.3 | 8387.7 |  | 167754 | 03- RESAND: O'Dwyer Gardens | U- OGE | 239 - OGE - Division 33 | Ongoing work on site using equipment. Bill 5% per month | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2142 | EROSION CONTROL FABRIC - OGW | 12350 | 9880 | 617.5 |  | 10497.5 | 03- RESAND: O'Dwyer Gardens | V- OGW | 240 - OGW - Division 2 | Work completed around OG8 and OG9; remaining for trenching work | 85% | MLJ | Brian | FALSE | TRUE | FALSE
2143 | INLET PROTECTION - OGW | 34210 | 29078.5 | 1710.5 |  | 30789 | 03- RESAND: O'Dwyer Gardens | V- OGW | 240 - OGW - Division 2 | Work completed around OG8 and OG9; remaining for trenching work | 90% | MLJ | Brian | FALSE | TRUE | FALSE
2144 | Survey | 66000 | 66000 |  |  | 66000 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
2145 | SILT FENCE - OGW | 26085 | 26085 | 1304.25 |  | 27389.25 | 03- RESAND: O'Dwyer Gardens | V- OGW | 240 - OGW - Division 2 | Work completed around OG8 and OG9; remaining for trenching work | 105% | MLJ | Brian | TRUE | TRUE | FALSE
2146 | STABILIZED CONSTRUCTION ENTRANCE - OGW | 48150 | 48150 |  |  | 48150 | 03- RESAND: O'Dwyer Gardens | V- OGW | 240 - OGW - Division 2 | Fencing & entrance for building foundations complete | 100% | MLJ | Brian | FALSE | FALSE | TRUE
2147 | MANTAIN EROSION CONTROL - OGW | 42735 | 6410.25 | 2136.75 |  | 8547 | 03- RESAND: O'Dwyer Gardens | V- OGW | 240 - OGW - Division 2 |  | 20% | MLJ | Brian | FALSE | TRUE | FALSE
2148 | REMOVE EROSION CONTROL - OGW | 29979 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 240 - OGW - Division 2 |  | 0% | MLJ | Brian | FALSE | FALSE | TRUE
2149 | REMOVE FENCE - OGW | 6800 | 5100 |  |  | 5100 | 03- RESAND: O'Dwyer Gardens | V- OGW | 240 - OGW - Division 2 |  | 75% | MLJ | Brian | FALSE | FALSE | TRUE
2150 | REMOVE FULL DEPTH ASPHALT PVMT - OGW | 157695 | 141925.5 |  |  | 141925.5 | 03- RESAND: O'Dwyer Gardens | V- OGW | 240 - OGW - Division 2 |  | 90% | MLJ | Brian | FALSE | FALSE | TRUE
2151 | REMOVE SITE FURNISHING - OGW | 116200 | 93100 |  |  | 93100 | 03- RESAND: O'Dwyer Gardens | V- OGW | 240 - OGW - Division 2 |  | 80.12% | MLJ | Brian | FALSE | FALSE | TRUE
2152 | REMOVE CONCRETE CURB & STEPS - OGW | 98525 | 88672.5 |  |  | 88672.5 | 03- RESAND: O'Dwyer Gardens | V- OGW | 240 - OGW - Division 2 |  | 90% | MLJ | Brian | FALSE | FALSE | TRUE
2153 | REMOVE PVMTS - OGW | 209575 | 188617.5 |  |  | 188617.5 | 03- RESAND: O'Dwyer Gardens | V- OGW | 240 - OGW - Division 2 |  | 90% | MLJ | Brian | FALSE | FALSE | TRUE
2154 | FORMWORK SITE CONCRETE - OGW | 55661 | 18368.13 |  |  | 18368.13 | 03- RESAND: O'Dwyer Gardens | V- OGW | 241 - OGW - Division 3 |  | 33% | MLJ | Brian | FALSE | FALSE | TRUE
2155 | Exhaust Fans: Furnish | 1320 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2156 | CONCRETE FOOTING FOR SITE FURNISHING - OGW | 5286 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 241 - OGW - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2157 | CONCRETE DUCTBANKS - OGW | 61956 | 55760.4 |  |  | 55760.4 | 03- RESAND: O'Dwyer Gardens | V- OGW | 241 - OGW - Division 3 |  | 90% | MLJ | Sully | FALSE | FALSE | TRUE
2158 | CONCRETE SITE RETAINING WALL AND FOOTINGS OGW | 31529 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 241 - OGW - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2159 | EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - OGW | 24647 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 242 - OGW - Division 11 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2160 | Jet Spray | 88000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 242 - OGW - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2161 | Crackle Corn | 22000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 242 - OGW - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2162 | 2-5 year play equipment | 88000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 242 - OGW - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2163 | 5-12 year play equipment | 88000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 242 - OGW - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2164 | Aquavator | 22000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 242 - OGW - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2165 | Install Water Play Equipment and Piping | 55000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 242 - OGW - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2166 | Exhaust Fans: Install | 4565 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2167 | Manhole Installation | 54750 | 27375 |  |  | 27375 | 03- RESAND: O'Dwyer Gardens | V- OGW | 243 - OGW - Division 26 | No manhoe in OGE so billed as conduit is installed | 50% | Five Star | Kurston | FALSE | FALSE | TRUE
2168 | Site Lighting - Cable | 82125 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 243 - OGW - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2169 | Site Lighting - Conduit | 76650 | 65152.5 |  |  | 65152.5 | 03- RESAND: O'Dwyer Gardens | V- OGW | 243 - OGW - Division 26 |  | 85% | Five Star | Kurston | FALSE | FALSE | TRUE
2170 | Site Lighting - Fixtures | 85629 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 243 - OGW - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2171 | Survey | 54750 | 54750 |  |  | 54750 | 03- RESAND: O'Dwyer Gardens | V- OGW | 243 - OGW - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
2172 | Underground Electric Service - Cable | 1095000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 243 - OGW - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2173 | Underground Electric Service - Conduit | 903375 | 858206.25 |  |  | 858206.25 | 03- RESAND: O'Dwyer Gardens | V- OGW | 243 - OGW - Division 26 |  | 95% | Five Star | Kurston | FALSE | FALSE | TRUE
2174 | TREE PROTECTION - OGW | 24912 | 22912 |  |  | 22912 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 |  | 91.97% | MLJ | Sully | FALSE | FALSE | TRUE
2175 | HAND EXCAVATION AS NEEDED - OGW | 86903 | 81903 |  |  | 81903 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 | Test pitting for OG8, OG9, and utility runs complete; completed excavation up against the building | 94.25% | MLJ | Sully | FALSE | FALSE | TRUE
2176 | EXCAVATION FOR SITE FURNISHING FOOTINGS - OGW | 4025 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2177 | Steam Unit Heaters: Furnish | 1100 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2178 | BACKFILL - OGW | 196176 | 117795.6 |  |  | 117795.6 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 |  | 60.05% | MLJ | Sully | FALSE | FALSE | TRUE
2179 | EXCAVATE FOR ASPHALT PAVEMENTS - OGW | 21187 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2180 | BACKFILL FOR ASPHALT PAVEMENTS - OGW | 4190 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2181 | SITE FURNISHINGS - OGW | 31684 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2182 | DRINKING FOUNTAIN - OGW | 8030 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2183 | LANDSCAPE BOULDERS - OGW | 277962 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2184 | Dewatering Permits | 15178 | 14419.1 |  |  | 14419.1 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 | 33% OG8, 33% OG9 and 33% utilities. OG8- 100% complete & OG9 100% complete, utility trenches 90% complete | 95% | MLJ | Brian | FALSE | FALSE | TRUE
2185 | Furnish and Install Deep Wells | 123750 | 117562.5 | 6187.5 |  | 123750 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 | 33% OG8, 33% OG9 and 33% utilities. OG8- 100% complete & OG9 100% complete, utility trenches 90% complete | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2186 | Furnish and Install Pumps and Piping | 24600 | 23370 | 1230 |  | 24600 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 | 33% OG8, 33% OG9 and 33% utilities. OG8- 100% complete & OG9 100% complete, utility trenches 90% complete | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2187 | Power for Dewatering | 109091 | 103636.45 | 5454.55 |  | 109091 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 | 33% OG8, 33% OG9 and 33% utilities. OG8- 100% complete & OG9 100% complete, utility trenches 90% complete | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2188 | Steam Unit Heaters: Install | 9900 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2189 | Installation Support | 120000 | 114000 | 6000 |  | 120000 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 | 33% OG8, 33% OG9 and 33% utilities. OG8- 100% complete & OG9 100% complete, utility trenches 90% complete | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2190 | Dewatering expenses | 218182 | 207272.9 | 10909.1 |  | 218182 | 03- RESAND: O'Dwyer Gardens | V- OGW | 244 - OGW - Division 31 | 33% OG8, 33% OG9 and 33% utilities. OG8- 100% complete & OG9 100% complete, utility trenches 90% complete | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2191 | 4' Chain Link Fence | 99000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Atlas | Ricky | FALSE | FALSE | TRUE
2192 | 10' Chain Link Fence | 19250 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Atlas | Ricky | FALSE | FALSE | TRUE
2193 | 8' High Temporary Fence | 316350 | 316350 |  |  | 316350 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 | all areas fenced | 100% | Atlas | Ricky | FALSE | FALSE | TRUE
2194 | Ametco Fence | 136950 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Atlas | Ricky | FALSE | FALSE | TRUE
2195 | 4" CONCRETE | 143000 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2196 | 7" CONCRETE RAMP | 2750 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2197 | 5" POROUS CONCRETE | 459030 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2198 | 5" COLOR CONCRETE | 39600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2199 | Condensate Return Unit: Furnish | 7700 | 7700 |  |  | 7700 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
2200 | CONCRETE CURB | 39600 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2201 | SFC -STELL FACING CURB | 27500 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2202 | CONCRETE STEPS | 15400 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2203 | Asphalt Parking | 129675 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Citywide Paving | Sully | FALSE | FALSE | TRUE
2204 | Pavement Marking for Parking | 2730 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Citywide Paving | Sully | FALSE | FALSE | TRUE
2205 | Deciduous Trees | 9214 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2206 | Deciduous Shrubs | 2793 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2207 | Evergreen Shrubs | 3686 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2208 | Perennials | 8180 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2209 | Grasses | 16160 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2210 | Condensate Return Unit: Install | 16500 | 16500 |  |  | 16500 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
2211 | Tree Removal | 39351 | 39351 |  |  | 39351 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 100% | Aspen | Adam | FALSE | FALSE | TRUE
2212 | Lawn Seeding (not including topsoil) | 9593 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2213 | Soil Erosion Mat | 1008 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2214 | Topsoil Stockpile/Spread | 67725 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2215 | Maintenance | 2678 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 245 - OGW - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2216 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - OGW | 16286 | 12214.5 | 814.3 |  | 13028.8 | 03- RESAND: O'Dwyer Gardens | V- OGW | 246 - OGW - Division 33 |  | 80% | MLJ | Brian | FALSE | TRUE | FALSE
2217 | TERMINATE AND DEMOLISH EXISTING UTILITIES - OGW | 20278 | 9125.1 | 1013.9 |  | 10139 | 03- RESAND: O'Dwyer Gardens | V- OGW | 246 - OGW - Division 33 |  | 50% | MLJ | Brian | FALSE | TRUE | FALSE
2218 | INSTALL HW, CW PIPE - OGW | 452669 | 452669 |  |  | 452669 | 03- RESAND: O'Dwyer Gardens | V- OGW | 246 - OGW - Division 33 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
2219 | TEST HW, CW - OGW | 21983 | 21983 |  |  | 21983 | 03- RESAND: O'Dwyer Gardens | V- OGW | 246 - OGW - Division 33 |  | 100% | MLJ | Sully | FALSE | FALSE | TRUE
2220 | INSTALL CONDENSATE AND STEAM PIPE - OGW | 622421 | 303741.448 |  |  | 303741.448 | 03- RESAND: O'Dwyer Gardens | V- OGW | 246 - OGW - Division 33 |  | 48.8% | Welkin | Sully | FALSE | FALSE | TRUE
2221 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2222 | TEST CONDENSATE, STEAM - OGW | 32367 | 9710.1 |  |  | 9710.1 | 03- RESAND: O'Dwyer Gardens | V- OGW | 246 - OGW - Division 33 |  | 30% | MLJ | Sully | FALSE | FALSE | TRUE
2223 | DEWATERING COVERAGE FOR UTILITY WORK - OGW | 56118 | 44894.4 | 2805.9 |  | 47700.3 | 03- RESAND: O'Dwyer Gardens | V- OGW | 246 - OGW - Division 33 | inline with utilities | 85% | MLJ | Brian | FALSE | TRUE | FALSE
2224 | SEWER / DRAINAGE PIPE - OGW | 187235 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 246 - OGW - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2225 | CATCH BASIN DRAINS AND CONNECTIONS - OGW | 131036 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 246 - OGW - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2226 | REMOVE AREA DRAINS - OGW | 46640 | 0 |  |  | 0 | 03- RESAND: O'Dwyer Gardens | V- OGW | 246 - OGW - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2227 | ELECTRICAL CONDUIT TRENCHES - OGW | 77232 | 77232 |  |  | 77232 | 03- RESAND: O'Dwyer Gardens | V- OGW | 246 - OGW - Division 33 |  | 100% | MLJ | Sully | FALSE | FALSE | TRUE
2228 | Equipment SUPPORT FOR SITE - OGW | 167754 | 150978.6 | 8387.7 |  | 159366.3 | 03- RESAND: O'Dwyer Gardens | V- OGW | 246 - OGW - Division 33 | Ongoing work on site using equipment. Bill 5% per month | 95% | MLJ | Brian | FALSE | TRUE | FALSE
2229 | INLET PROTECTION - S8 | 21770 | 5442.5 | 2177 |  | 7619.5 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 35% | MLJ | Brian | FALSE | TRUE | FALSE
2230 | SILT FENCE - S8 | 14520 | 3630 | 1452 |  | 5082 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 35% | MLJ | Brian | FALSE | TRUE | FALSE
2231 | STABILIZED CONSTRUCTION ENTRANCE - S8 | 45660 | 45660 |  |  | 45660 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 | entrances created | 100% | MLJ | Brian | FALSE | FALSE | TRUE
2232 | Heating and Ventilation Unit: Install | 17600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2233 | EROSION CONTROL FABRIC - S8 | 31260 | 7815 | 3126 |  | 10941 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 35% | MLJ | Brian | FALSE | TRUE | FALSE
2234 | MANTAIN EROSION CONTROL - S8 | 42735 | 10683.75 | 4273.5 |  | 14957.25 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 35% | MLJ | Brian | FALSE | TRUE | FALSE
2235 | REMOVE EROSION CONTROL - S8 | 29979 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | MLJ | Brian | FALSE | FALSE | TRUE
2236 | REMOVE FENCE - S8 | 10510 | 10510 |  |  | 10510 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
2237 | REMOVE FULL DEPTH ASPHALT PVMT - S8 | 8750 | 7000 |  |  | 7000 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 80% | MLJ | Brian | FALSE | FALSE | TRUE
2238 | REMOVE SITE FURNISHING -S8 | 120545 | 100545 |  |  | 100545 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 83.41% | MLJ | Brian | FALSE | FALSE | TRUE
2239 | REMOVE CONCRETE CURB & STEPS - S8 | 15600 | 12480 | 1560 |  | 14040 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 90% | MLJ | Brian | FALSE | TRUE | FALSE
2240 | REMOVE PVMTS - S8 | 115615 | 92492 | 11561.5 |  | 104053.5 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 90% | MLJ | Brian | FALSE | TRUE | FALSE
2241 | Gaskets | 101250 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2242 | Wire Insulation | 75000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2243 | Steam Traps: Furnish | 1320 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2244 | Assumed Flooring Material (Slab Penetrations) | 10800 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2245 | Vinyl Membrane and Mastic | 72114 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2246 | Caulk | 184500 | 51750 |  |  | 51750 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 | 23 SF out of 82 SF Contract | 28.05% | ATCO | Kurston | FALSE | FALSE | TRUE
2247 | Fibrous Slate | 25500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2248 | Waterproofing | 9942 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2249 | Underground Utility Materials | 4680 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2250 | Remove existing paint and plaster - cellar | 60000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2251 | Remove sump pump - cellar | 20000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2252 | Remove existing vent / window and frame - cellar and 1st floor | 20000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2253 | Remove existing door, frame and hardware - cellar and 1st floor | 20000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2254 | Steam Traps: Install | 12100 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2255 | Remove Areaway slab and drain - cellar | 60000 | 6000 |  |  | 6000 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 10% | MLJ | Kurston | FALSE | FALSE | TRUE
2256 | Remove Areaway grate - cellar | 20000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2257 | Sawcut and remove portion of areaway wall - cellar | 60000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2258 | Remove existing portion wall - 1st floor | 60000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2259 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2260 | Remove window sill - 1st floor | 10000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 247 - S8 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2261 | FORMWORK SITE CONCRETE - S8 | 55661 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 248 - S8 - Division 3 |  | 0% | MLJ | Brian | FALSE | FALSE | TRUE
2262 | CONCRETE FOOTING FOR SITE FURNISHING - S8 | 5947 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 248 - S8 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2263 | CONCRETE DUCTBANKS - S8 | 38245 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 248 - S8 - Division 3 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2264 | Cast Stone with SS letters | 6870 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 249 - S8 - Division 4 |  | 0% | S & D | Stefon | FALSE | FALSE | TRUE
2265 | Vacuum Pump Unit: Furnish | 17600 | 17600 |  |  | 17600 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
2266 | Dunnage Grating Galvanized | 20173 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 250 - S8 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
2267 | Dunnage Stair and Guard Rail at 1 Location | 13035 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 250 - S8 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
2268 | Stair A: 1st, 2nd & 3rd Floor Stair and Landing with Hand & Guard Rail | 124892 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 250 - S8 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
2269 | Ship Ladder with Cage and Platform | 25450 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 250 - S8 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
2270 | Bulkhead Roof Access Ship Ladder at 2 Locations | 15311 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 250 - S8 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
2271 | Temporary Aluminum Over Pass Stair | 114392 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 250 - S8 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
2272 | Overhead Door | 16000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 251 - S8 - Division 8 |  | 0% | Loading Dock | Ricky | FALSE | FALSE | TRUE
2273 | Painting S8-2 | 110000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 252 - S8 - Division 9 |  | 0% | GG Paint | Stefon | FALSE | FALSE | TRUE
2274 | Stair Identification Sign | 2750 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 253 - S8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2275 | Stairway Floor number and ID Sign | 2750 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 253 - S8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2276 | Vacuum Pump Unit: Install | 19800 | 19800 |  |  | 19800 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
2277 | Room Sign | 2200 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 253 - S8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2278 | Exit Sign | 550 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 253 - S8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2279 | Stairway Flood Access Door | 550 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 253 - S8 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2280 | Temporary Egress Stair Storage Sign | 1320 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 253 - S8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2281 | Address Signs | 3850 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 253 - S8 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2282 | EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - S8 | 36970 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 254 - S8 - Division 11 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2283 | Arch Jet | 44000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 254 - S8 - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2284 | Mist Spray | 22000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 254 - S8 - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2285 | 2-5 year play equipment | 88000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 254 - S8 - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2286 | 5-12 year play equipment | 88000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 254 - S8 - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2287 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 91850 | 82665 |  |  | 82665 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
2288 | Aquavator | 22000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 254 - S8 - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2289 | Splash Pad | 22000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 254 - S8 - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2290 | Install Water Play Equipment and Piping | 55000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 254 - S8 - Division 11 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2291 | Clean and refurbish landing device components in the pit | 4000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2292 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2293 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2294 | Replace oil buffers | 5000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2295 | Replace compensation guidance system per dwgs | 10000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2296 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2297 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2298 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 122100 | 109890 |  |  | 109890 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
2299 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2300 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2301 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2302 | Wire brush sills and support (at the first floor only) | 2000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2303 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2304 | Replace pit lights and outlets | 3000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2305 | Replace all pit stop switches and light switches | 5000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2306 | Repair/replace pit access doors and hardware | 5000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2307 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2308 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2309 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 45100 | 40590 |  |  | 40590 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
2310 | Clean and paint buffer inspection ladders | 2000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2311 | Clean out pit of all dirt and debris | 2000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2312 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 255 - S8 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2313 | Plumbing Pipe Insulation | 53797 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 256 - S8 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
2314 | TREE PROTECTION - S8 | 4844 | 2034.48 |  |  | 2034.48 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 |  | 42% | MLJ | Sully | FALSE | FALSE | TRUE
2315 | HAND EXCAVATION AS NEEDED - S8 | 52668 | 42134.4 |  |  | 42134.4 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 | Test pitting for building footings and sidewalk gas line, completed in July. Test pit for utilities from OGW in October. | 80% | MLJ | Sully | FALSE | FALSE | TRUE
2316 | EXCAVATION FOR SITE FURNISHING FOOTINGS - S8 | 4025 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2317 | BACKFILL - S8 | 141886 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2318 | EXCAVATE FOR ASPHALT PAVEMENTS - S8 | 7063 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2319 | BACKFILL FOR ASPHALT PAVEMENTS - S8 | 4190 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2320 | Mechanical Pipe: Hydrostatic Testing | 1650 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2321 | SITE FURNISHINGS - S8 | 27956 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2322 | DRINKING FOUNTAIN - S8 | 8030 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2323 | Dewatering Permits | 15178 | 7589 | 1517.8 |  | 9106.8 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 | Dewatering this area now | 60% | MLJ | Brian | FALSE | TRUE | FALSE
2324 | Furnish and Install Deep Wells | 67500 | 0 | 6750 |  | 6750 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 | Dewatering this area now | 10% | MLJ | Brian | FALSE | TRUE | FALSE
2325 | Furnish and Install Pumps and Piping | 7800 | 0 | 780 |  | 780 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 | Dewatering this area now | 10% | MLJ | Brian | FALSE | TRUE | FALSE
2326 | Power for Dewatering | 109091 | 0 | 10909.1 |  | 10909.1 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 | Dewatering this area now | 10% | MLJ | Brian | FALSE | TRUE | FALSE
2327 | Installation Support | 120000 | 0 | 12000 |  | 12000 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 | Dewatering this area now | 10% | MLJ | Brian | FALSE | TRUE | FALSE
2328 | Dewatering expenses | 218182 | 0 | 21818.2 |  | 21818.2 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 257 - S8 - Division 31 | Dewatering this area now | 10% | MLJ | Brian | FALSE | TRUE | FALSE
2329 | 4' High Steel Bar Fence | 87450 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | Atlas | Ricky | FALSE | FALSE | TRUE
2330 | 8' High Temporary Fence | 138225 | 138225 |  |  | 138225 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 | all areas fenced | 100% | Atlas | Ricky | FALSE | FALSE | TRUE
2331 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9900 | 9405 |  |  | 9405 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 95% | Welkin | Sully | FALSE | FALSE | TRUE
2332 | 4" CONCRETE | 38500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2333 | 5"POROUS CONCRETE | 148940 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2334 | 5" COLOR CONCRETE | 121000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2335 | CONCRETE CURB | 38500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2336 | SFC -STELL FACING CURB | 8800 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2337 | CONCRETE STEPS | 9240 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | JMC | Ricky | FALSE | FALSE | TRUE
2338 | Asphalt Parking | 43544 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | Citywide Paving | Sully | FALSE | FALSE | TRUE
2339 | Deciduous Trees | 11340 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2340 | Evergreen Trees | 2127 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2341 | Deciduous Shrubs | 882 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2342 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 17600 | 16720 |  |  | 16720 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 95% | Welkin | Sully | FALSE | FALSE | TRUE
2343 | Evergreen Shrubs | 1418 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2344 | Perennials | 3352 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2345 | Grasses | 6225 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2346 | Tree Removal | 32700 | 5000 |  |  | 5000 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 15.29% | Aspen | Adam | FALSE | FALSE | TRUE
2347 | Lawn Seeding (not including topsoil) | 2621 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2348 | Topsoil Stockpile/Spread | 18963 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2349 | Maintenance | 2659.34 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 258 - S8 - Division 32 |  | 0% | Aspen | Adam | FALSE | FALSE | TRUE
2350 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - S8 | 16286 | 0 | 1628.6 |  | 1628.6 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 259 - S8 - Division 33 |  | 10% | MLJ | Brian | FALSE | TRUE | FALSE
2351 | TERMINATE AND DEMOLISH EXISTING UTILITIES - S8 | 6926 | 0 | 692.6 |  | 692.6 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 259 - S8 - Division 33 |  | 10% | MLJ | Brian | FALSE | TRUE | FALSE
2352 | INSTALL CONDENSATE AND STEAM PIPE - S8 | 55999 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 259 - S8 - Division 33 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2353 | HVAC Ductwork: Testing & Balancing | 1100 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2354 | TEST CONDENSATE, STEAM - S8 | 6474 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 259 - S8 - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2355 | DEWATERING COVERAGE FOR UTILITY WORK - S8 | 56118 | 0 | 5611.8 |  | 5611.8 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 259 - S8 - Division 33 |  | 10% | MLJ | Brian | FALSE | TRUE | FALSE
2356 | SEWER / DRAINAGE PIPE - S8 | 126691 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 259 - S8 - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2357 | CATCH BASIN DRAINS AND CONNECTIONS - S8 | 69886 | 34943 |  |  | 34943 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 259 - S8 - Division 33 | Manholes stored on site | 50% | MLJ | Sully | FALSE | FALSE | TRUE
2358 | REMOVE AREA DRAINS - S8 | 58300 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 259 - S8 - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2359 | ELECTRICAL MANHOLES - S8 | 6363 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 259 - S8 - Division 33 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2360 | ELECTRICAL CONDUIT TRENCHES - S8 | 39193 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 259 - S8 - Division 33 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2361 | Equipment SUPPORT FOR SITE - S8 | 167754 | 8387.7 | 16775.4 |  | 25163.1 | 04- RESAND: Coney Island I (Site 8) | W- S8 | 259 - S8 - Division 33 |  | 15% | MLJ | Brian | FALSE | TRUE | FALSE
2362 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - S8 | 143660 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 260 - S81 - Division 3 |  | 0% | MLJ | Brian | FALSE | FALSE | TRUE
2363 | DRILL & GROUT DOWELS - S8 | 20861 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 260 - S81 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2364 | Controls: Furnish and Install: Devices | 71500 | 28600 |  |  | 28600 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 40% | Welkin | Sully | FALSE | FALSE | TRUE
2365 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - S8 | 60871 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 260 - S81 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2366 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - S8 | 117673 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 260 - S81 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2367 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - S8 | 10239 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 260 - S81 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2368 | Footing/Pier | 38805 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 260 - S81 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2369 | Retaining Walls | 8668 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 260 - S81 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2370 | Entrance Slab | 90825 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 260 - S81 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2371 | Concrete Shelf | 5785 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 260 - S81 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2372 | Brick Shelf | 29445 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 260 - S81 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2373 | Boiler Room Concrete Curb | 6508 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 260 - S81 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2374 | GFRP Sikawrap 100 G | 23232 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 260 - S81 - Division 3 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2375 | Controls: Furnish and Install: Controls Conduit | 33000 | 29700 |  |  | 29700 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 90% | Welkin | Sully | FALSE | FALSE | TRUE
2376 | Overhead protection for Masonry | 94478 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 261 - S81 - Division 4 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2377 | Face Brick 3-5/8" | 166796 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 261 - S81 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2378 | 2" Face Brick | 346786 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 261 - S81 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2379 | 8" CMU | 146034 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 261 - S81 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2380 | 6" CMU (2 hour rated) | 249945 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 261 - S81 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2381 | 4" CMU | 109956 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 261 - S81 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2382 | 3-1/8" Rigid insulation | 14969 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 261 - S81 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2383 | 2" Rigid Insulation | 17391 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 261 - S81 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2384 | Coping stone C1/A-260 | 32747 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 261 - S81 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2385 | Steel Channel on top | 9460 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 262 - S81 - Division 5 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2386 | Controls: Furnish and Install: Controls Wiring | 9900 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2387 | Cont. Shelf angle | 9680 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 262 - S81 - Division 5 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2388 | Steel Channel on top | 9680 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 262 - S81 - Division 5 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2389 | STEEL (MATERIAL ONLY) | 117614 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 262 - S81 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
2390 | FABRICATION COSTS | 226674 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 262 - S81 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
2391 | METAL DECK (BUY-OUT) | 10693 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 262 - S81 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
2392 | ANCHORS & EMBEDS | 8554 | 8554 |  |  | 8554 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 262 - S81 - Division 5 | anchor bolts onsite | 100% | Weir Welding | Ricky | FALSE | FALSE | TRUE
2393 | SURVEYING | 6416 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 262 - S81 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
2394 | STEEL & DECK ERECTION | 433032 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 262 - S81 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
2395 | BOLTS AND HARDWARE | 9623 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 262 - S81 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
2396 | TRUCKING | 10693 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 262 - S81 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
2397 | Controls: Connect to Final Termination Points | 6600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2398 | PENETRATION FIRESTOPPING EXTG BLDG - S8 | 9611 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 263 - S81 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2399 | JOINT SEALANTS EXTG BLDGS - S8 | 9611 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 263 - S81 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2400 | Air Film | 17108 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 263 - S81 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2401 | Bituthene 4000 waterproofing membrane | 27967 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 263 - S81 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2402 | GE Elemax 2600 Silicone air and vapor barrier | 16896 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 263 - S81 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2403 | Crystalline Waterproofing at perimeter walls | 48933 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 263 - S81 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
2404 | Waterproofing at foundation walls | 34730 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 263 - S81 - Division 7 |  | 0% | DStar | Ricky | FALSE | FALSE | TRUE
2405 | Layout | 55794 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 263 - S81 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
2406 | Framing | 116720 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 263 - S81 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
2407 | Insulation | 20905 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 263 - S81 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
2408 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2409 | Cladding Install | 146335 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 263 - S81 - Division 7 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
2410 | Louvers Install | 36500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 264 - S81 - Division 8 |  | 0% | Navillus | Stefon | FALSE | FALSE | TRUE
2411 | Furnish Doors | 6272 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 265 - S81 - Division 9 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2412 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - S8 | 306768 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 266 - S81 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2413 | WINDOW FLOODGATES (8.06 AND 8.14) - S8 | 49836 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 266 - S81 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2414 | COMMON WORK RESULTS FOR PLUMBING | 15371 | 3842.75 |  |  | 3842.75 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 25% | Vital | Kurston | FALSE | FALSE | TRUE
2415 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 6000 | 900 |  |  | 900 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 15% | Vital | Kurston | FALSE | FALSE | TRUE
2416 | ESCUTCHEONS FOR PLUMBING PIPING | 2500 | 375 |  |  | 375 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 15% | Vital | Kurston | FALSE | FALSE | TRUE
2417 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 12200 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2418 | HANGERS AND SUPPORTS | 21800 | 5450 |  |  | 5450 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 25% | Vital | Kurston | FALSE | FALSE | TRUE
2419 | Insulation: Furnish and Install: Ductwork Insulation | 7700 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2420 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2975 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2421 | DOMESTIC WATER PIPING | 284883 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2422 | DOMESTIC WATER PIPING SPECIALTIES | 38000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2423 | DOMESTIC WATER PUMPING SYSTEMS | 75000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2424 | SANITARY WASTE PIPING | 170771 | 128078.25 |  |  | 128078.25 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 75% | Vital | Kurston | FALSE | FALSE | TRUE
2425 | SANITARY WASTE PIPING SPECIALTIES | 58485 | 52636.5 |  |  | 52636.5 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
2426 | STORM DRAINAGE PIPING SPECIALTIES | 58485 | 35091 |  |  | 35091 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 60% | Vital | Kurston | FALSE | FALSE | TRUE
2427 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 359996 | 107998.8 |  |  | 107998.8 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 30% | Vital | Kurston | FALSE | FALSE | TRUE
2428 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 145920 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2429 | GAS SERVICE AND PIPING | 262955 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2430 | Insulation: Furnish and Install: Piping Insulation | 18150 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2431 | PLUMBING FIXTURES | 5200 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2432 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 63171 | 6317.1 |  |  | 6317.1 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 | Material on site | 10% | Vital | Kurston | FALSE | FALSE | TRUE
2433 | Heat Trace | 5000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 267 - S81 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2434 | Survey | 66000 | 66000 |  |  | 66000 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
2435 | Exhaust Fans: Furnish | 8400 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2436 | Exhaust Fans: Install | 19050 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2437 | Electric Unit Heaters: Furnish | 3500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2438 | Steam Unit Heater: Install | 20000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2439 | Steam Unit Heater: Furnish | 54000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2440 | Condensate Return Unit: Furnish | 14000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2441 | Insulation: Furnish and Install: Equipment Insulation | 7700 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 025 - SG2 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2442 | Condensate Return Unit: Install | 35000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2443 | Steam Traps: Furnish | 4400 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2444 | Steam Traps: Install | 34000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2445 | Heating and Ventilation Unit: Furnish | 6500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2446 | Heating and Ventilation Unit: Install | 24000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2447 | Vacuum Pump Unit: Furnish | 16000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2448 | Vacuum Pump Unit : Install | 26000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2449 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 250500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2450 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 511500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2451 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 160000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2452 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2453 | Mechanical Pipe: Hydrostatic Testing | 4950 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2454 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 35000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2455 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 77000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2456 | HVAC Ductwork: Testing & Balancing | 3500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2457 | Controls: Furnish and Install: Devices | 115000 | 34500 |  |  | 34500 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 30% | Welkin | Sully | FALSE | FALSE | TRUE
2458 | Controls: Furnish and Install: Controls Conduit | 60000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2459 | Controls: Furnish and Install: Controls Wiring | 17250 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2460 | Controls: Connect to Final Termination Points | 10000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2461 | Controls: Controls Testing | 6000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2462 | Insulation: Furnish and Install: Ductwork Insulation | 18150 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2463 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2464 | Insulation: Furnish and Install: Piping Insulation | 30250 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2465 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 268 - S81 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2466 | ATS Energization | 15000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2467 | ATS Installation | 210000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2468 | ATS Terminations | 15000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2469 | ATS Testing | 15000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2470 | Bypass Connections (Misc Panels, Re-routes, etc) | 5000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2471 | Cabling - Interior Branch (1/0 & Smaller) | 225000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2472 | Cabling - Risers & Feeders (2/0 & Larger) | 886950 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2473 | Conduit - Branch Circuits (1 1/2" & Smaller) | 136875 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2474 | Cabling - Risers & Feeders (2/0 & Larger) | 689850 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2475 | Conduit - In-Slab | 216810 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2476 | Conduit - Risers (2" & Larger) | 985500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2477 | Demolition | 20000 | 2000 |  |  | 2000 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 10% | Five Star | Kurston | FALSE | FALSE | TRUE
2478 | Firestopping | 5000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2479 | Foundation Coring | 10000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2480 | Generator Delivery | 50000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2481 | Generator Release | 300000 | 300000 |  |  | 300000 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
2482 | Generator Terminations | 50000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2483 | Generator Test | 50000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2484 | Lighting Controls | 50000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2485 | Conduit - Branch Circuits (1 1/2" & Smaller) | 191625 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2486 | Lighting Install | 67800 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2487 | Lighting Rough | 67800 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2488 | Lighting System Program & Energize | 5000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2489 | Lightning Protection | 20000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2490 | Manhole Work | 25000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2491 | Mechanical Terminations(Dampers, Heaters, Motors) | 100000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2492 | Site Lighting - Cable | 24638 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2493 | Site Lighting - Conduit | 32850 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2494 | Site Lighting - Fixtures | 34500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2495 | Site Survey | 64000 | 64000 |  |  | 64000 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
2496 | Conduit - Risers (2" & Larger) | 788400 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2497 | Survey | 66000 | 66000 |  |  | 66000 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
2498 | Switches and Receptacles | 10000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2499 | Switchgear & Panelboard Energization | 30000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2500 | Switchgear & Panelboard Installation | 360000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2501 | Switchgear & Panelboard Terminations | 30000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2502 | Switchgear & Panelboard Testing | 30000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2503 | Temp Light & Power | 50000 | 15000 |  |  | 15000 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 30% | Five Star | Kurston | FALSE | FALSE | TRUE
2504 | Underground Electric Service - Cable | 410625 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2505 | Underground Electric Service - Conduit | 328500 | 49275 |  |  | 49275 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 269 - S81 - Division 26 |  | 15% | Five Star | Kurston | FALSE | FALSE | TRUE
2506 | Fire Alarm Conduit | 32850 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 270 - S81 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2507 | Demolition/Temp Light & Power | 54750 | 10950 |  |  | 10950 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 20% | Five Star | Kurston | FALSE | FALSE | TRUE
2508 | Fire Alarm Wiring | 31500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 270 - S81 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2509 | Fire Alarm Devices | 57000 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 270 - S81 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2510 | Fire Alarm Programming & Pretest | 2500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 270 - S81 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2511 | Fire Alarm FDNY Approval | 2500 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 270 - S81 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2512 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - S8 | 74861 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 271 - S81 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2513 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - S8 | 28908 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 271 - S81 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2514 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - S8 | 417 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | X- S81 | 271 - S81 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2515 | FORMWORK NEW BUILDING - S8 | 317228 | 0 | 31722.8 |  | 31722.8 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 272 - S82 - Division 3 | Formwork delivered and footings started | 10% | MLJ | Brian | FALSE | TRUE | FALSE
2516 | SET ANCHOR BOLTS FOR STEEL COLUMNS - S8 | 5411 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 272 - S82 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2517 | POUR CONCRETE NEW BUILDINGS - S8 | 147088 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 272 - S82 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2518 | Firestopping | 5250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2519 | FINISH SLABS - S8 | 15940 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 272 - S82 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2520 | Footing/Pier | 43103 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 272 - S82 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2521 | Grade Beams | 2298 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 272 - S82 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2522 | Floor Slabs | 23287 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 272 - S82 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2523 | Equipment Pads | 109 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 272 - S82 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2524 | First Floor Plumbing Shaft Slab | 1034 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 272 - S82 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2525 | Plumbing Shafts | 28192 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 272 - S82 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2526 | Concrete Bench | 890 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 272 - S82 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2527 | WWM-Slabs | 4933 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 272 - S82 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2528 | Layout | 5109 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 273 - S82 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2529 | Foundation Coring | 21000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2530 | Loading | 13137 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 273 - S82 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2531 | Exterior Framing, Insulation & Drywall - Materials | 46709 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 273 - S82 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2532 | Exterior Framing- Labor | 54445 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 273 - S82 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2533 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - S8 | 12569 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 274 - S82 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2534 | PENETRATION FIRESTOPPING NEW BLDG - S8 | 11505 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 274 - S82 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2535 | JOINT SEALANTS NEW BLDGS - S8 | 11505 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 274 - S82 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2536 | Insulation- Labor | 4740 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 274 - S82 - Division 7 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2537 | Crystalline Waterproofing at plumbing shaft | 3514 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 274 - S82 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
2538 | Waterproofing at foundation | 66700 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 274 - S82 - Division 7 |  | 0% | DStar | Ricky | FALSE | FALSE | TRUE
2539 | Fireproofing | 46200 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 274 - S82 - Division 7 |  | 0% | SIG | Ricky | FALSE | FALSE | TRUE
2540 | Lighting Controls | 24150 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2541 | P&I Cold Applied Roof Membrane | 68145 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 274 - S82 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
2542 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 70092 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 274 - S82 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
2543 | P&I Aluminum Coping | 3102 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 274 - S82 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | FALSE | TRUE
2544 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S8 | 14378 | 1437.8 |  |  | 1437.8 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 275 - S82 - Division 8 | delivered | 10% | MLJ | Ricky | FALSE | FALSE | TRUE
2545 | Doors, Frames & Hardware - Labor | 26968 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 275 - S82 - Division 8 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2546 | Furnish Doors | 22996 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 276 - S82 - Division 9 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2547 | Sheathing & Drywall - Labor | 33946 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 276 - S82 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2548 | Tape/ Spackle finishes | 13372 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 276 - S82 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2549 | Direct Applied Stucco | 31684 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 276 - S82 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2550 | EXCAVATION NEW BLDGS - S8-2 | 70840 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 277 - S82 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2551 | Lighting Remove & Re-install | 22667 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2552 | BACKFILL NEW BLDGS - S8 | 35192 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 277 - S82 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2553 | DEWATERING COVERAGE FOR NEW BUILDINGS - S8 | 42088 | 0 | 4208.8 |  | 4208.8 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 277 - S82 - Division 31 |  | 10% | MLJ | Brian | FALSE | TRUE | FALSE
2554 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - S8 | 27148 | 0 |  |  | 0 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 277 - S82 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2555 | DRIVE PILES AND INSTALL LAGGING FOR SOE - S8 | 68282 | 40969.2 | 27312.8 |  | 68282 | 04- RESAND: Coney Island I (Site 8) | Y- S82 | 277 - S82 - Division 31 | lagging complete | 100% | MLJ | Brian | FALSE | TRUE | FALSE
2556 | CON EDISON ELECTRICAL UTILITY SERVICE FEE | 51926.66 | 0 |  |  | 0 | 04- RESAND: Allowance | Z- Allowance | 278 - Allowance - Division 1 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2557 | NATIONAL GRID GAS UTILITY -CIAC | 141408 | 0 |  |  | 0 | 04- RESAND: Allowance | Z- Allowance | 278 - Allowance - Division 1 |  | 0% | MLJ | Sully | FALSE | FALSE | TRUE
2558 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2559 | Mechanical Terminations(Dampers, Heaters, Motors) | 43800 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2560 | Survey | 65700 | 65700 |  |  | 65700 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 100% | Five Star | Kurston | FALSE | FALSE | TRUE
2561 | Switches and Receptacles | 10950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2562 | Switchgear & Panelboard Energization | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2563 | Switchgear & Panelboard Installation | 65700 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2564 | Switchgear & Panelboard Terminations | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2565 | Switchgear & Panelboard Testing | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 026 - SG2 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2566 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-2 | 12713 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 027 - SG2 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2567 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-2 | 5028 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 027 - SG2 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2568 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-2 | 486 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | C- SG2 | 027 - SG2 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2569 | Gaskets | 36000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2570 | Wire Insulation | 37500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2571 | Assumed Flooring Material (Slab Penetrations) | 36000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2572 | Vinyl Membrane and Mastic | 53652 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2573 | Caulk | 103500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2574 | Fibrous Slate | 14025 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2575 | Waterproofing | 9942 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2576 | Underground Utility Materials | 46800 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | ATCO | Kurston | FALSE | FALSE | TRUE
2577 | Remove existing paint and plaster - cellar | 60000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2578 | Remove sump pump - cellar | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2579 | Remove existing vent / window and frame - cellar and 1st floor | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2580 | Remove existing door, frame and hardware - cellar and 1st floor | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2581 | Remove Areaway slab and drain - cellar | 60000 | 6000 |  |  | 6000 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 10% | MLJ | Ricky | FALSE | FALSE | TRUE
2582 | Remove Areaway grate - cellar | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2583 | Sawcut and remove portion of areaway wall - cellar | 60000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2584 | Saw cut openings through slab for cellar ventilation / exhaust ducts | 40000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2585 | Remove window sill - 1st floor | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2586 | Remove Existing Ramp - 1st floor | 80000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2587 | Existing Ramp railing to be be removed - 1st floor | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2588 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2589 | Remove floor finish - 2nd floor | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
2590 | Remove stove - 2nd floor | 4000 | 4000 |  |  | 4000 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
2591 | Remove CMU wall - 2nd floor | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
2592 | Remove sinks - 2nd floor | 4000 | 4000 |  |  | 4000 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
2593 | Remove interior walls - 2nd floor | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
2594 | Patch floor and make smooth - 2nd floor | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2595 | Cut openings in slab - 2nd floor | 40000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | RIcky | FALSE | FALSE | TRUE
2596 | Remove existing windows - 2nd floor | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2597 | Remove appliances - 2nd floor | 6000 | 6000 |  |  | 6000 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
2598 | Remove ceiling finishes - 2nd floor | 20000 | 20000 |  |  | 20000 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
2599 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 |  |  | 6000 | 02- RESAND: Surfside Gardens | D- SG3 | 028 - SG3 - Division 2 |  | 100% | MLJ | Kurston | FALSE | FALSE | TRUE
2600 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - SG-3 | 52908 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | MLJ | Brian | FALSE | FALSE | TRUE
2601 | DRILL & GROUT DOWELS - SG-3 | 7874 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2602 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-3 | 42713 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2603 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-3 | 30285 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2604 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-3 | 30854 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2605 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG-3 | 4329 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2606 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - SG-3 | 50274 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2607 | Footing/Pier | 17233 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2608 | Retaining Walls | 2856 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2609 | Entrance Slab | 13291 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2610 | Concrete Shelf | 6304 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2611 | New Concrete Curb Next to Existing Wall | 242 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2612 | Boiler Room Concrete Curb | 4178 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | Tonage | Ricky | FALSE | FALSE | TRUE
2613 | GFRP Sikawrap 100 G | 60346 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 029 - SG3 - Division 3 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2614 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-3 | 378 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 030 - SG3 - Division 4 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2615 | Overhead protection for Masonry | 24710 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 030 - SG3 - Division 4 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2616 | 6" vertically reinforced CMU | 132685 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 030 - SG3 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2617 | 2" Face brick | 410182 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 030 - SG3 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2618 | 2" rigid Insulation | 19418 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 030 - SG3 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2619 | Coping Stone C1/A-300 | 22968 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 030 - SG3 - Division 4 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2620 | MATERIAL AND FABRICATION | 21224 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 031 - SG3 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
2621 | INSTALLATION | 37400 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 031 - SG3 - Division 5 |  | 0% | Weir Welding | Ricky | FALSE | FALSE | TRUE
2622 | Temporary Aluminum Over Pass Stairs | 57196 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 031 - SG3 - Division 5 |  | 0% | E&Y | Ricky | FALSE | FALSE | TRUE
2623 | PENETRATION FIRESTOPPING EXTG BLDG - SG-3 | 11505 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 032 - SG3 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2624 | JOINT SEALANTS EXTG BLDGS - SG-3 | 11505 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 032 - SG3 - Division 7 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2625 | Bituthene 4000 waterproofing membrane | 17281 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 032 - SG3 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2626 | GE Elemax 2600 Silicone air and vapor barrier | 25531 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 032 - SG3 - Division 7 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2627 | Crystalline Waterproofing at perimeter walls | 50313 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 032 - SG3 - Division 7 |  | 0% | Dstar | Ricky | FALSE | FALSE | TRUE
2628 | Waterproofing at foundation walls | 17020 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 032 - SG3 - Division 7 |  | 0% | DStar | Ricky | FALSE | FALSE | TRUE
2629 | Doors, Frames & Hardware - Labor | 5838 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 033 - SG3 - Division 8 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2630 | Furnish Doors | 8362 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 034 - SG3 - Division 9 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2631 | Layout | 5658 | 5658 |  |  | 5658 | 02- RESAND: Surfside Gardens | D- SG3 | 034 - SG3 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2632 | Loading | 8744 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 034 - SG3 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2633 | Framing & Drywall - Materials | 13115 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 034 - SG3 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2634 | Framing- Labor | 20060 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 034 - SG3 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2635 | Drywall - Labor | 23660 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 034 - SG3 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2636 | Tape/ Spackle finishes | 18517 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 034 - SG3 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2637 | Stucco | 10183 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 034 - SG3 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | FALSE | TRUE
2638 | Resilient Flooring and base - SG-3 | 15640 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 034 - SG3 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | FALSE | TRUE
2639 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-3 | 45295 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 035 - SG3 - Division 10 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2640 | Wiper wall panel | 4851 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 035 - SG3 - Division 10 |  | 0% | Faxa | Ricky | FALSE | FALSE | TRUE
2641 | Address Signs | 4950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 035 - SG3 - Division 10 |  | 0% | MLJ | Kurston | FALSE | FALSE | TRUE
2642 | Clean and refurbish landing device components in the pit | 4000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2643 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2644 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2645 | Replace oil buffers | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2646 | Replace compensation guidance system per dwgs | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2647 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2648 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2649 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2650 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2651 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2652 | Wire brush sills and support (at the first floor only) | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2653 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2654 | Replace pit lights and outlets | 3000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2655 | Replace all pit stop switches and light switches | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2656 | Repair/replace pit access doors and hardware | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2657 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2658 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2659 | Clean and paint buffer inspection ladders | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2660 | Clean out pit of all dirt and debris | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2661 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 036 - SG3 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | FALSE | TRUE
2662 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 6124.05 |  |  | 6124.05 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 45% | Vital | Kurston | FALSE | FALSE | TRUE
2663 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1056 | 105.6 |  |  | 105.6 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 10% | Vital | Kurston | FALSE | FALSE | TRUE
2664 | ESCUTCHEONS FOR PLUMBING PIPING | 1096 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2665 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 5940 | 4158 |  |  | 4158 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 70% | Vital | Kurston | FALSE | FALSE | TRUE
2666 | HANGERS AND SUPPORTS | 11512 | 9209.6 |  |  | 9209.6 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 80% | Vital | Kurston | FALSE | FALSE | TRUE
2667 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2668 | DOMESTIC WATER PIPING | 137444 | 109955.2 |  |  | 109955.2 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 80% | Vital | Kurston | FALSE | FALSE | TRUE
2669 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 13838 |  |  | 13838 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 85% | Vital | Kurston | FALSE | FALSE | TRUE
2670 | SANITARY WASTE PIPING | 135254 | 108203.2 |  |  | 108203.2 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 80% | Vital | Kurston | FALSE | FALSE | TRUE
2671 | SANITARY WASTE PIPING SPECIALTIES | 47078 | 42370.2 |  |  | 42370.2 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
2672 | STORM DRAINAGE PIPING SPECIALTIES | 47078 | 18831.2 |  |  | 18831.2 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 40% | Vital | Kurston | FALSE | FALSE | TRUE
2673 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 417998 | 41799.8 |  |  | 41799.8 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 10% | Vital | Kurston | FALSE | FALSE | TRUE
2674 | GAS SERVICE AND PIPING | 2261 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 0% | Vital | Kurston | FALSE | FALSE | TRUE
2675 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 13266 | 13266 |  |  | 13266 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 100% | Vital | Kurston | FALSE | FALSE | TRUE
2676 | Plumbing Pipe Insulation | 35750 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 0% | Tristan | Ricky | FALSE | FALSE | TRUE
2677 | Heat Trace | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 037 - SG3 - Division 22 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2678 | Survey | 66000 | 66000 |  |  | 66000 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 100% | Welkin | Sully | FALSE | FALSE | TRUE
2679 | Exhaust Fans: Furnish | 3960 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2680 | Exhaust Fans: Install | 14795 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2681 | Steam Unit Heaters: Furnish | 1100 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2682 | Steam Unit Heaters: Install | 17600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2683 | Condensate Return Unit: Furnish | 7700 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2684 | Condensate Return Unit: Install | 24200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2685 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2686 | Heating and Ventilation Unit: Install | 25300 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2687 | Steam Traps: Furnish | 3080 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2688 | Steam Traps: Install | 25850 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2689 | Vacuum Pump Unit: Furnish | 17600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2690 | Vacuum Pump Unit: Install | 27500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2691 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 290565 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2692 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 445500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2693 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 176000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2694 | Mechanical Pipe: Hydrostatic Testing | 6435 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2695 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 33000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2696 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 93500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2697 | HVAC Ductwork: Testing & Balancing | 3300 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2698 | Controls: Furnish and Install: Devices | 82500 | 37125 |  |  | 37125 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 45% | Welkin | Sully | FALSE | FALSE | TRUE
2699 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 |  |  | 41800 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 95% | Welkin | Sully | FALSE | FALSE | TRUE
2700 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2701 | Controls: Connect to Final Termination Points | 8800 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2702 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2703 | Insulation: Furnish and Install: Ductwork Insulation | 16500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2704 | Insulation: Furnish and Install: Piping Insulation | 33000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2705 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 038 - SG3 - Division 23 |  | 0% | Welkin | Sully | FALSE | FALSE | TRUE
2706 | ATS Energization | 13688 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2707 | ATS Installation | 194250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2708 | ATS Terminations | 13875 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2709 | ATS Testing | 13688 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2710 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2711 | Cabling - Interior Branch (1/0 & Smaller) | 164250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2712 | Cabling - Risers & Feeders (2/0 & Larger) | 394200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2713 | Conduit - Branch Circuits (1 1/2" & Smaller) | 222000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2714 | Conduit - Risers (2" & Larger) | 399600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2715 | Demolition/Temp Light & Power | 54750 | 24637.5 |  |  | 24637.5 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 45% | Five Star | Kurston | FALSE | FALSE | TRUE
2716 | Firestopping | 5250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2717 | Foundation Coring | 21000 | 1050 |  |  | 1050 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 5% | Five Star | Kurston | FALSE | FALSE | TRUE
2718 | Lighting Controls | 31500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2719 | Lighting Remove & Re-install | 54203 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2720 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2721 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2722 | Survey | 65700 | 32850 |  |  | 32850 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 50% | Five Star | Kurston | FALSE | FALSE | TRUE
2723 | Switchgear & Panelboard Energization | 32850 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2724 | Switchgear & Panelboard Installation | 394200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2725 | Switchgear & Panelboard Terminations | 32850 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2726 | Switchgear & Panelboard Testing | 32850 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 039 - SG3 - Division 26 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2727 | Fire Alarm Conduit | 27375 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 040 - SG3 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2728 | Fire Alarm Wiring | 24638 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 040 - SG3 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2729 | Fire Alarm Devices | 19710 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 040 - SG3 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2730 | Fire Alarm Programming & Pretest | 2738 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 040 - SG3 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2731 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 040 - SG3 - Division 28 |  | 0% | Five Star | Kurston | FALSE | FALSE | TRUE
2732 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-3 | 15538 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 041 - SG3 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2733 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-3 | 6285 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 041 - SG3 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2734 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-3 | 625 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | D- SG3 | 041 - SG3 - Division 31 |  | 0% | MLJ | Ricky | FALSE | FALSE | TRUE
2735 | Gaskets | 45000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 0% | ATCO | Kurston | FALSE |  | TRUE
2736 | Wire Insulation | 37500 | 37500 |  |  | 37500 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | ATCO | Kurston | FALSE | TRUE | TRUE
2737 | Assumed Flooring Material (Slab Penetrations) | 46800 | 46800 |  |  | 46800 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 | 1st and 2nd floor penetrations complete | 100% | ATCO | Kurston | FALSE |  | TRUE
2738 | Pipe Insulation | 15750 | 15750 |  |  | 15750 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | ATCO | Kurston | FALSE | TRUE | TRUE
2739 | Vinyl Membrane and Mastic | 43248 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 0% | ATCO | Kurston | FALSE |  | TRUE
2740 | Caulk | 90000 | 20250 |  |  | 20250 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 22.5% | ATCO | Kurston | FALSE |  | TRUE
2741 | Fibrous Slate | 14535 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 0% | ATCO | Kurston | FALSE |  | TRUE
2742 | Waterproofing | 9942 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 0% | ATCO | Kurston | FALSE |  | TRUE
2743 | Underground Utility Materials | 54600 | 54600 |  |  | 54600 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | ATCO | Kurston | FALSE | TRUE | TRUE
2744 | Remove existing paint and plaster - cellar | 60000 | 60000 |  |  | 60000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2745 | Remove sump pump - cellar | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 0% | MLJ | Kurston | FALSE |  | TRUE
2746 | Remove existing vent / window and frame - cellar and 1st floor | 20000 | 20000 |  |  | 20000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2747 | Remove existing door, frame and hardware - cellar and 1st floor | 20000 | 10000 |  |  | 10000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 | Metal drop down gate has been removed; door still there | 50% | MLJ | Kurston | FALSE |  | TRUE
2748 | Remove Areaway slab and drain - cellar | 60000 | 60000 |  |  | 60000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2749 | Remove Areaway grate - cellar | 20000 | 20000 |  |  | 20000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2750 | Sawcut and remove portion of areaway wall - cellar | 60000 | 60000 |  |  | 60000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Ricky | FALSE |  | TRUE
2751 | Saw cut openings through slab for cellar ventilation / exhaust ducts | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Ricky | FALSE |  | TRUE
2752 | Remove window sill - 1st floor | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 0% | MLJ | Kurston | FALSE |  | TRUE
2753 | Remove Existing Ramp - 1st floor | 80000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 | ramp near building entrance | 50% | MLJ | Kurston | FALSE |  | TRUE
2754 | Existing Ramp railing to be be removed - 1st floor | 20000 | 14000 |  |  | 14000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 | ramp near building entrance | 70% | MLJ | Kurston | FALSE |  | TRUE
2755 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Ricky | FALSE |  | TRUE
2756 | Remove floor finish - 2nd floor | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE |  | TRUE
2757 | Remove stove - 2nd floor | 4000 | 4000 |  |  | 4000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2758 | Remove CMU wall - 2nd floor | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2759 | Remove sinks - 2nd floor | 4000 | 4000 |  |  | 4000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2760 | Remove interior walls - 2nd floor | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2761 | Patch floor and make smooth - 2nd floor | 20000 | 20000 |  |  | 20000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE |  | TRUE
2762 | Cut openings in slab - 2nd floor | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | RIcky | FALSE |  | TRUE
2763 | Remove existing windows - 2nd floor | 20000 | 20000 |  |  | 20000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE |  | TRUE
2764 | Remove appliances - 2nd floor | 6000 | 6000 |  |  | 6000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2765 | Remove ceiling finishes - 2nd floor | 20000 | 20000 |  |  | 20000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2766 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 |  |  | 6000 | 02- RESAND: Surfside Gardens | E- SG4 | 042 - SG4 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2767 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - SG-4 | 106025 | 79518.75 | 26506.25 |  | 106025 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 |  | 100% | MLJ | Brian | FALSE | FALSE | FALSE
2768 | DRILL & GROUT DOWELS - SG-4 | 25962 | 25962 |  |  | 25962 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 | doweling for masonry shelf | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2769 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-4 | 25126 | 25126 |  |  | 25126 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2770 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-4 | 49048 | 36786 |  |  | 36786 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 |  | 75% | MLJ | Ricky | FALSE | TRUE | TRUE
2771 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-4 | 23998 | 23998 |  |  | 23998 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2772 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG-4 | 4137 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2773 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - SG-4 | 50274 | 50274 |  |  | 50274 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2774 | Footing/Pier | 20904 | 20904 |  |  | 20904 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 | for rebar | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
2775 | Retaining Walls | 4692 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 |  | 0% | Tonage | Ricky | FALSE | TRUE | TRUE
2776 | Entrance Slab | 20706 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 |  | 0% | Tonage | Ricky | FALSE | TRUE | TRUE
2777 | Concrete Shelf | 4320 | 4320 |  |  | 4320 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 |  | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
2778 | New Concrete Curb Next to Existing Wall | 234 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 |  | 0% | Tonage | Ricky | FALSE | TRUE | TRUE
2779 | Boiler Room Concrete Curb | 3354 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 |  | 0% | Tonage | Ricky | FALSE | TRUE | TRUE
2780 | GFRP Sikawrap 100 G | 87230 | 87230 |  |  | 87230 | 02- RESAND: Surfside Gardens | E- SG4 | 043 - SG4 - Division 3 |  | 100% | Faxa | Ricky | FALSE | TRUE | TRUE
2781 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-4 | 270 | 270 |  |  | 270 | 02- RESAND: Surfside Gardens | E- SG4 | 044 - SG4 - Division 4 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2782 | Overhead protection for Masonry | 35611 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 044 - SG4 - Division 4 | Not required so billing along with Masonry work % | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2783 | 6" vertically reinforced CMU | 126280 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 044 - SG4 - Division 4 | 50% for all materials on site | 0% | Faxa | Ricky | FALSE | TRUE | TRUE | 0%
2784 | 2" Face brick | 538422 | 53842.2 |  |  | 53842.2 | 02- RESAND: Surfside Gardens | E- SG4 | 044 - SG4 - Division 4 | 25% for half materials on site | 10% | Faxa | Ricky | FALSE | TRUE | TRUE | 0%
2785 | 2" rigid Insulation | 18480 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 044 - SG4 - Division 4 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
2786 | Coping Stone C1/A-300 | 18586 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 044 - SG4 - Division 4 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
2787 | MATERIAL AND FABRICATION | 21224 | 21224 |  |  | 21224 | 02- RESAND: Surfside Gardens | E- SG4 | 045 - SG4 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | TRUE | TRUE
2788 | INSTALLATION | 37400 | 37400 |  |  | 37400 | 02- RESAND: Surfside Gardens | E- SG4 | 045 - SG4 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | TRUE | TRUE
2789 | Temporary Aluminum Over Pass Stairs | 57196 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 045 - SG4 - Division 5 |  | 0% | E&Y | Ricky | FALSE | TRUE | TRUE
2790 | PENETRATION FIRESTOPPING EXTG BLDG - SG-4 | 11505 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 046 - SG4 - Division 7 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2791 | JOINT SEALANTS EXTG BLDGS - SG-4 | 11505 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 046 - SG4 - Division 7 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2792 | Bituthene 4000 waterproofing membrane | 21142 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 046 - SG4 - Division 7 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
2793 | GE Elemax 2600 Silicone air and vapor barrier | 36905 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 046 - SG4 - Division 7 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
2794 | Crystalline Waterproofing at perimeter walls | 42694 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 046 - SG4 - Division 7 |  | 0% | Dstar | Ricky | FALSE | TRUE | TRUE
2795 | Waterproofing at foundation walls | 17020 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 046 - SG4 - Division 7 |  | 0% | DStar | Ricky | FALSE | TRUE | TRUE
2796 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-4 | 1050 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 047 - SG4 - Division 8 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2797 | Doors, Frames & Hardware - Labor | 13066 | 7000 |  |  | 7000 | 02- RESAND: Surfside Gardens | E- SG4 | 047 - SG4 - Division 8 |  | 53.57% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2798 | Furnish Doors | 8362 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 048 - SG4 - Division 9 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2799 | Layout | 7715 | 7715 |  |  | 7715 | 02- RESAND: Surfside Gardens | E- SG4 | 048 - SG4 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2800 | Loading | 9001 | 9001 |  |  | 9001 | 02- RESAND: Surfside Gardens | E- SG4 | 048 - SG4 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2801 | Framing & Drywall - Materials | 17638 | 17638 |  |  | 17638 | 02- RESAND: Surfside Gardens | E- SG4 | 048 - SG4 - Division 9 |  | 100% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2802 | Framing- Labor | 7458 | 6712.2 |  |  | 6712.2 | 02- RESAND: Surfside Gardens | E- SG4 | 048 - SG4 - Division 9 |  | 90% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2803 | Drywall - Labor | 15944 | 14349.6 |  |  | 14349.6 | 02- RESAND: Surfside Gardens | E- SG4 | 048 - SG4 - Division 9 |  | 90% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2804 | Tape/ Spackle finishes | 23660 | 21294 |  |  | 21294 | 02- RESAND: Surfside Gardens | E- SG4 | 048 - SG4 - Division 9 |  | 90% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2805 | Stucco | 10183 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 048 - SG4 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2806 | Resilient Flooring and base - SG-4 | 27600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 048 - SG4 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | TRUE | TRUE
2807 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-4 | 51471 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 049 - SG4 - Division 10 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2808 | WINDOW FLOODGATES (8.06 AND 8.14) - SG-4 | 11690 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 049 - SG4 - Division 10 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2809 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE (8.15) - SG-4 | 140863 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 049 - SG4 - Division 10 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2810 | Wiper wall panel | 3234 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 049 - SG4 - Division 10 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
2811 | Temporary Egress Stair Storage Sign | 2640 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 049 - SG4 - Division 10 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2812 | Address Signs | 4950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 049 - SG4 - Division 10 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2813 | Clean and refurbish landing device components in the pit | 4000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2814 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2815 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2816 | Replace oil buffers | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2817 | Replace compensation guidance system per dwgs | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2818 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2819 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2820 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2821 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2822 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2823 | Wire brush sills and support (at the first floor only) | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2824 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2825 | Replace pit lights and outlets | 3000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2826 | Replace all pit stop switches and light switches | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2827 | Repair/replace pit access doors and hardware | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2828 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2829 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2830 | Clean and paint buffer inspection ladders | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2831 | Clean out pit of all dirt and debris | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2832 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 050 - SG4 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2833 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 8845.85 |  |  | 8845.85 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 65% | Vital | Kurston | FALSE | TRUE | TRUE
2834 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1056 | 950.4 |  |  | 950.4 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 90% | Vital | Kurston | FALSE | TRUE | TRUE
2835 | ESCUTCHEONS FOR PLUMBING PIPING | 1096 | 986.4 |  |  | 986.4 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 90% | Vital | Kurston | FALSE | TRUE | TRUE
2836 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 4620 | 2772 |  |  | 2772 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 60% | Vital | Kurston | FALSE | TRUE | TRUE
2837 | HANGERS AND SUPPORTS | 11509 | 9207.2 |  |  | 9207.2 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 80% | Vital | Kurston | FALSE | TRUE | TRUE
2838 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 0% | Vital | Kurston | FALSE | TRUE | TRUE
2839 | DOMESTIC WATER PIPING | 140998 | 126898.2 |  |  | 126898.2 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 90% | Vital | Kurston | FALSE | TRUE | TRUE
2840 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 8140 |  |  | 8140 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 50% | Vital | Kurston | FALSE | TRUE | TRUE
2841 | SANITARY WASTE PIPING | 122074 | 109866.6 |  |  | 109866.6 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 90% | Vital | Kurston | FALSE | TRUE | TRUE
2842 | SANITARY WASTE PIPING SPECIALTIES | 45569 | 41012.1 |  |  | 41012.1 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 90% | Vital | Kurston | FALSE | TRUE | TRUE
2843 | STORM DRAINAGE PIPING SPECIALTIES | 45569 | 18227.6 |  |  | 18227.6 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 40% | Vital | Kurston | FALSE | TRUE | TRUE
2844 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 324500 | 32450 |  |  | 32450 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 10% | Vital | Kurston | FALSE | TRUE | TRUE
2845 | GAS SERVICE AND PIPING | 6369 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 0% | Vital | Kurston | FALSE | TRUE | TRUE
2846 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 |  |  | 5357 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 100% | Vital | Kurston | FALSE | TRUE | TRUE
2847 | Plumbing Pipe Insulation | 35464 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 0% | Tristan | Ricky | FALSE | TRUE | TRUE
2848 | Heat Trace | 5475 | 821.25 |  |  | 821.25 | 02- RESAND: Surfside Gardens | E- SG4 | 051 - SG4 - Division 22 |  | 15% | Five Star | Kurston | FALSE | TRUE | TRUE
2849 | Survey | 66000 | 66000 |  |  | 66000 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
2850 | Exhaust Fans: Furnish | 3960 | 3960 |  |  | 3960 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
2851 | Exhaust Fans: Install | 11495 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2852 | Steam Unit Heaters: Furnish | 1100 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2853 | Steam Unit Heaters: Install | 14300 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2854 | Condensate Return Unit: Furnish | 7700 | 7700 |  |  | 7700 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
2855 | Condensate Return Unit: Install | 20900 | 20900 |  |  | 20900 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
2856 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2857 | Heating and Ventilation Unit: Install | 22000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2858 | Steam Traps: Furnish | 2420 | 2420 |  |  | 2420 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
2859 | Steam Traps: Install | 18150 | 11550.66 |  |  | 11550.66 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 63.64% | Welkin | Sully | FALSE | TRUE | TRUE
2860 | Vacuum Pump Unit: Furnish | 17600 | 17600 |  |  | 17600 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
2861 | Vacuum Pump Unit: Install | 24200 | 24200 |  |  | 24200 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
2862 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 189613 | 170651.7 |  |  | 170651.7 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 90% | Welkin | Sully | FALSE | TRUE | TRUE
2863 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 312400 | 281160 |  |  | 281160 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 90% | Welkin | Sully | FALSE | TRUE | TRUE
2864 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 96250 | 86625 |  |  | 86625 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 90% | Welkin | Sully | FALSE | TRUE | TRUE
2865 | Mechanical Pipe: Hydrostatic Testing | 3163 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2866 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 19250 | 13475 |  |  | 13475 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 70% | Welkin | Sully | FALSE | TRUE | TRUE
2867 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 38500 | 26950 |  |  | 26950 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 70% | Welkin | Sully | FALSE | TRUE | TRUE
2868 | HVAC Ductwork: Testing & Balancing | 2200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2869 | Controls: Furnish and Install: Devices | 82500 | 53625 |  |  | 53625 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 65% | Welkin | Sully | FALSE | TRUE | TRUE
2870 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 |  |  | 41800 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 95% | Welkin | Sully | FALSE | TRUE | TRUE
2871 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2872 | Controls: Connect to Final Termination Points | 88000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2873 | Controls: Controls Testing | 6600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2874 | Insulation: Furnish and Install: Ductwork Insulation | 12650 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2875 | Insulation: Furnish and Install: Piping Insulation | 25300 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2876 | Insulation: Furnish and Install: Equipment Insulation | 12650 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 052 - SG4 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
2877 | ATS Energization | 13688 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
2878 | ATS Installation | 191625 | 172462.5 |  |  | 172462.5 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 90% | Five Star | Kurston | FALSE | TRUE | TRUE
2879 | ATS Terminations | 13688 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
2880 | ATS Testing | 13688 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
2881 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 20531.25 |  |  | 20531.25 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 75% | Five Star | Kurston | FALSE | FALSE | TRUE
2882 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
2883 | Cabling - Risers & Feeders (2/0 & Larger) | 473040 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
2884 | Conduit - Branch Circuits (1 1/2" & Smaller) | 273750 | 232687.5 |  |  | 232687.5 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 85% | Five Star | Kurston | FALSE | FALSE | TRUE
2885 | Conduit - Risers (2" & up) | 542025 | 514923.75 |  |  | 514923.75 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 95% | Five Star | Kurston | FALSE | FALSE | TRUE
2886 | Demolition/Temp Light & Power | 54750 | 35587.5 |  |  | 35587.5 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 65% | Five Star | Kurston | FALSE | FALSE | TRUE
2887 | Firestopping | 5250 | 4200 |  |  | 4200 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 80% | Five Star | Kurston | FALSE | TRUE | TRUE
2888 | Foundation Coring | 21000 | 21000 |  |  | 21000 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 100% | Five Star | Kurston | FALSE | TRUE | TRUE
2889 | Lighting Controls | 25200 | 6300 |  |  | 6300 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 25% | Five Star | Kurston | FALSE | TRUE | TRUE
2890 | Lighting Remove & Re-install | 54945 | 19230.75 |  |  | 19230.75 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 35% | Five Star | Kurston | FALSE | TRUE | TRUE
2891 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
2892 | Mechanical Terminations(Dampers, Heaters, Motors) | 56940 | 28470 |  |  | 28470 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 50% | Five Star | Kurston | FALSE | TRUE | TRUE
2893 | Survey | 65700 | 65700 |  |  | 65700 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 100% | Five Star | Kurston | FALSE | TRUE | TRUE
2894 | Switches and Receptacles | 10950 | 1095 |  |  | 1095 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 10% | Five Star | Kurston | FALSE | TRUE | TRUE
2895 | Switchgear & Panelboard Energization | 30113 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
2896 | Switchgear & Panelboard Installation | 361350 | 325215 |  |  | 325215 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 90% | Five Star | Kurston | FALSE | TRUE | TRUE
2897 | Switchgear & Panelboard Terminations | 30113 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
2898 | Switchgear & Panelboard Testing | 30113 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 053 - SG4 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
2899 | Fire Alarm Conduit | 16650 | 6660 |  |  | 6660 | 02- RESAND: Surfside Gardens | E- SG4 | 054 - SG4 - Division 28 |  | 40% | Five Star | Kurston | FALSE | FALSE | TRUE
2900 | Fire Alarm Wiring | 13140 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 054 - SG4 - Division 28 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
2901 | Fire Alarm Devices | 21900 | 5475 |  |  | 5475 | 02- RESAND: Surfside Gardens | E- SG4 | 054 - SG4 - Division 28 |  | 25% | Five Star | Kurston | FALSE | TRUE | TRUE
2902 | Fire Alarm Programming & Pretest | 2738 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 054 - SG4 - Division 28 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
2903 | Fire Alarm FDNY Approval | 2738 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 054 - SG4 - Division 28 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
2904 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-4 | 17656 | 15890.4 |  |  | 15890.4 | 02- RESAND: Surfside Gardens | E- SG4 | 055 - SG4 - Division 31 |  | 90% | MLJ | Ricky | FALSE | TRUE | TRUE
2905 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-4 | 7542 | 1885.5 |  |  | 1885.5 | 02- RESAND: Surfside Gardens | E- SG4 | 055 - SG4 - Division 31 |  | 25% | MLJ | Ricky | FALSE | TRUE | TRUE
2906 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-4 | 625 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | E- SG4 | 055 - SG4 - Division 31 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2907 | Gaskets | 22500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | ATCO | Kurston | FALSE | TRUE | TRUE
2908 | Wire Insulation | 37500 | 37500 |  |  | 37500 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | ATCO | Kurston | FALSE | TRUE | TRUE
2909 | Assumed Flooring Material (Slab Penetrations) | 43200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | ATCO | Kurston | FALSE | TRUE | TRUE
2910 | Pipe Insulation | 151200 | 151200 |  |  | 151200 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | ATCO | Kurston | FALSE | TRUE | TRUE
2911 | Mudded Joint Packing | 25086 | 25086 |  |  | 25086 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | ATCO | Kurston | FALSE | TRUE | TRUE
2912 | Vinyl Membrane and Mastic | 43248 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | ATCO | Kurston | FALSE | TRUE | TRUE
2913 | Caulk | 108000 | 58500 |  |  | 58500 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 54.17% | ATCO | Kurston | FALSE | TRUE | TRUE
2914 | Fibrous Slate | 15810 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | ATCO | Kurston | FALSE | TRUE | TRUE
2915 | Waterproofing | 9942 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 | waterproofing | 0% | ATCO | Kurston | FALSE | TRUE | TRUE
2916 | Underground Utility Materials | 54600 | 54600 |  |  | 54600 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | ATCO | Kurston | FALSE | TRUE | TRUE
2917 | Remove existing paint and plaster - cellar | 60000 | 60000 |  |  | 60000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2918 | Remove sump pump - cellar | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2919 | Remove existing vent / window and frame - cellar and 1st floor | 20000 | 20000 |  |  | 20000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2920 | Remove existing door, frame and hardware | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2921 | Remove Areaway slab and drain | 60000 | 60000 |  |  | 60000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2922 | Remove Areaway grate | 20000 | 20000 |  |  | 20000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2923 | Sawcut and remove portion of areaway wall | 60000 | 60000 |  |  | 60000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2924 | Prepare existing wall surface for paint | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2925 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2926 | Remove window sill - 1st floor | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2927 | Remove Existing Ramp - 1st floor | 80000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2928 | Existing Ramp railing to be be removed - 1st floor | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2929 | Sawcut slab opening for mechanical - 1st floor | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2930 | Remove floor finish - 2nd floor | 40000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2931 | Remove stove - 2nd floor | 4000 | 4000 |  |  | 4000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2932 | Remove CMU wall - 2nd floor | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2933 | Remove sinks - 2nd floor | 4000 | 4000 |  |  | 4000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2934 | Remove interior walls - 2nd floor | 40000 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2935 | Patch floor and make smooth - 2nd floor | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2936 | Cut openings in slab - 2nd floor | 40000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | MLJ | RIcky | FALSE | TRUE | TRUE
2937 | Remove existing windows - 2nd floor | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2938 | Remove appliances - 2nd floor | 6000 | 6000 |  |  | 6000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2939 | Remove ceiling finishes - 2nd floor | 20000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2940 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 |  |  | 6000 | 02- RESAND: Surfside Gardens | F- SG5 | 056 - SG5 - Division 2 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2941 | FORM FLOOD BARRIER FOUNDATIONS - SG-5 | 86514 | 64885.5 | 21628.5 |  | 86514 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 |  | 100% | MLJ | Brian | FALSE | FALSE | FALSE
2942 | DRILL & GROUT DOWELS - SG-5 | 26772 | 26772 |  |  | 26772 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 | doweling for masonry shelf | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2943 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-5 | 41980 | 41980 |  |  | 41980 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 | All windows removed; none have been infilled yet | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2944 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-5 | 45756 | 22878 |  |  | 22878 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 |  | 50% | MLJ | Ricky | FALSE | TRUE | TRUE
2945 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-5 | 23998 | 23998 |  |  | 23998 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
2946 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG-5 | 3591 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2947 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - SG-5 | 168000 | 42000 |  |  | 42000 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 |  | 25% | MLJ | Ricky | FALSE | TRUE | TRUE
2948 | Footing/Pier | 24258 | 12129 |  |  | 12129 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 | rebar | 50% | Tonage | Ricky | FALSE | TRUE | TRUE
2949 | Retaining Walls | 4692 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 |  | 0% | Tonage | Ricky | FALSE | TRUE | TRUE
2950 | Entrance Slab | 20400 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 |  | 0% | Tonage | Ricky | FALSE | TRUE | TRUE
2951 | Concrete Shelf | 4320 | 4320 |  |  | 4320 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 |  | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
2952 | New Concrete Curb Next to Existing Wall | 234 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 |  | 0% | Tonage | Ricky | FALSE | TRUE | TRUE
2953 | Boiler Room Concrete Curb | 3354 | 3354 |  |  | 3354 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 |  | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
2954 | GFRP Sikawrap 100 G | 83226 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 057 - SG5 - Division 3 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
2955 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-5 | 270 | 270 |  |  | 270 | 02- RESAND: Surfside Gardens | F- SG5 | 058 - SG5 - Division 4 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
2956 | Overhead protection for Masonry | 34158 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 058 - SG5 - Division 4 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2957 | 6" vertically reinforced CMU | 123200 | 12320 |  |  | 12320 | 02- RESAND: Surfside Gardens | F- SG5 | 058 - SG5 - Division 4 | 50% for all materials on site | 10% | Faxa | Ricky | FALSE | TRUE | TRUE | 0%
2958 | 2" Face brick | 530612 | 53061.2 |  |  | 53061.2 | 02- RESAND: Surfside Gardens | F- SG5 | 058 - SG5 - Division 4 | 25% for half materials on site | 10% | Faxa | Ricky | FALSE | TRUE | TRUE | 0%
2959 | 2" rigid Insulation | 18480 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 058 - SG5 - Division 4 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
2960 | Coping Stone C1/A-300 | 17319 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 058 - SG5 - Division 4 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
2961 | MATERIAL AND FABRICATION | 38589 | 38589 |  |  | 38589 | 02- RESAND: Surfside Gardens | F- SG5 | 059 - SG5 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | TRUE | TRUE
2962 | INSTALLATION | 68000 | 68000 |  |  | 68000 | 02- RESAND: Surfside Gardens | F- SG5 | 059 - SG5 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | TRUE | TRUE
2963 | Temporary Aluminum Over Pass Stairs | 103992 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 059 - SG5 - Division 5 |  | 0% | E&Y | Ricky | FALSE | TRUE | TRUE
2964 | PENETRATION FIRESTOPPING EXTG BLDG - SG-5 | 19222 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 060 - SG5 - Division 7 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2965 | JOINT SEALANTS EXTG BLDGS - SG-5 | 19222 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 060 - SG5 - Division 7 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2966 | Bituthene 4000 waterproofing membrane | 21362 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 060 - SG5 - Division 7 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
2967 | GE Elemax 2600 Silicone air and vapor barrier | 35211 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 060 - SG5 - Division 7 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
2968 | Crystalline Waterproofing at perimeter walls | 42694 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 060 - SG5 - Division 7 |  | 0% | Dstar | Ricky | FALSE | TRUE | TRUE
2969 | Waterproofing at foundation walls | 17020 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 060 - SG5 - Division 7 |  | 0% | DStar | Ricky | FALSE | TRUE | TRUE
2970 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-5 | 1200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 061 - SG5 - Division 8 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2971 | Doors, Frames & Hardware - Labor | 5004 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 061 - SG5 - Division 8 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2972 | Furnish Doors | 6780 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 062 - SG5 - Division 9 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2973 | Layout | 4170 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 062 - SG5 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2974 | Loading | 6950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 062 - SG5 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2975 | Framing & Drywall - Materials | 14456 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 062 - SG5 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2976 | Framing- Labor | 16680 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 062 - SG5 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2977 | Drywall - Labor | 28914 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 062 - SG5 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2978 | Tape/ Spackle finishes | 13344 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 062 - SG5 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2979 | Stucco | 11008 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 062 - SG5 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
2980 | Resilient Flooring and base - SG-5 | 27600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 062 - SG5 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | TRUE | TRUE
2981 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-5 | 49413 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 063 - SG5 - Division 10 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2982 | WINDOW FLOODGATES (8.06 AND 8.14) - SG-5 | 27072 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 063 - SG5 - Division 10 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2983 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE (8.15) - SG-5 | 140863 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 063 - SG5 - Division 10 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
2984 | Wiper wall panel | 3333 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 063 - SG5 - Division 10 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
2985 | Temporary Egress Stair Storage Sign | 2400 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 063 - SG5 - Division 10 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2986 | Address Signs | 9000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 063 - SG5 - Division 10 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
2987 | Clean and refurbish landing device components in the pit | 4000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2988 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2989 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2990 | Replace oil buffers | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2991 | Replace compensation guidance system per dwgs | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2992 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2993 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2994 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2995 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2996 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2997 | Wire brush sills and support (at the first floor only) | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2998 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
2999 | Replace pit lights and outlets | 3000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
3000 | Replace all pit stop switches and light switches | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
3001 | Repair/replace pit access doors and hardware | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
3002 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
3003 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
3004 | Clean and paint buffer inspection ladders | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
3005 | Clean out pit of all dirt and debris | 2000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
3006 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 064 - SG5 - Division 14 |  | 0% | Dynasty Elevator | Ricky | FALSE | TRUE | TRUE
3007 | COMMON WORK RESULTS FOR PLUMBING | 14846 | 5938.4 |  |  | 5938.4 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 40% | Vital | Kurston | FALSE | TRUE | TRUE
3008 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 864 | 777.6 |  |  | 777.6 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 90% | Vital | Kurston | FALSE | FALSE | TRUE
3009 | ESCUTCHEONS FOR PLUMBING PIPING | 1196 | 837.2 |  |  | 837.2 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 70% | Vital | Kurston | FALSE | TRUE | TRUE
3010 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 4080 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 0% | Vital | Kurston | FALSE | TRUE | TRUE
3011 | HANGERS AND SUPPORTS | 12555 | 2511 |  |  | 2511 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 20% | Vital | Kurston | FALSE | FALSE | TRUE
3012 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2394 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 0% | Vital | Kurston | FALSE | TRUE | TRUE
3013 | DOMESTIC WATER PIPING | 108372 | 86697.6 |  |  | 86697.6 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 80% | Vital | Kurston | FALSE | TRUE | TRUE
3014 | DOMESTIC WATER PIPING SPECIALTIES | 17760 | 13320 |  |  | 13320 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 75% | Vital | Kurston | FALSE | TRUE | TRUE
3015 | SANITARY WASTE PIPING | 107844 | 80883 |  |  | 80883 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 75% | Vital | Kurston | FALSE | TRUE | TRUE
3016 | SANITARY WASTE PIPING SPECIALTIES | 22562 | 20305.8 |  |  | 20305.8 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 90% | Vital | Kurston | FALSE | TRUE | TRUE
3017 | STORM DRAINAGE PIPING SPECIALTIES | 46560 | 16296 |  |  | 16296 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 35% | Vital | Kurston | FALSE | TRUE | TRUE
3018 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 270000 | 40500 |  |  | 40500 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 15% | Vital | Kurston | FALSE | TRUE | TRUE
3019 | GAS SERVICE AND PIPING | 2112 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 0% | Vital | Kurston | FALSE | TRUE | TRUE
3020 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 10714 | 10714 |  |  | 10714 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 100% | Vital | Kurston | FALSE | TRUE | TRUE
3021 | Plumbing Pipe Insulation | 35464 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 0% | Tristan | Ricky | FALSE | TRUE | TRUE
3022 | Heat Trace | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 065 - SG5 - Division 22 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3023 | Survey | 72000 | 72000 |  |  | 72000 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3024 | Exhaust Fans: Furnish | 4320 | 4320 |  |  | 4320 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3025 | Exhaust Fans: Install | 8940 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3026 | Steam Unit Heaters: Furnish | 1200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3027 | Steam Unit Heaters: Install | 12000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3028 | Condensate Return Unit: Furnish | 8400 | 8400 |  |  | 8400 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3029 | Condensate Return Unit: Install | 19200 | 3840 |  |  | 3840 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 20% | Welkin | Sully | FALSE | TRUE | TRUE
3030 | Heating and Ventilation Unit: Furnish | 7800 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3031 | Heating and Ventilation Unit: Install | 20400 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3032 | Steam Traps: Furnish | 1920 | 1920 |  |  | 1920 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3033 | Steam Traps: Install | 15600 | 7800 |  |  | 7800 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 50% | Welkin | Sully | FALSE | TRUE | TRUE
3034 | Vacuum Pump Unit: Furnish | 19200 | 19200 |  |  | 19200 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3035 | Vacuum Pump Unit: Install | 22800 | 4560 |  |  | 4560 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 20% | Welkin | Sully | FALSE | TRUE | TRUE
3036 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 104700 | 94230.005 |  |  | 94230.005 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 90% | Welkin | Sully | FALSE | TRUE | TRUE
3037 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 167200 | 150480 |  |  | 150480 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 90% | Welkin | Sully | FALSE | TRUE | TRUE
3038 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 50400 | 45360 |  |  | 45360 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 90% | Welkin | Sully | FALSE | TRUE | TRUE
3039 | Mechanical Pipe: Hydrostatic Testing | 1925 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3040 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 10800 | 8640 |  |  | 8640 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 80% | Welkin | Sully | FALSE | TRUE | TRUE
3041 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 17600 | 14080 |  |  | 14080 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 80% | Welkin | Sully | FALSE | TRUE | TRUE
3042 | HVAC Ductwork: Testing & Balancing | 1200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3043 | Controls: Furnish and Install: Devices | 90000 | 58500 |  |  | 58500 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 65% | Welkin | Sully | FALSE | TRUE | TRUE
3044 | Controls: Furnish and Install: Controls Conduit | 42000 | 39900 |  |  | 39900 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 95% | Welkin | Sully | FALSE | TRUE | TRUE
3045 | Controls: Furnish and Install: Controls Wiring | 12000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3046 | Controls: Connect to Final Termination Points | 9000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3047 | Controls: Controls Testing | 7200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3048 | Insulation: Furnish and Install: Ductwork Insulation | 12650 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3049 | Insulation: Furnish and Install: Piping Insulation | 25300 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3050 | Insulation: Furnish and Install: Equipment Insulation | 13800 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 066 - SG5 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3051 | ATS Energization | 12000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3052 | ATS Installation | 168000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3053 | ATS Terminations | 12000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3054 | ATS Testing | 12000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3055 | Bypass Connections (Misc Panels, Re-routes, etc) | 30000 | 9000 |  |  | 9000 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 30% | Five Star | Kurston | FALSE | FALSE | TRUE
3056 | Cabling - Interior Branch (1/0 & Smaller) | 160000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3057 | Cabling - Risers & Feeders (2/0 & Larger) | 354780 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3058 | Conduit - Branch Circuits (1 1/2" & Smaller) | 219000 | 109500 |  |  | 109500 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 50% | Five Star | Kurston | FALSE | FALSE | TRUE
3059 | Conduit - Risers (2" & Larger) | 394200 | 315360 |  |  | 315360 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 80% | Five Star | Kurston | FALSE | FALSE | TRUE
3060 | Demolition/Temp Light & Power | 60000 | 27000 |  |  | 27000 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 45% | Five Star | Kurston | FALSE | FALSE | TRUE
3061 | Firestopping | 6000 | 1200 |  |  | 1200 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 20% | Five Star | Kurston | FALSE | TRUE | TRUE
3062 | Foundation Coring | 24000 | 24000 |  |  | 24000 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 100% | Five Star | Kurston | FALSE | TRUE | TRUE
3063 | Lighting Controls | 33600 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3064 | Lighting Remove & Re-install | 60480 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3065 | Lighting System Program & Energize | 6000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3066 | Mechanical Terminations(Dampers, Heaters, Motors) | 62400 | 15600 |  |  | 15600 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 25% | Five Star | Kurston | FALSE | TRUE | TRUE
3067 | Survey | 72000 | 72000 |  |  | 72000 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 100% | Five Star | Kurston | FALSE | TRUE | TRUE
3068 | Switches and Receptacles | 12000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3069 | Switchgear & Panelboard Energization | 33000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3070 | Switchgear & Panelboard Installation | 396000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3071 | Switchgear & Panelboard Terminations | 33000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3072 | Switchgear & Panelboard Testing | 33000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 067 - SG5 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3073 | Fire Alarm Conduit | 16650 | 1665 |  |  | 1665 | 02- RESAND: Surfside Gardens | F- SG5 | 068 - SG5 - Division 28 |  | 10% | Five Star | Kurston | FALSE | TRUE | TRUE
3074 | Fire Alarm Wiring | 13140 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 068 - SG5 - Division 28 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3075 | Fire Alarm Devices | 24000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 068 - SG5 - Division 28 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3076 | Fire Alarm Programming & Pretest | 3000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 068 - SG5 - Division 28 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3077 | Fire Alarm FDNY Approval | 3000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 068 - SG5 - Division 28 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3078 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-5 | 17656 | 17656 |  |  | 17656 | 02- RESAND: Surfside Gardens | F- SG5 | 069 - SG5 - Division 31 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
3079 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-5 | 7542 | 1885.5 |  |  | 1885.5 | 02- RESAND: Surfside Gardens | F- SG5 | 069 - SG5 - Division 31 |  | 25% | MLJ | Ricky | FALSE | TRUE | TRUE
3080 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-5 | 625 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | F- SG5 | 069 - SG5 - Division 31 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
3081 | FORMWORK NEW BUILDING - SG-6 | 469701 | 469701 |  |  | 469701 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | MLJ | Brian | FALSE | TRUE | TRUE
3082 | SET ANCHOR BOLTS FOR STEEL COLUMNS - SG-6 | 5411 | 5411 |  |  | 5411 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
3083 | POUR CONCRETE NEW BUILDINGS - SG-6 | 179646 | 179646 |  |  | 179646 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
3084 | FINISH SLABS - SG-6 | 10746 | 10746 |  |  | 10746 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | MLJ | Ricky | FALSE | FALSE | TRUE
3085 | Footing/Pier | 69927 | 69927 |  |  | 69927 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
3086 | Grade Beams | 4634 | 4634 |  |  | 4634 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
3087 | First Floor Slab | 29856 | 29856 |  |  | 29856 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
3088 | Equipment Pads | 1690 | 1690 |  |  | 1690 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
3089 | First Floor Plumbing Shaft Slab | 1373 | 1373 |  |  | 1373 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
3090 | Second Floor Plumbing Shaft Slab | 898 | 898 |  |  | 898 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
3091 | Plumbing Shafts | 22737 | 22737 |  |  | 22737 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
3092 | Fuel Oil Tank Room | 11970 | 11970 |  |  | 11970 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
3093 | WWM-Slabs | 4173 | 4173 |  |  | 4173 | 02- RESAND: Surfside Gardens | G- SG6 | 070 - SG6 - Division 3 |  | 100% | Tonage | Ricky | FALSE | TRUE | TRUE
3094 | 8" CMU (3 hour rated) | 349751 | 332263.45 |  |  | 332263.45 | 02- RESAND: Surfside Gardens | G- SG6 | 071 - SG6 - Division 4 |  | 95% | Faxa | Ricky | FALSE | TRUE | TRUE | 95%
3095 | 4" CMU | 61023 | 57971.85 |  |  | 57971.85 | 02- RESAND: Surfside Gardens | G- SG6 | 071 - SG6 - Division 4 |  | 95% | Faxa | Ricky | FALSE | TRUE | TRUE | 95%
3096 | Face Brick 3-5/8" | 158400 | 40000 |  |  | 40000 | 02- RESAND: Surfside Gardens | G- SG6 | 071 - SG6 - Division 4 | Material on site, applied 50% for materials | 25.25% | Faxa | Ricky | FALSE | TRUE | TRUE | 0%
3097 | 3-1/8" Rigid insulation | 15840 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 071 - SG6 - Division 4 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
3098 | Cast Stone with SS letters | 8521 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 071 - SG6 - Division 4 |  | 0% | S & D | Stefon | FALSE | TRUE | TRUE
3099 | Steel Channel | 18876 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
3100 | Cont. Shelf angle | 11616 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
3101 | STEEL (MATERIAL ONLY) | 165824 | 165824 |  |  | 165824 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | TRUE | TRUE
3102 | FABRICATION COSTS | 246972 | 246972 |  |  | 246972 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | TRUE | TRUE
3103 | METAL DECK (BUY-OUT) | 14113 | 14113 |  |  | 14113 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | TRUE | TRUE
3104 | ANCHORS & EMBEDS | 9410 | 9410 |  |  | 9410 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | TRUE | TRUE
3105 | SURVEYING | 11762 | 11762 |  |  | 11762 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | TRUE | TRUE
3106 | STEEL & DECK ERECTION | 576267 | 576267 |  |  | 576267 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | TRUE | TRUE
3107 | BOLTS AND HARDWARE | 23522 | 23522 |  |  | 23522 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | TRUE | TRUE
3108 | TRUCKING | 11762 | 11762 |  |  | 11762 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | Weir Welding | Ricky | FALSE | TRUE | TRUE
3109 | Dunnage Grating Galvanized | 60521 | 60521 |  |  | 60521 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | E&Y | Ricky | FALSE | TRUE | TRUE
3110 | Dunnage Guard Rail | 28968 | 28968 |  |  | 28968 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | E&Y | Ricky | FALSE | FALSE | TRUE
3111 | Dunnage Platform Stair with Guard Rail | 13035 | 13035 |  |  | 13035 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | E&Y | Ricky | FALSE | FALSE | TRUE
3112 | Stair A: Ground to Roof Floor Stair and Landing with and Hand & Guard Rail | 136365 | 136365 |  |  | 136365 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | E&Y | Ricky | FALSE | FALSE | TRUE
3113 | Stair B: Ground to 2nd Floor Stair and Landing with Hand & Guard Rail | 64143 | 64143 |  |  | 64143 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | E&Y | Ricky | FALSE | FALSE | TRUE
3114 | 1st to 2nd Floor Ship Ladder with Cage and Platform | 27106 | 27106 |  |  | 27106 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | E&Y | Ricky | FALSE | TRUE | TRUE
3115 | Egress Stair: Stair & Landing with Hand & Guard Rail | 64143 | 64143 |  |  | 64143 | 02- RESAND: Surfside Gardens | G- SG6 | 072 - SG6 - Division 5 |  | 100% | E&Y | Ricky | FALSE | FALSE | TRUE
3116 | Layout | 5109 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 073 - SG6 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
3117 | Loading | 18391 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 073 - SG6 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
3118 | Exterior Framing, Insulation & Drywall - Materials | 74880 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 073 - SG6 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
3119 | Exterior Framing- Labor | 87871 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 073 - SG6 - Division 6 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
3120 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - SG-6 | 1444 | 1444 |  |  | 1444 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 100% | MLJ | Ricky | FALSE | TRUE | TRUE
3121 | PENETRATION FIRESTOPPING NEW BLDG - SG-6 | 11505 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
3122 | JOINT SEALANTS NEW BLDGS - S6 | 11505 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
3123 | Air Film | 13200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 0% | Faxa | Ricky | FALSE | TRUE | TRUE
3124 | Insulation- Labor | 6422 | 6422 |  |  | 6422 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 100% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
3125 | Crystalline Waterproofing at plumbing shaft | 5486 | 5486 |  |  | 5486 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 100% | Dstar | Ricky | FALSE | TRUE | TRUE
3126 | Waterproofing at foundation | 10040 | 10040 |  |  | 10040 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 100% | DStar | Ricky | FALSE | TRUE | TRUE
3127 | Layout | 86622 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 0% | Navillus | Stefon | FALSE | TRUE | TRUE
3128 | Framing | 196161 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 0% | Navillus | Stefon | FALSE | TRUE | TRUE
3129 | Insulation | 35133 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 0% | Navillus | Stefon | FALSE | TRUE | TRUE
3130 | Cladding Install | 245934 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 0% | Navillus | Stefon | FALSE | TRUE | TRUE
3131 | Fireproofing | 41800 | 41800 |  |  | 41800 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 100% | SIG | Ricky | FALSE | FALSE | TRUE
3132 | P&I Cold Applied Roof Membrane | 102076 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | TRUE | TRUE
3133 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 123891 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | TRUE | TRUE
3134 | P&I Aluminum Coping | 8547 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 074 - SG6 - Division 7 |  | 0% | Triangle GC | Stefon | FALSE | TRUE | TRUE
3135 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S6 | 12324 | 1232.4 |  |  | 1232.4 | 02- RESAND: Surfside Gardens | G- SG6 | 075 - SG6 - Division 8 | delivered | 10% | MLJ | Ricky | FALSE | TRUE | TRUE
3136 | Doors, Frames & Hardware - Labor | 22798 | 17098.5 |  |  | 17098.5 | 02- RESAND: Surfside Gardens | G- SG6 | 075 - SG6 - Division 8 |  | 75% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
3137 | Louvers Install | 61342 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 075 - SG6 - Division 8 |  | 0% | Navillus | Stefon | FALSE | TRUE | TRUE
3138 | Furnish Doors | 33448 | 33448 |  |  | 33448 | 02- RESAND: Surfside Gardens | G- SG6 | 076 - SG6 - Division 9 |  | 100% | MLJ | Kurston | FALSE | TRUE | TRUE
3139 | Sheathing & Drywall - Labor | 40634 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 076 - SG6 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
3140 | Tape/ Spackle finishes | 13372 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 076 - SG6 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
3141 | ACT ceilings - Materials | 1029 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 076 - SG6 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
3142 | ACT ceilings - Labor | 4629 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 076 - SG6 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
3143 | Direct Applied Stucco | 18722 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 076 - SG6 - Division 9 |  | 0% | Custom Carpentry | Stefon | FALSE | TRUE | TRUE
3144 | Painting SG-6 | 110000 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 076 - SG6 - Division 9 |  | 0% | GG Paint | Stefon | FALSE | TRUE | TRUE
3145 | Cermic Tile and Base - SG-6 | 7564 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 076 - SG6 - Division 9 |  | 0% | Floor Sub | Stefon | FALSE | TRUE | TRUE
3146 | FIRE EXTINGUISHERS NEW BLDGS - SG-6 | 2931 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 077 - SG6 - Division 10 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
3147 | TOILET ACCESSORIES NEW BLDGS - SG-6 | 2830 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 077 - SG6 - Division 10 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
3148 | Stair Identification Sign | 2750 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 077 - SG6 - Division 10 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
3149 | Stairway Floor number and ID Sign | 2750 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 077 - SG6 - Division 10 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
3150 | Room Sign | 2750 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 077 - SG6 - Division 10 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
3151 | Exit Sign | 1100 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 077 - SG6 - Division 10 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
3152 | Public Unisex Toilet Sign | 550 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 077 - SG6 - Division 10 |  | 0% | MLJ | Kurston | FALSE | TRUE | TRUE
3153 | Stairway Flood Access Door | 550 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 077 - SG6 - Division 10 |  | 0% | MLJ | Ricky | FALSE | TRUE | TRUE
3154 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 1552.8 |  |  | 1552.8 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 30% | Vital | Kurston | FALSE | TRUE | TRUE
3155 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 5280 |  |  | 5280 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 100% | Vital | Kurston | FALSE | TRUE | TRUE
3156 | ESCUTCHEONS FOR PLUMBING PIPING | 2178 | 435.6 |  |  | 435.6 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 20% | Vital | Kurston | FALSE | TRUE | TRUE
3157 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 19800 | 1980 |  |  | 1980 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 10% | Vital | Kurston | FALSE | TRUE | TRUE
3158 | HANGERS AND SUPPORTS | 21995 | 15396.5 |  |  | 15396.5 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 70% | Vital | Kurston | FALSE | TRUE | TRUE
3159 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2728 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 0% | Vital | Kurston | FALSE | TRUE | TRUE
3160 | DOMESTIC WATER PIPING | 224153 | 112056.5 |  |  | 112056.5 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 49.99% | Vital | Kurston | FALSE | FALSE | TRUE
3161 | DOMESTIC WATER PIPING SPECIALTIES | 39863 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 0% | Vital | Kurston | FALSE | TRUE | TRUE
3162 | DOMESTIC WATER PUMPING SYSTEMS | 82500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 0% | Vital | Kurston | FALSE | TRUE | TRUE
3163 | SANITARY WASTE PIPING | 118800 | 89100 |  |  | 89100 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 75% | Vital | Kurston | FALSE | TRUE | TRUE
3164 | SANITARY WASTE PIPING SPECIALTIES | 21998 | 1099.9 |  |  | 1099.9 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 5% | Vital | Kurston | FALSE | TRUE | TRUE
3165 | STORM DRAINAGE PIPING SPECIALTIES | 32997 | 23097.9 |  |  | 23097.9 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 70% | Vital | Kurston | FALSE | TRUE | TRUE
3166 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 16368 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 0% | Vital | Kurston | FALSE | TRUE | TRUE
3167 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 240768 | 89084.16 |  |  | 89084.16 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 37% | Vital | Kurston | FALSE | TRUE | TRUE
3168 | GAS SERVICE AND PIPING | 277970 | 83391 |  |  | 83391 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 30% | Vital | Kurston | FALSE | TRUE | TRUE
3169 | PLUMBING FIXTURES | 14167 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 0% | Vital | Kurston | FALSE | TRUE | TRUE
3170 | EMERGENCY PLUMBING FIXTURES | 5104 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 0% | Vital | Kurston | FALSE | TRUE | TRUE
3171 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 45430 | 45430 |  |  | 45430 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 100% | Vital | Kurston | FALSE | TRUE | TRUE
3172 | Plumbing Pipe Insulation | 3032 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 0% | Tristan | Ricky | FALSE | TRUE | TRUE
3173 | Heat Trace | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 078 - SG6 - Division 22 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3174 | Survey | 66000 | 66000 |  |  | 66000 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3175 | Exhaust Fans: Furnish | 3960 | 3960 |  |  | 3960 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3176 | Exhaust Fans: Install | 23045 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3177 | Steam Unit Heaters: Furnish | 4400 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3178 | Steam Unit Heaters: Install | 45650 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3179 | Electric Unit Heaters: Furnish | 4950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3180 | Condensate Return Unit: Furnish | 15400 | 15400 |  |  | 15400 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3181 | Condensate Return Unit: Install | 45650 | 34237.5 |  |  | 34237.5 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 | 50% to place, 50% remaining to hook up | 75% | Welkin | Sully | FALSE | FALSE | TRUE
3182 | Heating and Ventilation Unit: Furnish | 7150 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3183 | Heating and Ventilation Unit: Install | 33550 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3184 | Steam Traps: Furnish | 2200 | 990 |  |  | 990 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 45% | Welkin | Sully | FALSE | TRUE | TRUE
3185 | Steam Traps: Install | 17600 | 7920 |  |  | 7920 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 45% | Welkin | Sully | FALSE | TRUE | TRUE
3186 | Steam Separator: Furnish | 26400 | 26400 |  |  | 26400 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3187 | Steam Separator: Install | 195250 | 195250 |  |  | 195250 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3188 | Low Pressure Steam Boilers: Install | 107250 | 107250 |  |  | 107250 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 | 50% for connecting the boilers. 50% for install. | 100% | Welkin | Sully | FALSE | FALSE | TRUE
3189 | Boiler Feed Unit: Furnish | 38500 | 38500 |  |  | 38500 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3190 | Boiler Feed Unit: Install | 52250 | 41800 |  |  | 41800 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 | 50% for install. 50% for connection. | 80% | Welkin | Sully | FALSE | FALSE | TRUE
3191 | Fuel Oil Pump: Furnish | 55000 | 55000 |  |  | 55000 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3192 | Fuel Oil Pump: Install | 52250 | 52250 |  |  | 52250 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 | Supply pipe installed in December | 100% | Welkin | Sully | FALSE | FALSE | TRUE
3193 | Fuel Oil Storage Tank: Furnish | 44000 | 44000 |  |  | 44000 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3194 | Fuel Oil Storage Tank: Install | 52250 | 52250 |  |  | 52250 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 | Supply pipe installed in December | 100% | Welkin | Sully | FALSE | FALSE | TRUE
3195 | Rigging | 145750 | 145750 |  |  | 145750 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 | 1/3 for Fuel Oil Tank. 2/3 for Boilers | 100% | Welkin | Sully | FALSE | TRUE | TRUE
3196 | Furnish and Install: Hangers/Supports | 433895 | 399183.4 |  |  | 399183.4 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 | First floor completed, 50% total. 2nd floor- Inserts & rods are installed. Rollers remaining to be installed, 1/2 of second floor complete, 25% of total. Overall 75%. | 92% | Welkin | Sully | FALSE | TRUE | TRUE
3197 | Furnish and Install: PVF (Mains) | 682000 | 627440 |  |  | 627440 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 92% | Welkin | Sully | FALSE | FALSE | TRUE
3198 | Furnish and Install: PVF (Branches and Equipment Tie-ins) | 187000 | 168300 |  |  | 168300 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 | First Floor complete - 25%, 2nd floor yet to start - remaining 75% | 90% | Welkin | Sully | FALSE | FALSE | TRUE
3199 | Furnish and Install: Boiler Exhaust Material | 181500 | 159720 |  |  | 159720 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 88% | Welkin | Sully | FALSE | TRUE | TRUE
3200 | Hydrostatic Testing | 6105 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3201 | Furnish and Install: Hangers/Supports | 55000 | 41250 |  |  | 41250 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 75% | Welkin | Sully | FALSE | TRUE | TRUE
3202 | Furnish and Install: Sheetmetal and RGDs | 110000 | 82500 |  |  | 82500 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 75% | Welkin | Sully | FALSE | TRUE | TRUE
3203 | Testing & Balancing | 5500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3204 | Furnish and Install: Devices | 209000 | 41800 |  |  | 41800 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 20% | Welkin | Sully | FALSE | TRUE | TRUE
3205 | Furnish and Install: Controls Conduit | 93500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3206 | Furnish and Install: Controls Wiring | 27500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3207 | Connect to Final Termination Points | 18700 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3208 | Controls Testing | 14575 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3209 | Furnish and Install: Ductwork Insulation | 29700 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3210 | Furnish and Install: Piping Insulation | 60500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3211 | Furnish and Install: Equipment Insulation | 29700 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3212 | Furnish and Install: Chemical Feed Equipment | 10230 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3213 | Chemical Cleaning | 8250 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 079 - SG6 - Division 23 |  | 0% | Welkin | Sully | FALSE | TRUE | TRUE
3214 | ATS Energization | 10950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3215 | ATS Installation | 153300 | 122640 |  |  | 122640 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 80% | Five Star | Kurston | FALSE | TRUE | TRUE
3216 | ATS Terminations | 10950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3217 | ATS Testing | 10950 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3218 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 61250 |  |  | 61250 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 35% | Five Star | Kurston | FALSE | TRUE | TRUE
3219 | Cabling - Risers & Feeders (2/0 & Larger) | 492750 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3220 | Conduit - Branch Circuits (1 1/2" & Smaller) | 54750 | 43800 |  |  | 43800 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 80% | Five Star | Kurston | FALSE | FALSE | TRUE
3221 | Conduit - In-Slab | 216810 | 216810 |  |  | 216810 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 100% | Five Star | Kurston | FALSE | TRUE | TRUE
3222 | Conduit - Risers (2" & Larger) | 295650 | 266085 |  |  | 266085 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 90% | Five Star | Kurston | FALSE | FALSE | TRUE
3223 | Firestopping | 5250 | 787.5 |  |  | 787.5 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 15% | Five Star | Kurston | FALSE | TRUE | TRUE
3224 | Generator Delivery | 52500 | 52500 |  |  | 52500 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 100% | Five Star | Kurston | FALSE | TRUE | TRUE
3225 | Generator Release | 315000 | 315000 |  |  | 315000 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 100% | Five Star | Kurston | FALSE | TRUE | TRUE
3226 | Generator Terminations | 52500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3227 | Generator Test | 52500 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3228 | Lighting Controls | 25200 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3229 | Lighting Install | 88830 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3230 | Lighting Rough | 92637 | 69477.75 |  |  | 69477.75 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 75% | Five Star | Kurston | FALSE | FALSE | TRUE
3231 | Lighting System Program & Energize | 5475 | 0 |  |  | 0 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
3232 | Lightning Protection | 21900 | 2190 |  |  | 2190 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 10% | Five Star | Kurston | FALSE | TRUE | TRUE
3233 | Mechanical Terminations(Dampers, Heaters, Motors) | 142350 | 7117.5 |  |  | 7117.5 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 5% | Five Star | Kurston | FALSE | TRUE | TRUE
3234 | Survey | 54750 | 54750 |  |  | 54750 | 02- RESAND: Surfside Gardens | G- SG6 | 080 - SG6 - Division 26 |  | 100% | Five Star | Kurston | FALSE | TRUE | TRUE
Change orders | [13 empty] | FALSE | TRUE | TRUE
CO1 | Second floor Apartment Removals | 17585 | 17585 |  |  | 17585 |  |  |  |  | 100% | MLJ | Brian | FALSE | TRUE | TRUE
CO2 | National Grid Additional Allowance | 199883 | 0 |  |  | 0 |  |  |  |  | 0% | MLJ | Pat | FALSE | TRUE | TRUE
CO3 | SG6 Additional Strobe | 2486 | 0 |  |  | 0 |  |  |  |  | 0% | Five Star | Kurston | FALSE | TRUE | TRUE
CO4 | CO#2-GC - PCOCO 2 Site 8 Basement Deteriorated Slab Shoring | 39587 | 39587 |  |  | 39587 |  |  |  |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
CO5 | First Floor Move | 61418 | 61418 |  |  | 61418 |  |  |  |  | 100% | MLJ | Brian | FALSE | TRUE | TRUE
CO6 | Site 8 Electrical Hazards | 22438.52 | 22438.52 |  |  | 22438.52 |  |  |  |  | 100% | MLJ | Brian | FALSE | FALSE | TRUE
CO7 | PCO-4 Door Hardware Changes | 25825.5 | 8522.415 |  |  | 8522.415 |  |  |  |  | 33% |  |  |  |  | TRUE
CO8 | PCO-7 Boiler Accessories Supply | 195313 | 0 |  |  | 0 |  |  |  |  | 0% |  |  |  |  | TRUE
CO9 | PCO-9 Irma Pagan Move | 2603 | 2603 |  |  | 2603 |  |  |  |  | 100% |  |  |  |  | TRUE
CO10 | PCO-14 National Grid Gas Line Work | 21598 | 21598 |  |  | 21598 |  |  |  |  | 100% |  |  |  |  | TRUE
CO11 | PCO-15 Additional Windows | 7011 | 7011 |  |  | 7011 |  |  |  |  | 100% |  |  |  |  | TRUE
Total |  | 187395748.02 | 64655747.4903 | 481758.1095 | 0 | 65137505.5998 | 0.34759 | [6 empty] | FALSE | TRUE | FALSE

## Sub by Eng
Highlighted gray are not billing this month
Row Labels | Sum of This Period Requested | Sum of Total Commitment | Sum of Current Total | Remaining | % Complete | Notes
Adam |  | 798805.34 | 230947.05 | 567858.29 | 28.91%
Aspen |  | 798805.34 | 230947.05 | 567858.29 | 28.91%
Brian | 481758.1095 | 26916223.52 | 17794658.4123 | 9121565.1077 | 66.11%
General Conditions | 22079.9095 | 15000000 | 8916329.4323 | 6083670.5677 | 59.44%
MLJ | 459678.2 | 11916223.52 | 8878328.98 | 3037894.54 | 74.51%
Kurston |  | 78087065 | 21219069.95 | 56867995.05 | 27.17%
ATCO |  | 4673955 | 1856801.4 | 2817153.6 | 39.73%
Five Star |  | 54423694 | 11913519.73 | 42510174.27 | 21.89%
MLJ |  | 4640793 | 2375198.26 | 2265594.74 | 51.18%
Vital |  | 14348623 | 5073550.56 | 9275072.44 | 35.36%
Pat |  | 199883 | 0 | 199883 | 0%
MLJ |  | 199883 | 0 | 199883 | 0%
Ricky |  | 38404465 | 11482046.9 | 26922418.1 | 29.9%
Atlas |  | 2078175 | 1275275 | 802900 | 61.37%
Dstar |  | 1014631 | 240895.2 | 773735.8 | 23.74%
Dynasty Elevator |  | 1080000 | 0 | 1080000 | 0%
E&Y |  | 2321029 | 852768.85 | 1468260.15 | 36.74%
Faxa |  | 10010473 | 720756.1 | 9289716.9 | 7.2%
JMC |  | 3234000 | 0 | 3234000 | 0%
Loading Dock |  | 32000 | 0 | 32000 | 0%
MLJ |  | 10020916 | 2994706.85 | 7026209.15 | 29.88%
SIG |  | 262900 | 74800 | 188100 | 28.45%
Tonage |  | 1500800 | 750340.3 | 750459.7 | 50%
Tristan |  | 462407 | 0 | 462407 | 0%
Weir Welding |  | 6387134 | 4572504.6 | 1814629.4 | 71.59%
Sully |  | 34179608.66 | 13398878.463 | 20780730.197 | 39.2%
Citywide Paving |  | 478996 | 0 | 478996 | 0%
MLJ |  | 5475320.66 | 1200849.47 | 4274471.19 | 21.93%
Welkin |  | 28225292 | 12198028.993 | 16027263.007 | 43.22%
(blank) | 481758.1095 | 187648098.52 | 64695481.9053 | 122952616.6147 | 34.48%
(blank) | 481758.1095 | 187648098.52 | 64695481.9053 | 122952616.6147 | 34.48%
Stefon |  | 8557347 | 490412.3 | 8066934.7 | 5.731%
Custom Carpentry |  | 2686033 | 490412.3 | 2195620.7 | 18.26%
Floor Sub |  | 189172 | 0 | 189172 | 0%
GG Paint |  | 660000 | 0 | 660000 | 0%
Navillus |  | 3689394 | 0 | 3689394 | 0%
S & D |  | 181503 | 0 | 181503 | 0%
Triangle GC |  | 1151245 | 0 | 1151245 | 0%
Grand Total | 963516.219 | 374791496.04 | 129311494.9806 | 245480001.0594 | 34.5%

## Bldg by Sub
Row Labels | Sum of This Period Requested | Sum of Current Commitment | Sum of Total | Remaining | % Complete
Aspen |  | 798805.34 | 230947.05 | 567858.29 | 28.91%
ATCO |  | 4673955 | 1856801.4 | 2817153.6 | 39.73%
Atlas |  | 2078175 | 1275275 | 802900 | 61.37%
Citywide Paving |  | 478996 | 0 | 478996 | 0%
Custom Carpentry |  | 2686033 | 490412.3 | 2195620.7 | 18.26%
Dstar |  | 1014631 | 240895.2 | 773735.8 | 23.74%
Dynasty Elevator |  | 1080000 | 0 | 1080000 | 0%
E&Y |  | 2321029 | 852768.85 | 1468260.15 | 36.74%
Faxa |  | 10010473 | 720756.1 | 9289716.9 | 7.2%
Five Star |  | 54423694 | 11913519.73 | 42510174.27 | 21.89%
Floor Sub |  | 189172 | 0 | 189172 | 0%
General Conditions | 22079.9095 | 15000000 | 8916329.4323 | 6083670.5677 | 59.44%
GG Paint |  | 660000 | 0 | 660000 | 0%
JMC |  | 3234000 | 0 | 3234000 | 0%
Loading Dock |  | 32000 | 0 | 32000 | 0%
MLJ | 459678.2 | 32253136.18 | 15449083.56 | 16804052.62 | 47.9%
Navillus |  | 3689394 | 0 | 3689394 | 0%
S & D |  | 181503 | 0 | 181503 | 0%
SIG |  | 262900 | 74800 | 188100 | 28.45%
Tonage |  | 1500800 | 750340.3 | 750459.7 | 50%
Triangle GC |  | 1151245 | 0 | 1151245 | 0%
Tristan |  | 462407 | 0 | 462407 | 0%
Vital |  | 14348623 | 5073550.56 | 9275072.44 | 35.36%
Weir Welding |  | 6387134 | 4572504.6 | 1814629.4 | 71.59%
Welkin |  | 28225292 | 12198028.993 | 16027263.007 | 43.22%
B- SG1 |  | 654996 | 430434.15 | 224561.85 | 65.72%
C- SG2 |  | 633105 | 445170 | 187935 | 70.32%
D- SG3 |  | 1509035 | 144925 | 1364110 | 9.604%
E- SG4 |  | 1161051 | 828617.36 | 332433.64 | 71.37%
F- SG5 |  | 779555 | 533230.005 | 246324.995 | 68.4%
G- SG6 |  | 3201110 | 2407150.9 | 793959.1 | 75.2%
H- SG7 |  | 1048465 | 77000 | 971465 | 7.344%
I- SGN |  | 711517 | 495750.4 | 215766.6 | 69.68%
J- SGS |  | 1021287 | 626544.81 | 394742.19 | 61.35%
K- OG1 |  | 650870 | 470592.54 | 180277.46 | 72.3%
L- OG2 |  | 737551 | 509358.2 | 228192.8 | 69.06%
M- OG3 |  | 1465915 | 1194822.75 | 271092.25 | 81.51%
N- OG4 |  | 1296020 | 154861.3 | 1141158.7 | 11.95%
O- OG5 |  | 1631190 | 356444 | 1274746 | 21.85%
P- OG6 |  | 1298165 | 614407.75 | 683757.25 | 47.33%
R- OG8 |  | 5216530 | 836852.5 | 4379677.5 | 16.04%
S- OG9 |  | 969210 | 366781.25 | 602428.75 | 37.84%
T- OG10 |  | 803165 | 283137.25 | 520027.75 | 35.25%
U- OGE |  | 659016 | 565038.38 | 93977.62 | 85.74%
V- OGW |  | 1075090 | 756410.448 | 318679.552 | 70.36%
W- S8 |  | 55999 | 0 | 55999 | 0%
X- S81 |  | 1646450 | 100500 | 1545950 | 6.104%
(blank) | 481758.1095 | 187648098.52 | 64695481.9053 | 122952616.6147 | 34.48%
(blank) | 481758.1095 | 187648098.52 | 64695481.9053 | 122952616.6147 | 34.48%
Grand Total | 963516.219 | 374791496.04 | 129311494.9806 | 245480001.0594 | 34.5%
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!
|  |  |  | 0 | #DIV/0!

## Summary by Bldg
Row Labels | Sum of This Period Requested | Sum of Current Commitment | Sum of Total | Remaining | % Complete
A- General Conditions | 22079.9095 | 15000000 | 8916329.4323 | 6083670.5677 | 0.59442
B- SG1 |  | 5307915 | 1103495.85 | 4204419.15 | 0.2079
C- SG2 |  | 5469358 | 932548.45 | 4536809.55 | 0.1705
D- SG3 |  | 7224333 | 742981.35 | 6481351.65 | 0.10284
E- SG4 | 26506.25 | 7415708 | 4000930.86 | 3414777.14 | 0.53952
F- SG5 | 21628.5 | 7013670 | 2548319.805 | 4465350.195 | 0.36334
G- SG6 |  | 11781460 | 7296715.56 | 4484744.44 | 0.61934
H- SG7 |  | 10772666 | 2019344.53 | 8753321.47 | 0.18745
I- SGN | 19250.9 | 6567995 | 3602752.78 | 2965242.22 | 0.54853
J- SGS | 58744.75 | 6461290 | 2239170.2 | 4222119.8 | 0.34655
K- OG1 | 15052.5 | 5947589 | 1794066.4 | 4153522.6 | 0.30165
L- OG2 | 9211.2 | 5372148 | 1642729.86 | 3729418.14 | 0.30579
M- OG3 |  | 6050313 | 2581271.55 | 3469041.45 | 0.42663
N- OG4 | 15352 | 6456333 | 1209557.46 | 5246775.54 | 0.18734
O- OG5 | 15352 | 6632764 | 1282698.16 | 5350065.84 | 0.19339
P- OG6 |  | 7393279 | 1845254.92 | 5548024.08 | 0.24959
Q- OG7 |  | 44660 | 44660 | 0 | 1
R- OG8 |  | 17147180 | 5393687.9 | 11753492.1 | 0.31455
S- OG9 |  | 7183490 | 3162183.8 | 4021306.2 | 0.4402
T- OG10 |  | 7642873 | 2847043.75 | 4795829.25 | 0.37251
U- OGE | 64130.25 | 7494331 | 3730742.48 | 3763588.52 | 0.49781
V- OGW | 48571.95 | 8365774 | 3957752.228 | 4408021.772 | 0.47309
W- S8 | 102633.5 | 4507332.34 | 592321.83 | 3915010.51 | 0.13141
X- S81 |  | 11960325 | 946018.4 | 11014306.6 | 0.079096
Y- S82 | 63244.4 | 1393879 | 42407 | 1351472 | 0.030424
Z- Allowance |  | 193334.66 | 0 | 193334.66 | 0
(blank) | 481758.1095 | 187991496.04 | 64836510.4253 | 123154985.6147 | 0.34489
Grand Total | 963516.219 | 374791496.04 | 129311494.9806 | 245480001.0594 | 0.34502

## Eng Update
Sub | MLJ
Row Labels | Sum of Percent Complete
Brian | 9787%
003 - SG1 - Division 3 | 0%
FORM FLOOD BARRIER FOUNDATIONS - SG-1 | 0%
016 - SG2 - Division 3 | 0%
FORM FLOOD BARRIER FOUNDATIONS - SG-2 | 0%
029 - SG3 - Division 3 | 0%
FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - SG-3 | 0%
043 - SG4 - Division 3 | 75%
FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - SG-4 | 75%
057 - SG5 - Division 3 | 75%
FORM FLOOD BARRIER FOUNDATIONS - SG-5 | 75%
070 - SG6 - Division 3 | 100%
FORMWORK NEW BUILDING - SG-6 | 100%
082 - SG6 - Division 31 | 200%
DEWATERING COVERAGE FOR NEW BUILDINGS - SG-6 | 100%
DRIVE PILES AND INSTALL LAGGING FOR SOE - SG-6 | 100%
083 - SG7 - Division 3 | 100%
FORMWORK NEW BUILDING - SG-7 | 100%
095 - SG7 - Division 31 | 200%
DEWATERING COVERAGE FOR NEW BUILDINGS - SG-7 | 100%
DRIVE PILES AND INSTALL LAGGING FOR SOE - SG-7 | 100%
096 - SGN - Division 2 | 967.4%
EROSION CONTROL FABRIC - SGN | 97.21%
INLET PROTECTION - SGN | 93.57%
MANTAIN EROSION CONTROL - SGN | 95.32%
REMOVE CONCRETE CURB & STEPS - SGN | 90%
REMOVE EROSION CONTROL - SGN | 0%
REMOVE FENCE - SGN | 100%
REMOVE FULL DEPTH ASPHALT PVMT - SGN | 100%
REMOVE PVMTS - SGN | 100%
REMOVE SITE FURNISHING - SGN | 100%
SILT FENCE - SGN | 91.29%
STABILIZED CONSTRUCTION ENTRANCE - SGN | 100%
097 - SGN - Division 3 | 33%
FORMWORK SITE CONCRETE - SGN | 33%
100 - SGN - Division 31 | 594.3%
Dewatering expenses | 99.08%
Dewatering Permits | 100%
Furnish and Install Deep Wells | 100%
Furnish and Install Pumps and Piping | 98.76%
Installation Support | 98.33%
Power for Dewatering | 98.17%
102 - SGN - Division 33 | 376.4%
DEWATERING COVERAGE FOR UTILITY WORK - SGN | 96.44%
Equipment SUPPORT FOR SITE - SGN | 100%
MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - SGN | 100%
TERMINATE AND DEMOLISH EXISTING UTILITIES - SGN | 80%
103 - SGS - Division 2 | 818.3%
EROSION CONTROL FABRIC - SGS | 65%
INLET PROTECTION - SGS | 65%
MANTAIN EROSION CONTROL - SGS | 80%
REMOVE CONCRETE CURB & STEPS - SGS | 88.38%
REMOVE EROSION CONTROL - SGS | 0%
REMOVE FENCE - SGS | 100%
REMOVE FULL DEPTH ASPHALT PVMT - SGS | 85.47%
REMOVE PVMTS - SGS | 84.94%
REMOVE SITE FURNISHING - SGS | 84.52%
SILT FENCE - SGS | 65%
STABILIZED CONSTRUCTION ENTRANCE - SGS | 100%
104 - SGS - Division 3 | 0%
FORMWORK SITE CONCRETE - SGS | 0%
106 - SGS - Division 31 | 475%
Dewatering expenses | 80%
Dewatering Permits | 75%
Furnish and Install Deep Wells | 80%
Furnish and Install Pumps and Piping | 80%
Installation Support | 80%
Power for Dewatering | 80%
108 - SGS - Division 33 | 245%
DEWATERING COVERAGE FOR UTILITY WORK - SGS | 50%
Equipment SUPPORT FOR SITE - SGS | 65%
MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - SGS | 80%
TERMINATE AND DEMOLISH EXISTING UTILITIES - SGS | 50%
110 - OG1 - Division 3 | 50%
FORM FLOOD BARRIER FOUNDATIONS - OG-1 | 50%
124 - OG2 - Division 3 | 70%
FORM FLOOD BARRIER FOUNDATIONS - OG-2 | 70%
138 - OG3 - Division 3 | 0%
FORM FLOOD BARRIER FOUNDATIONS - OG-3 | 0%
152 - OG4 - Division 3 | 0%
FORM FLOOD BARRIER FOUNDATIONS - OG-4 | 0%
166 - OG5 - Division 3 | 0%
FORM FLOOD BARRIER FOUNDATIONS - OG-5 | 0%
180 - OG6 - Division 3 | 0%
FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - OG-6 | 0%
195 - OG8 - Division 3 | 100%
FORMWORK NEW BUILDING - OG-8 | 100%
207 - OG8 - Division 31 | 200%
DEWATERING COVERAGE FOR NEW BUILDINGS - OG-8 | 100%
DRIVE PILES AND INSTALL LAGGING FOR SOE - OG-8 | 100%
208 - OG9 - Division 3 | 100%
FORMWORK NEW BUILDING - OG-9 | 100%
220 - OG9 - Division 31 | 100%
DEWATERING COVERAGE FOR NEW BUILDINGS - OG-9 | 100%
221 - OG10 - Division 3 | 100%
FORMWORK NEW BUILDING - OG-10 | 100%
233 - OG10 - Division 31 | 200%
DEWATERING COVERAGE FOR NEW BUILDINGS - OG-10 | 100%
DRIVE PILES AND INSTALL LAGGING FOR SOE - OG-10 | 100%
234 - OGE - Division 2 | 815%
EROSION CONTROL FABRIC - OGE | 55%
INLET PROTECTION - OGE | 55%
MANTAIN EROSION CONTROL - OGE | 55%
REMOVE CONCRETE CURB & STEPS - OGE | 95%
REMOVE EROSION CONTROL - OGE | 0%
REMOVE FENCE - OGE | 100%
REMOVE FULL DEPTH ASPHALT PVMT - OGE | 95%
REMOVE PVMTS - OGE | 95%
REMOVE SITE FURNISHING - OGE | 95%
SILT FENCE - OGE | 70%
STABILIZED CONSTRUCTION ENTRANCE - OGE | 100%
235 - OGE - Division 3 | 25%
FORMWORK SITE CONCRETE - OGE | 25%
237 - OGE - Division 31 | 551.3%
Dewatering expenses | 95%
Dewatering Permits | 95%
Furnish and Install Deep Wells | 95%
Furnish and Install Pumps and Piping | 85%
Installation Support | 90.83%
Power for Dewatering | 90.42%
239 - OGE - Division 33 | 380%
DEWATERING COVERAGE FOR UTILITY WORK - OGE | 95%
Equipment SUPPORT FOR SITE - OGE | 95%
MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - OGE | 95%
TERMINATE AND DEMOLISH EXISTING UTILITIES - OGE | 95%
240 - OGW - Division 2 | 805.1%
EROSION CONTROL FABRIC - OGW | 80%
INLET PROTECTION - OGW | 85%
MANTAIN EROSION CONTROL - OGW | 15%
REMOVE CONCRETE CURB & STEPS - OGW | 90%
REMOVE EROSION CONTROL - OGW | 0%
REMOVE FENCE - OGW | 75%
REMOVE FULL DEPTH ASPHALT PVMT - OGW | 90%
REMOVE PVMTS - OGW | 90%
REMOVE SITE FURNISHING - OGW | 80.12%
SILT FENCE - OGW | 100%
STABILIZED CONSTRUCTION ENTRANCE - OGW | 100%
241 - OGW - Division 3 | 33%
FORMWORK SITE CONCRETE - OGW | 33%
244 - OGW - Division 31 | 570%
Dewatering expenses | 95%
Dewatering Permits | 95%
Furnish and Install Deep Wells | 95%
Furnish and Install Pumps and Piping | 95%
Installation Support | 95%
Power for Dewatering | 95%
246 - OGW - Division 33 | 290%
DEWATERING COVERAGE FOR UTILITY WORK - OGW | 80%
Equipment SUPPORT FOR SITE - OGW | 90%
MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - OGW | 75%
TERMINATE AND DEMOLISH EXISTING UTILITIES - OGW | 45%
247 - S8 - Division 2 | 623.4%
EROSION CONTROL FABRIC - S8 | 25%
INLET PROTECTION - S8 | 25%
MANTAIN EROSION CONTROL - S8 | 25%
REMOVE CONCRETE CURB & STEPS - S8 | 80%
REMOVE EROSION CONTROL - S8 | 0%
REMOVE FENCE - S8 | 100%
REMOVE FULL DEPTH ASPHALT PVMT - S8 | 80%
REMOVE PVMTS - S8 | 80%
REMOVE SITE FURNISHING -S8 | 83.41%
SILT FENCE - S8 | 25%
STABILIZED CONSTRUCTION ENTRANCE - S8 | 100%
248 - S8 - Division 3 | 0%
FORMWORK SITE CONCRETE - S8 | 0%
257 - S8 - Division 31 | 50%
Dewatering expenses | 0%
Dewatering Permits | 50%
Furnish and Install Deep Wells | 0%
Furnish and Install Pumps and Piping | 0%
Installation Support | 0%
Power for Dewatering | 0%
259 - S8 - Division 33 | 5%
DEWATERING COVERAGE FOR UTILITY WORK - S8 | 0%
Equipment SUPPORT FOR SITE - S8 | 5%
MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - S8 | 0%
TERMINATE AND DEMOLISH EXISTING UTILITIES - S8 | 0%
260 - S81 - Division 3 | 0%
FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - S8 | 0%
272 - S82 - Division 3 | 0%
FORMWORK NEW BUILDING - S8 | 0%
277 - S82 - Division 31 | 60%
DEWATERING COVERAGE FOR NEW BUILDINGS - S8 | 0%
DRIVE PILES AND INSTALL LAGGING FOR SOE - S8 | 60%
(blank) | 400%
CO#2-GC - PCOCO 2 Site 8 Basement Deteriorated Slab Shoring | 100%
Second floor Apartment Removals | 100%
First Floor Move | 100%
Site 8 Electrical Hazards | 100%
Kurston | 10373%
002 - SG1 - Division 2 | 100%
Existing Ramp railing to be be removed - 1st floor | 0%
Remove existing door, frame and hardware - cellar and 1st floor | 0%
Remove existing paint and plaster - cellar | 100%
Remove Existing Ramp - 1st floor | 0%
Remove existing stair - 1st floor | 0%
Remove existing vent / window and frame - cellar | 0%
Remove sump pump - cellar | 0%
Remove window sill - 1st floor | 0%
004 - SG1 - Division 4 | 0%
CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-1 | 0%
008 - SG1 - Division 9 | 0%
Furnish Doors | 0%
009 - SG1 - Division 10 | 0%
Address Signs | 0%
Temporary Egress Stair Storage Sign | 0%
015 - SG2 - Division 2 | 0%
Existing Ramp railing to be be removed - 1st fllor | 0%
Remove existing door, frame and hardware - cellar | 0%
Remove existing paint and plaster - cellar | 0%
Remove Existing Ramp - 1st floor | 0%
Remove existing vent / window and frame - cellar | 0%
Remove sump pump - cellar | 0%
Remove window sill - 1st floor | 0%
017 - SG2 - Division 4 | 0%
CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-2 | 0%
021 - SG2 - Division 9 | 0%
Furnish Doors | 0%
022 - SG2 - Division 10 | 0%
Address Signs | 0%
Temporary Egress Stair Storage Sign | 0%
028 - SG3 - Division 2 | 800%
Existing Ramp railing to be be removed - 1st floor | 0%
Patch floor and make smooth - 2nd floor | 0%
Remove appliances - 2nd floor | 100%
Remove ceiling finishes - 2nd floor | 100%
Remove CMU wall - 2nd floor | 100%
Remove existing door, frame and hardware - cellar and 1st floor | 0%
Remove existing paint and plaster - cellar | 0%
Remove Existing Ramp - 1st floor | 0%
Remove existing vent / window and frame - cellar and 1st floor | 0%
Remove existing windows - 2nd floor | 0%
Remove floor finish - 2nd floor | 100%
Remove interior walls - 2nd floor | 100%
Remove plumbing to fixtures - 2nd floor | 100%
Remove sinks - 2nd floor | 100%
Remove stove - 2nd floor | 100%
Remove sump pump - cellar | 0%
Remove window sill - 1st floor | 0%
029 - SG3 - Division 3 | 0%
PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG-3 | 0%
030 - SG3 - Division 4 | 0%
CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-3 | 0%
034 - SG3 - Division 9 | 0%
Furnish Doors | 0%
035 - SG3 - Division 10 | 0%
Address Signs | 0%
042 - SG4 - Division 2 | 1370%
Existing Ramp railing to be be removed - 1st floor | 70%
Patch floor and make smooth - 2nd floor | 100%
Remove appliances - 2nd floor | 100%
Remove ceiling finishes - 2nd floor | 100%
Remove CMU wall - 2nd floor | 100%
Remove existing door, frame and hardware - cellar and 1st floor | 50%
Remove existing paint and plaster - cellar | 100%
Remove Existing Ramp - 1st floor | 50%
Remove existing vent / window and frame - cellar and 1st floor | 100%
Remove existing windows - 2nd floor | 100%
Remove floor finish - 2nd floor | 100%
Remove interior walls - 2nd floor | 100%
Remove plumbing to fixtures - 2nd floor | 100%
Remove sinks - 2nd floor | 100%
Remove stove - 2nd floor | 100%
Remove sump pump - cellar | 0%
Remove window sill - 1st floor | 0%
043 - SG4 - Division 3 | 0%
PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG-4 | 0%
044 - SG4 - Division 4 | 100%
CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-4 | 100%
048 - SG4 - Division 9 | 0%
Furnish Doors | 0%
049 - SG4 - Division 10 | 0%
Address Signs | 0%
Temporary Egress Stair Storage Sign | 0%
056 - SG5 - Division 2 | 800%
Existing Ramp railing to be be removed - 1st floor | 0%
Patch floor and make smooth - 2nd floor | 0%
Prepare existing wall surface for paint | 0%
Remove appliances - 2nd floor | 100%
Remove ceiling finishes - 2nd floor | 0%
Remove CMU wall - 2nd floor | 100%
Remove existing door, frame and hardware | 0%
Remove existing paint and plaster - cellar | 100%
Remove Existing Ramp - 1st floor | 0%
Remove existing vent / window and frame - cellar and 1st floor | 100%
Remove existing windows - 2nd floor | 0%
Remove floor finish - 2nd floor | 0%
Remove interior walls - 2nd floor | 100%
Remove plumbing to fixtures - 2nd floor | 100%
Remove sinks - 2nd floor | 100%
Remove stove - 2nd floor | 100%
Remove sump pump - cellar | 0%
Remove window sill - 1st floor | 0%
057 - SG5 - Division 3 | 0%
PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG-5 | 0%
058 - SG5 - Division 4 | 100%
CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-5 | 100%
062 - SG5 - Division 9 | 0%
Furnish Doors | 0%
063 - SG5 - Division 10 | 0%
Address Signs | 0%
Temporary Egress Stair Storage Sign | 0%
076 - SG6 - Division 9 | 100%
Furnish Doors | 100%
077 - SG6 - Division 10 | 0%
Exit Sign | 0%
FIRE EXTINGUISHERS NEW BLDGS - SG-6 | 0%
Public Unisex Toilet Sign | 0%
Room Sign | 0%
Stair Identification Sign | 0%
Stairway Floor number and ID Sign | 0%
TOILET ACCESSORIES NEW BLDGS - SG-6 | 0%
089 - SG7 - Division 9 | 0%
Furnish Doors | 0%
090 - SG7 - Division 10 | 0%
Exit Sign | 0%
FIRE EXTINGUISHERS NEW BLDGS - SG-7 | 0%
Public Unisex Toilet Sign | 0%
Room Sign | 0%
Stair Identification Sign | 0%
Stairway Floor number and ID Sign | 0%
TOILET ACCESSORIES NEW BLDGS - SG-7 | 0%
102 - SGN - Division 33 | 100%
ELECTRICAL MANHOLES - SGN | 100%
108 - SGS - Division 33 | 0%
ELECTRICAL MANHOLES - SGS | 0%
109 - OG1 - Division 2 | 1100%
Patch floor and make smooth - 2nd floor | 0%
Prepare existing wall surface for paint - 1st floor | 0%
Remove appliances - 2nd floor | 100%
Remove ceiling finishes - 2nd floor | 100%
Remove CMU wall - 2nd floor | 100%
Remove existing AC units and sleeves - 1st floor | 0%
Remove existing door, frame and hardware | 0%
Remove existing paint and plaster - cellar | 100%
Remove existing vent / window and frame | 100%
Remove existing windows - 2nd floor | 100%
Remove floor finish - 2nd floor | 100%
Remove interior walls - 2nd floor | 100%
Remove plumbing to fixtures - 2nd floor | 100%
Remove sinks - 2nd floor | 100%
Remove stove - 2nd floor | 100%
Remove window sill - 1st floor | 0%
110 - OG1 - Division 3 | 0%
PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-1 | 0%
111 - OG1 - Division 4 | 0%
CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-1 | 0%
115 - OG1 - Division 9 | 33%
Furnish Doors | 33%
116 - OG1 - Division 10 | 0%
Address Signs | 0%
Temporary Egress Stair Storage Sign | 0%
123 - OG2 - Division 2 | 1100%
Patch floor and make smooth - 2nd floor | 0%
Prepare existing wall surface for paint - 1st floor | 0%
Remove appliances - 2nd floor | 100%
Remove ceiling finishes - 2nd floor | 100%
Remove CMU wall - 2nd floor | 100%
Remove existing AC units and sleeves - 1st floor | 0%
Remove existing door, frame and hardware | 0%
Remove existing paint and plaster - cellar | 100%
Remove existing vent / window and frame | 100%
Remove existing windows - 2nd floor | 100%
Remove floor finish - 2nd floor | 100%
Remove interior walls - 2nd floor | 100%
Remove plumbing to fixtures - 2nd floor | 100%
Remove sinks - 2nd floor | 100%
Remove stove - 2nd floor | 100%
Remove sump pump - cellar | 0%
Remove window sill - 1st floor | 0%
124 - OG2 - Division 3 | 0%
PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-2 | 0%
125 - OG2 - Division 4 | 0%
CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-2 | 0%
129 - OG2 - Division 9 | 33%
Furnish Doors | 33%
130 - OG2 - Division 10 | 0%
Address Signs | 0%
Temporary Egress Stair Storage Sign | 0%
137 - OG3 - Division 2 | 1100%
Patch floor and make smooth - 2nd floor | 0%
Remove appliances - 2nd floor | 100%
Remove ceiling finishes - 2nd floor | 100%
Remove CMU wall - 2nd floor | 100%
Remove existing AC units and sleeves - 1st floor | 0%
Remove existing door, frame and hardware | 0%
Remove existing paint and plaster - cellar | 100%
Remove existing vent / window and frame | 100%
Remove existing windows - 2nd floor | 100%
Remove floor finish - 2nd floor | 100%
Remove interior walls - 2nd floor | 100%
Remove plumbing to fixtures - 2nd floor | 100%
Remove sinks - 2nd floor | 100%
Remove stove - 2nd floor | 100%
Remove sump pump - cellar | 0%
Remove window sill - 1st floor | 0%
138 - OG3 - Division 3 | 0%
PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-3 | 0%
139 - OG3 - Division 4 | 0%
CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-3 | 0%
143 - OG3 - Division 9 | 0%
Furnish Doors | 0%
144 - OG3 - Division 10 | 0%
Address Signs | 0%
Temporary Egress Stair Storage Sign | 0%
151 - OG4 - Division 2 | 1100%
Patch floor and make smooth - 2nd floor | 0%
Prepare existing wall surface for paint - 1st floor | 0%
Remove appliances - 2nd floor | 100%
Remove ceiling finishes - 2nd floor | 100%
Remove CMU wall - 2nd floor | 100%
Remove existing AC units and sleeves - 1st floor | 0%
Remove existing door, frame and hardware | 0%
Remove existing paint and plaster - cellar | 100%
Remove existing vent / window and frame | 100%
Remove existing windows - 2nd floor | 100%
Remove floor finish - 2nd floor | 100%
Remove interior walls - 2nd floor | 100%
Remove plumbing to fixtures - 2nd floor | 100%
Remove sinks - 2nd floor | 100%
Remove stove - 2nd floor | 100%
Remove sump pump - cellar | 0%
Remove window sill - 1st floor | 0%
152 - OG4 - Division 3 | 0%
PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-4 | 0%
153 - OG4 - Division 4 | 0%
CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-4 | 0%
157 - OG4 - Division 9 | 33%
Furnish Doors | 33%
158 - OG4 - Division 10 | 0%
Address Signs | 0%
Temporary Egress Stair Storage Sign | 0%
165 - OG5 - Division 2 | 1200%
Patch floor and make smooth - 2nd floor | 100%
Prepare existing wall surface for paint - 1st floor | 0%
Remove appliances - 2nd floor | 100%
Remove ceiling finishes - 2nd floor | 100%
Remove CMU wall - 2nd floor | 100%
Remove existing AC units and sleeves - 1st floor | 0%
Remove existing door, frame and hardware | 0%
Remove existing paint and plaster - cellar | 100%
Remove existing vent / window and frame | 100%
Remove existing windows - 2nd floor | 100%
Remove floor finish - 2nd floor | 100%
Remove interior walls - 2nd floor | 100%
Remove plumbing to fixtures - 2nd floor | 100%
Remove sinks - 2nd floor | 100%
Remove stove - 2nd floor | 100%
Remove sump pump - cellar | 0%
Remove window sill - 1st floor | 0%
166 - OG5 - Division 3 | 0%
PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-5 | 0%
167 - OG5 - Division 4 | 0%
CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-5 | 0%
171 - OG5 - Division 9 | 33%
Furnish Doors | 33%
172 - OG5 - Division 10 | 0%
Address Signs | 0%
Temporary Egress Stair Storage Sign | 0%
179 - OG6 - Division 2 | 980%
Patch floor and make smooth - 2nd floor | 0%
Remove appliances - 2nd floor | 100%
Remove ceiling finishes - 2nd floor | 100%
Remove CMU wall - 2nd floor | 100%
Remove existing AC units and sleeves - 1st floor | 0%
Remove existing door, frame and hardware - basement | 0%
Remove existing paint and plaster - cellar and basement | 80%
Remove existing vent / window and frame- cellar and basement | 0%
Remove existing windows - 2nd floor | 100%
Remove floor finish - 2nd floor | 100%
Remove interior walls - 2nd floor | 100%
Remove plumbing to fixtures - 2nd floor | 100%
Remove sinks - 2nd floor | 100%
Remove stove - 2nd floor | 100%
Remove sump pump - cellar | 0%
Remove window sill - 1st floor | 0%
180 - OG6 - Division 3 | 0%
PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-6 | 0%
185 - OG6 - Division 9 | 33%
Furnish Doors | 33%
186 - OG6 - Division 10 | 0%
Address Signs | 0%
Temporary Egress Stair Storage Sign | 0%
201 - OG8 - Division 9 | 0%
Furnish Doors | 0%
202 - OG8 - Division 10 | 0%
Exit Sign | 0%
FIRE EXTINGUISHERS NEW BLDGS - S8 | 0%
Public Unisex Toilet Sign | 0%
Room Sign | 0%
Stair Identification Sign | 0%
Stairway Floor number and ID Sign | 0%
TOILET ACCESSORIES NEW BLDGS - OG-8 | 0%
214 - OG9 - Division 9 | 47.83%
Furnish Doors | 47.83%
215 - OG9 - Division 10 | 0%
Exit Sign | 0%
Public Unisex Toilet Sign | 0%
Room Sign | 0%
Stair Identification Sign | 0%
Stairway Floor number and ID Sign | 0%
TOILET ACCESSORIES NEW BLDGS - OG-9 | 0%
227 - OG10 - Division 9 | 0%
Furnish Doors | 0%
228 - OG10 - Division 10 | 0%
Public Unisex Toilet Sign | 0%
Room Sign | 0%
Stair Identification Sign | 0%
Stairway Floor number and ID Sign | 0%
TOILET ACCESSORIES NEW BLDGS - OG-10 | 0%
239 - OGE - Division 33 | 100%
ELECTRICAL MANHOLES - OGE | 100%
247 - S8 - Division 2 | 10%
Remove Areaway grate - cellar | 0%
Remove Areaway slab and drain - cellar | 10%
Remove existing door, frame and hardware - cellar and 1st floor | 0%
Remove existing paint and plaster - cellar | 0%
Remove existing portion wall - 1st floor | 0%
Remove existing vent / window and frame - cellar and 1st floor | 0%
Remove sump pump - cellar | 0%
Remove window sill - 1st floor | 0%
253 - S8 - Division 10 | 0%
Address Signs | 0%
Exit Sign | 0%
Room Sign | 0%
Stair Identification Sign | 0%
Stairway Floor number and ID Sign | 0%
Temporary Egress Stair Storage Sign | 0%
259 - S8 - Division 33 | 0%
ELECTRICAL MANHOLES - S8 | 0%
265 - S81 - Division 9 | 0%
Furnish Doors | 0%
276 - S82 - Division 9 | 0%
Furnish Doors | 0%
Pat | 0%
(blank) | 0%
National Grid Additional Allowance | 0%
Ricky | 7972%
002 - SG1 - Division 2 | 0%
Remove Areaway grate - cellar | 0%
Remove Areaway slab and drain - cellar | 0%
Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 0%
Sawcut and remove portion of areaway wall - cellar | 0%
003 - SG1 - Division 3 | 0%
DRILL & GROUT DOWELS - SG-1 | 0%
FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-1 | 0%
INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-1 | 0%
POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-1 | 0%
004 - SG1 - Division 4 | 0%
Overhead protection for Masonry | 0%
006 - SG1 - Division 7 | 0%
JOINT SEALANTS EXTG BLDGS - SG-1 | 0%
PENETRATION FIRESTOPPING EXTG BLDG - SG-1 | 0%
007 - SG1 - Division 8 | 0%
(2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-1 | 0%
009 - SG1 - Division 10 | 0%
AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-1 | 0%
MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - SG-1 | 0%
WINDOW FLOODGATES (8.06 AND 8.14) - SG-1 | 0%
014 - SG1 - Division 31 | 0%
BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-1 | 0%
EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-1 | 0%
INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-1 | 0%
015 - SG2 - Division 2 | 10%
Remove Areaway grate - cellar | 0%
Remove Areaway slab and drain - cellar | 10%
Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 0%
Sawcut and remove portion of areaway wall - cellar | 0%
016 - SG2 - Division 3 | 0%
DRILL & GROUT DOWELS - SG-2 | 0%
FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-2 | 0%
INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-2 | 0%
New Concrete Curb Next to Existing Wall | 0%
POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-2 | 0%
017 - SG2 - Division 4 | 0%
Overhead protection for Masonry | 0%
019 - SG2 - Division 7 | 0%
JOINT SEALANTS EXTG BLDGS - SG-2 | 0%
PENETRATION FIRESTOPPING EXTG BLDG - SG-2 | 0%
020 - SG2 - Division 8 | 0%
(2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-2 | 0%
022 - SG2 - Division 10 | 0%
AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-2 | 0%
MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - SG-2 | 0%
WINDOW FLOODGATES (8.06 AND 8.14) - SG-2 | 0%
027 - SG2 - Division 31 | 0%
BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-2 | 0%
EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-2 | 0%
INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-2 | 0%
028 - SG3 - Division 2 | 10%
Cut openings in slab - 2nd floor | 0%
Remove Areaway grate - cellar | 0%
Remove Areaway slab and drain - cellar | 10%
Saw cut openings through slab for cellar ventilation / exhaust ducts | 0%
Sawcut and remove portion of areaway wall - cellar | 0%
Sawcut slab opening for mechanical - cellar and 1st floor | 0%
029 - SG3 - Division 3 | 0%
DRILL & GROUT DOWELS - SG-3 | 0%
FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-3 | 0%
FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - SG-3 | 0%
INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-3 | 0%
POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-3 | 0%
030 - SG3 - Division 4 | 0%
Overhead protection for Masonry | 0%
032 - SG3 - Division 7 | 0%
JOINT SEALANTS EXTG BLDGS - SG-3 | 0%
PENETRATION FIRESTOPPING EXTG BLDG - SG-3 | 0%
035 - SG3 - Division 10 | 0%
AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-3 | 0%
041 - SG3 - Division 31 | 0%
BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-3 | 0%
EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-3 | 0%
INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-3 | 0%
042 - SG4 - Division 2 | 600%
Cut openings in slab - 2nd floor | 100%
Remove Areaway grate - cellar | 100%
Remove Areaway slab and drain - cellar | 100%
Saw cut openings through slab for cellar ventilation / exhaust ducts | 100%
Sawcut and remove portion of areaway wall - cellar | 100%
Sawcut slab opening for mechanical - cellar and 1st floor | 100%
043 - SG4 - Division 3 | 475%
DRILL & GROUT DOWELS - SG-4 | 100%
FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-4 | 100%
FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - SG-4 | 100%
INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-4 | 100%
POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-4 | 75%
044 - SG4 - Division 4 | 0%
Overhead protection for Masonry | 0%
046 - SG4 - Division 7 | 0%
JOINT SEALANTS EXTG BLDGS - SG-4 | 0%
PENETRATION FIRESTOPPING EXTG BLDG - SG-4 | 0%
047 - SG4 - Division 8 | 0%
(2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-4 | 0%
049 - SG4 - Division 10 | 0%
AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-4 | 0%
MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE (8.15) - SG-4 | 0%
WINDOW FLOODGATES (8.06 AND 8.14) - SG-4 | 0%
055 - SG4 - Division 31 | 115%
BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-4 | 25%
EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-4 | 90%
INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-4 | 0%
056 - SG5 - Division 2 | 500%
Cut openings in slab - 2nd floor | 0%
Remove Areaway grate | 100%
Remove Areaway slab and drain | 100%
Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 100%
Sawcut and remove portion of areaway wall | 100%
Sawcut slab opening for mechanical - 1st floor | 100%
057 - SG5 - Division 3 | 375%
DRILL & GROUT DOWELS - SG-5 | 100%
FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-5 | 100%
FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - SG-5 | 25%
INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-5 | 100%
POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-5 | 50%
058 - SG5 - Division 4 | 0%
Overhead protection for Masonry | 0%
060 - SG5 - Division 7 | 0%
JOINT SEALANTS EXTG BLDGS - SG-5 | 0%
PENETRATION FIRESTOPPING EXTG BLDG - SG-5 | 0%
061 - SG5 - Division 8 | 0%
(2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-5 | 0%
063 - SG5 - Division 10 | 0%
AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-5 | 0%
MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE (8.15) - SG-5 | 0%
WINDOW FLOODGATES (8.06 AND 8.14) - SG-5 | 0%
069 - SG5 - Division 31 | 125%
BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-5 | 25%
EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-5 | 100%
INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-5 | 0%
070 - SG6 - Division 3 | 300%
FINISH SLABS - SG-6 | 100%
POUR CONCRETE NEW BUILDINGS - SG-6 | 100%
SET ANCHOR BOLTS FOR STEEL COLUMNS - SG-6 | 100%
074 - SG6 - Division 7 | 100%
3" RIGID INSULATION UNDER GRADE NEW BLDGS - SG-6 | 100%
JOINT SEALANTS NEW BLDGS - S6 | 0%
PENETRATION FIRESTOPPING NEW BLDG - SG-6 | 0%
075 - SG6 - Division 8 | 10%
(1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S6 | 10%
077 - SG6 - Division 10 | 0%
Stairway Flood Access Door | 0%
082 - SG6 - Division 31 | 300%
BACKFILL NEW BLDGS - SG-6 | 100%
DENSE GRADED STONE BASE FOR FOUNDATION SLAB - SG-6 | 100%
EXCAVATION NEW BLDGS - SG-6 | 100%
083 - SG7 - Division 3 | 220%
FINISH SLABS - SG-7 | 25%
POUR CONCRETE NEW BUILDINGS - SG-7 | 95%
SET ANCHOR BOLTS FOR STEEL COLUMNS - SG-7 | 100%
087 - SG7 - Division 7 | 100%
3" RIGID INSULATION UNDER GRADE NEW BLDGS - SG-7 | 100%
JOINT SEALANTS NEW BLDGS - S7 | 0%
PENETRATION FIRESTOPPING NEW BLDG - SG-7 | 0%
088 - SG7 - Division 8 | 0%
(1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S7 | 0%
090 - SG7 - Division 10 | 0%
Stairway Flood Access Door | 0%
095 - SG7 - Division 31 | 188.9%
BACKFILL NEW BLDGS - SG-7 | 88.92%
DENSE GRADED STONE BASE FOR FOUNDATION SLAB - SG-7 | 0%
EXCAVATION NEW BLDGS - SG-7 | 100%
097 - SGN - Division 3 | 0%
CONCRETE FOOTING FOR SITE FURNISHING - SGN | 0%
CONCRETE SITE RETAINING WALL AND FOOTINGS - SGN | 0%
098 - SGN - Division 11 | 0%
EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - SGN | 0%
104 - SGS - Division 3 | 0%
CONCRETE FOOTING FOR SITE FURNISHING - SGS | 0%
109 - OG1 - Division 2 | 20%
Cut openings in slab - 2nd floor | 0%
Remove Areaway grate | 0%
Remove Areaway slab and drain | 20%
Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 0%
Sawcut and remove portion of areaway wall | 0%
Sawcut slab opening for mechanical - cellar and 1st floor | 0%
110 - OG1 - Division 3 | 250%
DRILL & GROUT DOWELS - OG-1 | 50%
FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-1 | 0%
FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-1 | 0%
INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-1 | 100%
New Concrete Curb Next to Existing Wall | 100%
POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-1 | 0%
111 - OG1 - Division 4 | 0%
Overhead protection for Masonry | 0%
113 - OG1 - Division 7 | 0%
JOINT SEALANTS EXTG BLDGS - OG-1 | 0%
PENETRATION FIRESTOPPING EXTG BLDG - OG-1 | 0%
116 - OG1 - Division 10 | 0%
AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-1 | 0%
MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-1 | 0%
122 - OG1 - Division 31 | 95%
BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-1 | 0%
EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-1 | 95%
INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-1 | 0%
123 - OG2 - Division 2 | 10%
Cut openings in slab - 2nd floor | 0%
Remove Areaway grate | 0%
Remove Areaway slab and drain | 10%
Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 0%
Sawcut and remove portion of areaway wall | 0%
Sawcut slab opening for mechanical - 1st floor | 0%
124 - OG2 - Division 3 | 325%
DRILL & GROUT DOWELS - OG-2 | 50%
FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-2 | 0%
FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-2 | 0%
INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-2 | 100%
New Concrete Curb Next to Existing Wall | 100%
POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-2 | 75%
125 - OG2 - Division 4 | 0%
Overhead protection for Masonry | 0%
127 - OG2 - Division 7 | 0%
JOINT SEALANTS EXTG BLDGS - OG-2 | 0%
PENETRATION FIRESTOPPING EXTG BLDG - OG-2 | 0%
130 - OG2 - Division 10 | 0%
AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-2 | 0%
MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-2 | 0%
136 - OG2 - Division 31 | 80%
BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-2 | 0%
EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-2 | 80%
INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-2 | 0%
137 - OG3 - Division 2 | 250%
Cut openings in slab - 2nd floor | 100%
Remove Areaway grate | 50%
Remove Areaway slab and drain | 50%
Sawcut and remove portion of areaway wall | 50%
Sawcut slab opening for mechanical - 1st floor | 0%
138 - OG3 - Division 3 | 300%
DRILL & GROUT DOWELS - OG-3 | 50%
FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-3 | 0%
FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-3 | 100%
INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-3 | 50%
New Concrete Curb Next to Existing Wall | 100%
POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-3 | 0%
139 - OG3 - Division 4 | 0%
Overhead protection for Masonry | 0%
141 - OG3 - Divisiono 7 | 0%
JOINT SEALANTS EXTG BLDGS - OG-3 | 0%
PENETRATION FIRESTOPPING EXTG BLDG - OG-3 | 0%
144 - OG3 - Division 10 | 0%
AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-3 | 0%
MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-3 | 0%
150 - OG3 - Division 31 | 25%
BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-3 | 0%
EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-3 | 25%
INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-3 | 0%
151 - OG4 - Division 2 | 10%
Cut openings in slab - 2nd floor | 0%
Remove Areaway grate | 0%
Remove Areaway slab and drain | 10%
Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 0%
Sawcut and remove portion of areaway wall | 0%
Sawcut slab opening for mechanical - cellar and 1st floor | 0%
152 - OG4 - Division 3 | 250%
DRILL & GROUT DOWELS - OG-4 | 100%
FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-4 | 0%
FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-4 | 0%
INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-4 | 50%
New Concrete Curb Next to Existing Wall | 100%
POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-4 | 0%
153 - OG4 - Division 4 | 0%
Overhead protection for Masonry | 0%
155 - OG4 - Division 7 | 0%
JOINT SEALANTS EXTG BLDGS - OG-4 | 0%
PENETRATION FIRESTOPPING EXTG BLDG - OG 4 | 0%
158 - OG4 - Division 10 | 0%
AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-4 | 0%
MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-4 | 0%
164 - OG4 - Division 31 | 0%
BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-4 | 0%
EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-4 | 0%
INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-4 | 0%
165 - OG5 - Division 2 | 20%
Cut openings in slab - 2nd floor | 0%
Remove Areaway grate | 0%
Remove Areaway slab and drain | 20%
Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 0%
Sawcut and remove portion of areaway wall | 0%
Sawcut slab opening for mechanical - cellar and 1st floor | 0%
166 - OG5 - Division 3 | 200%
DRILL & GROUT DOWELS - OG-5 | 50%
FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-5 | 0%
FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-5 | 0%
INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-5 | 50%
New Concrete Curb Next to Existing Wall | 100%
POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-5 | 0%
167 - OG5 - Division 4 | 0%
Overhead protection for Masonry | 0%
169 - OG5 - Division 7 | 0%
JOINT SEALANTS EXTG BLDGS - OG-5 | 0%
PENETRATION FIRESTOPPING EXTG BLDG - OG 5 | 0%
172 - OG5 - Division 10 | 0%
AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-5 | 0%
MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-5 | 0%
178 - OG5 - Division 31 | 0%
BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-5 | 0%
EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-5 | 0%
INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-5 | 0%
179 - OG6 - Division 2 | 10%
Cut openings in slab - 2nd floor | 0%
Remove Areaway grate - cellar and basement | 0%
Remove Areaway slab and drain - basement | 10%
Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 0%
Sawcut and remove portion of areaway wall - basement | 0%
Sawcut slab opening for mechanical - 1st floor | 0%
180 - OG6 - Division 3 | 135%
DRILL & GROUT DOWELS - OG-6 | 10%
FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-6 | 0%
FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-6 | 0%
INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-6 | 25%
New Concrete Curb Next to Existing Wall | 100%
POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-6 | 0%
181 - OG6 - Division 4 | 0%
Overhead protection for Masonry | 0%
183 - OG6 - Division 7 | 0%
JOINT SEALANTS EXTG BLDGS - OG 6 | 0%
PENETRATION FIRESTOPPING EXTG BLDG - OG-6 | 0%
184 - OG6 - Division 8 | 0%
ALUMINUM WINDOWS | 0%
186 - OG6 - Division 10 | 0%
AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-6 | 0%
MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-6 | 0%
192 - OG6 - Division 31 | 0%
BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-6 | 0%
EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-6 | 0%
INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-6 | 0%
195 - OG8 - Division 3 | 228%
FINISH SLABS - OG-8 | 33%
POUR CONCRETE NEW BUILDINGS - OG-8 | 95%
SET ANCHOR BOLTS FOR STEEL COLUMNS - OG-8 | 100%
199 - OG8 - Division 7 | 100%
3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG-8 | 100%
JOINT SEALANTS NEW BLDGS - OG-8 | 0%
PENETRATION FIRESTOPPING NEW BLDG - OG-8 | 0%
200 - OG8 - Division 8 | 10%
(1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG-8 | 10%
202 - OG8 - Division 10 | 0%
Stairway Flood Access Door | 0%
207 - OG8 - Division 31 | 395%
BACKFILL NEW BLDGS - OG-8 | 95%
DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG-8 | 100%
EXCAVATION NEW BLDGS - OG-8 | 100%
STONE FOR FOUNDATION - OG-8 | 100%
208 - OG9 - Division 3 | 400%
FINISH SLABS - OG-9 | 100%
Plumbing Shafts | 100%
POUR CONCRETE NEW BUILDINGS - OG-9 | 100%
SET ANCHOR BOLTS FOR STEEL COLUMNS - OG-9 | 100%
212 - OG9 - Division 7 | 100%
3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG-9 | 100%
JOINT SEALANTS NEW BLDGS - OG-9 | 0%
PENETRATION FIRESTOPPING NEW BLDG - OG-9 | 0%
213 - OG9 - Division 8 | 10%
(1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG-9 | 10%
220 - OG9 - Division 31 | 400%
BACKFILL NEW BLDGS - OG-9 | 100%
DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG-9 | 100%
EXCAVATION NEW BLDGS - OG-9 | 100%
STONE FOR FOUNDATION - OG-9 | 100%
221 - OG10 - Division 3 | 400%
FINISH SLABS - OG-10 | 100%
Plumbing Shafts | 100%
POUR CONCRETE NEW BUILDINGS - OG-10 | 100%
SET ANCHOR BOLTS FOR STEEL COLUMNS - OG-10 | 100%
225 - OG10 - Division 7 | 100%
3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG-10 | 100%
JOINT SEALANTS NEW BLDGS - OG-10 | 0%
PENETRATION FIRESTOPPING NEW BLDG - OG-10 | 0%
226 - OG10 - Division 8 | 10%
(1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG-10 | 10%
233 - OG10 - Division 31 | 400%
BACKFILL NEW BLDGS - OG-10 | 100%
DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG-10 | 100%
EXCAVATION NEW BLDGS - OG-10 | 100%
STONE FOR FOUNDATION - OG-10 | 100%
235 - OGE - Division 3 | 0%
CONCRETE FOOTING FOR SITE FURNISHING - OGE | 0%
CONCRETE SITE RETAINING WALL AND FOOTINGS - OGE | 0%
241 - OGW - Division 3 | 0%
CONCRETE FOOTING FOR SITE FURNISHING - OGW | 0%
CONCRETE SITE RETAINING WALL AND FOOTINGS OGW | 0%
242 - OGW - Division 11 | 0%
EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - OGW | 0%
247 - S8 - Division 2 | 0%
Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 0%
Sawcut and remove portion of areaway wall - cellar | 0%
248 - S8 - Division 3 | 0%
CONCRETE FOOTING FOR SITE FURNISHING - S8 | 0%
253 - S8 - Division 10 | 0%
Stairway Flood Access Door | 0%
254 - S8 - Division 11 | 0%
EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - S8 | 0%
260 - S81 - Division 3 | 0%
DRILL & GROUT DOWELS - S8 | 0%
FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - S8 | 0%
INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - S8 | 0%
POUR CONCRETE FLOOD BARRIER FOUNDATIONS - S8 | 0%
261 - S81 - Division 4 | 0%
Overhead protection for Masonry | 0%
263 - S81 - Division 7 | 0%
JOINT SEALANTS EXTG BLDGS - S8 | 0%
PENETRATION FIRESTOPPING EXTG BLDG - S8 | 0%
266 - S81 - Division 10 | 0%
AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - S8 | 0%
WINDOW FLOODGATES (8.06 AND 8.14) - S8 | 0%
271 - S81 - Division 31 | 0%
BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - S8 | 0%
EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - S8 | 0%
INFILL AREAWAY W/ GRAVEL/TOPSOIL - S8 | 0%
272 - S82 - Division 3 | 0%
FINISH SLABS - S8 | 0%
POUR CONCRETE NEW BUILDINGS - S8 | 0%
SET ANCHOR BOLTS FOR STEEL COLUMNS - S8 | 0%
274 - S82 - Division 7 | 0%
3" RIGID INSULATION UNDER GRADE NEW BLDGS - S8 | 0%
JOINT SEALANTS NEW BLDGS - S8 | 0%
PENETRATION FIRESTOPPING NEW BLDG - S8 | 0%
275 - S82 - Division 8 | 10%
(1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S8 | 10%
277 - S82 - Division 31 | 0%
BACKFILL NEW BLDGS - S8 | 0%
DENSE GRADED STONE BASE FOR FOUNDATION SLAB - S8 | 0%
EXCAVATION NEW BLDGS - S8-2 | 0%
Sully | 2413%
097 - SGN - Division 3 | 100%
CONCRETE DUCTBANKS - SGN | 100%
098 - SGN - Division 11 | 0%
2-5 year play equipment | 0%
5-12 year play equipment | 0%
Crackle Corn | 0%
Install Water Play Equipment and Piping | 0%
Jet Spray | 0%
Splash Pad | 0%
100 - SGN - Division 31 | 233.1%
BACKFILL - SGN | 40%
DRINKING FOUNTAIN - SGN | 0%
EXCAVATION FOR SITE FURNISHING FOOTINGS - SGN | 0%
HAND EXCAVATION AS NEEDED - SGN | 100%
LANDSCAPE BOULDERS - SGN | 0%
SITE FURNISHINGS - SGN | 0%
TREE PROTECTION - SGN | 93.12%
102 - SGN - Division 33 | 405%
CATCH BASIN DRAINS AND CONNECTIONS - SGN | 50%
ELECTRICAL CONDUIT TRENCHES - SGN | 100%
REMOVE AREA DRAINS - SGN | 45%
SEWER / DRAINAGE PIPE - SGN | 10%
TEST CONDENSATE, STEAM - SGN | 100%
TEST HW, CW - SGN | 100%
104 - SGS - Division 3 | 0%
CONCRETE DUCTBANKS - SGS | 0%
106 - SGS - Division 31 | 180%
BACKFILL - SGS | 0%
BOLLARDS - SGS | 0%
DRINKING FOUNTAIN - SGS | 0%
EXCAVATION FOR SITE FURNISHING FOOTINGS - SGS | 0%
HAND EXCAVATION AS NEEDED - SGS | 100%
SITE FURNISHINGS - SGS | 0%
TREE PROTECTION - SGS | 80%
108 - SGS - Division 33 | 169%
CATCH BASIN DRAINS AND CONNECTIONS - SGS | 50%
ELECTRICAL CONDUIT TRENCHES - SGS | 0%
REMOVE AREA DRAINS - SGS | 0%
SEWER / DRAINAGE PIPE - SGS | 0%
TEST CONDENSATE, STEAM - SGS | 44%
TEST HW, CW - SGS | 75%
235 - OGE - Division 3 | 80%
CONCRETE DUCTBANKS - OGE | 80%
237 - OGE - Division 31 | 237.7%
BACKFILL - OGE | 50%
BACKFILL FOR ASPHALT PAVEMENTS - OGE | 0%
DRINKING FOUNTAIN - OGE | 0%
EXCAVATE FOR ASPHALT PAVEMENTS - OGE | 0%
EXCAVATION FOR SITE FURNISHING FOOTINGS - OGE | 0%
HAND EXCAVATION AS NEEDED - OGE | 94.55%
SITE FURNISHINGS - OGE | 0%
TREE PROTECTION - OGE | 93.12%
239 - OGE - Division 33 | 270%
CATCH BASIN DRAINS AND CONNECTIONS - OGE | 10%
DRAINAGE MANHOLES - OGE | 0%
ELECTRICAL CONDUIT TRENCHES - OGE | 90%
REMOVE AREA DRAINS - OGE | 0%
SEWER / DRAINAGE PIPE - OGE | 0%
TEST CONDENSATE, STEAM - OGE | 70%
TEST HW, CW - OGE | 100%
241 - OGW - Division 3 | 90%
CONCRETE DUCTBANKS - OGW | 90%
242 - OGW - Division 11 | 0%
2-5 year play equipment | 0%
5-12 year play equipment | 0%
Aquavator | 0%
Crackle Corn | 0%
Install Water Play Equipment and Piping | 0%
Jet Spray | 0%
244 - OGW - Division 31 | 246.3%
BACKFILL - OGW | 60.05%
BACKFILL FOR ASPHALT PAVEMENTS - OGW | 0%
DRINKING FOUNTAIN - OGW | 0%
EXCAVATE FOR ASPHALT PAVEMENTS - OGW | 0%
EXCAVATION FOR SITE FURNISHING FOOTINGS - OGW | 0%
HAND EXCAVATION AS NEEDED - OGW | 94.25%
LANDSCAPE BOULDERS - OGW | 0%
SITE FURNISHINGS - OGW | 0%
TREE PROTECTION - OGW | 91.97%
246 - OGW - Division 33 | 230%
CATCH BASIN DRAINS AND CONNECTIONS - OGW | 0%
ELECTRICAL CONDUIT TRENCHES - OGW | 100%
REMOVE AREA DRAINS - OGW | 0%
SEWER / DRAINAGE PIPE - OGW | 0%
TEST CONDENSATE, STEAM - OGW | 30%
TEST HW, CW - OGW | 100%
248 - S8 - Division 3 | 0%
CONCRETE DUCTBANKS - S8 | 0%
254 - S8 - Division 11 | 0%
2-5 year play equipment | 0%
5-12 year play equipment | 0%
Aquavator | 0%
Arch Jet | 0%
Install Water Play Equipment and Piping | 0%
Mist Spray | 0%
Splash Pad | 0%
257 - S8 - Division 31 | 122%
BACKFILL - S8 | 0%
BACKFILL FOR ASPHALT PAVEMENTS - S8 | 0%
DRINKING FOUNTAIN - S8 | 0%
EXCAVATE FOR ASPHALT PAVEMENTS - S8 | 0%
EXCAVATION FOR SITE FURNISHING FOOTINGS - S8 | 0%
HAND EXCAVATION AS NEEDED - S8 | 80%
SITE FURNISHINGS - S8 | 0%
TREE PROTECTION - S8 | 42%
259 - S8 - Division 33 | 50%
CATCH BASIN DRAINS AND CONNECTIONS - S8 | 50%
ELECTRICAL CONDUIT TRENCHES - S8 | 0%
REMOVE AREA DRAINS - S8 | 0%
SEWER / DRAINAGE PIPE - S8 | 0%
TEST CONDENSATE, STEAM - S8 | 0%
278 - Allowance - Division 1 | 0%
CON EDISON ELECTRICAL UTILITY SERVICE FEE | 0%
NATIONAL GRID GAS UTILITY -CIAC | 0%
Grand Total | 30545%