## Sheet1
Cost Code | 6 | 7 | Area | Activity Description | Spec Division | Location | SOV QTY | SOV UNIT | SOV UNIT COST | SOV COST | Quan | Unit | Crew | MH | Total Labor | Total Labor UC | PM | PM UC | CM | CM UC | Total Equip | Total Eqp UC | Subs | Subs UC | sub type | Allowance | Allowance UC | Total UC | Total | SCHEDULE OF VALUES ITEM | COMMENTS
02-1000 | 02 | 1000 | SGN | EROSION CONTROL FABRIC - SGN | Division 02 | SURSFIDE GARDENS - NORTH | 7166 | SF | 2.3981 | 17184.7593 |  |  |  |  | #REF! | [14 empty] | SOV
02-1000 | 02 | 1000 | SGS | EROSION CONTROL FABRIC - SGS | Division 02 | SURSFIDE GARDENS - SOUTH | 7165 | SF | 2.3981 | 17182.3612 |  |  |  |  | #REF! | [14 empty] | SOV
02-1000 | 02 | 1000 | OGE | EROSION CONTROL FABRIC - OGE | Division 02 | O'DWYER GARDENS - EAST | 18440 | SF | 2.3981 | 44220.8989 |  |  |  |  | #REF! | [14 empty] | SOV
02-1000 | 02 | 1000 | OGW | EROSION CONTROL FABRIC - OGW | Division 02 | O'DWYER GARDENS - WEST | 1235 | SF | 2.3981 | 2961.6491 |  |  |  |  | #REF! | [14 empty] | SOV
02-1100 | 02 | 1100 | SGN | INLET PROTECTION - SGN | Division 02 | SURSFIDE GARDENS - NORTH | 20 | EA | 311.8133 | 6236.2667 |  |  |  |  | #REF! | [14 empty] | SOV
02-1100 | 02 | 1100 | SGS | INLET PROTECTION - SGS | Division 02 | SURSFIDE GARDENS - SOUTH | 15 | EA | 311.8133 | 4677.2 |  |  |  |  | #REF! | [14 empty] | SOV
02-1100 | 02 | 1100 | OGE | INLET PROTECTION - OGE | Division 02 | O'DWYER GARDENS - EAST | 25 | EA | 311.8133 | 7795.3333 |  |  |  |  | #REF! | [14 empty] | SOV
02-1100 | 02 | 1100 | OGW | INLET PROTECTION - OGW | Division 02 | O'DWYER GARDENS - WEST | 22 | EA | 311.8133 | 6859.8933 |  |  |  |  | #REF! | [14 empty] | SOV
02-1100 | 02 | 1100 | S8 | INLET PROTECTION - S8 | Division 02 | SITE 8 | 14 | EA | 311.8133 | 4365.3867 |  |  |  |  | #REF! | [14 empty] | SOV
02-1200 | 02 | 1200 | SGN | SILT FENCE - SGN | Division 02 | SURSFIDE GARDENS - NORTH | 1530 | LF | 3.7952 | 5806.6968 |  |  |  |  | #REF! | [14 empty] | SOV
02-1200 | 02 | 1200 | SGS | SILT FENCE - SGS | Division 02 | SURSFIDE GARDENS - SOUTH | 1940 | LF | 3.7952 | 7362.7397 |  |  |  |  | #REF! | [14 empty] | SOV
02-1200 | 02 | 1200 | OGE | SILT FENCE - OGE | Division 02 | O'DWYER GARDENS - EAST | 1286 | LF | 3.7952 | 4880.6615 |  |  |  |  | #REF! | [14 empty] | SOV
02-1200 | 02 | 1200 | OGW | SILT FENCE - OGW | Division 02 | O'DWYER GARDENS - WEST | 1739 | LF | 3.7952 | 6599.8992 |  |  |  |  | #REF! | [14 empty] | SOV
02-1200 | 02 | 1200 | S8 | SILT FENCE - S8 | Division 02 | SITE 8 | 968 | LF | 3.7952 | 3673.7794 |  |  |  |  | #REF! | [14 empty] | SOV
02-1300 | 02 | 1300 | SGN | STABILIZED CONSTRUCTION ENTRANCE - SGN | Division 02 | SURSFIDE GARDENS - NORTH | 1610 | SF | 6.5342 | 10520.1143 |  |  |  |  | #REF! | [14 empty] | SOV
02-1300 | 02 | 1300 | SGS | STABILIZED CONSTRUCTION ENTRANCE - SGS | Division 02 | SURSFIDE GARDENS - SOUTH | 1613 | SF | 6.5342 | 10539.717 |  |  |  |  | #REF! | [14 empty] | SOV
02-1300 | 02 | 1300 | OGE | STABILIZED CONSTRUCTION ENTRANCE - OGE | Division 02 | O'DWYER GARDENS - EAST | 1580 | SF | 6.5342 | 10324.0873 |  |  |  |  | #REF! | [14 empty] | SOV
02-1300 | 02 | 1300 | OGW | STABILIZED CONSTRUCTION ENTRANCE - OGW | Division 02 | O'DWYER GARDENS - WEST | 1605 | SF | 6.5342 | 10487.4432 |  |  |  |  | #REF! | [14 empty] | SOV
02-1300 | 02 | 1300 | S8 | STABILIZED CONSTRUCTION ENTRANCE - S8 | Division 02 | SITE 8 | 1522 | SF | 6.5342 | 9945.1019 |  |  |  |  | #REF! | [14 empty] | SOV
02-1400 | 02 | 1400 | SGN | MANTAIN EROSION CONTROL - SGN | Division 02 | SURSFIDE GARDENS - NORTH | 11 | WEEK | 777.77 | 8555.47 |  |  |  |  | #REF! | [14 empty] | SOV
02-1400 | 02 | 1400 | SGS | MANTAIN EROSION CONTROL - SGS | Division 02 | SURSFIDE GARDENS - SOUTH | 11 | WEEK | 777.77 | 8555.47 |  |  |  |  | #REF! | [14 empty] | SOV
02-1400 | 02 | 1400 | OGE | MANTAIN EROSION CONTROL - OGE | Division 02 | O'DWYER GARDENS - EAST | 11 | WEEK | 777.77 | 8555.47 |  |  |  |  | #REF! | [14 empty] | SOV
02-1400 | 02 | 1400 | OGW | MANTAIN EROSION CONTROL - OGW | Division 02 | O'DWYER GARDENS - WEST | 11 | WEEK | 777.77 | 8555.47 |  |  |  |  | #REF! | [14 empty] | SOV
02-1400 | 02 | 1400 | S8 | MANTAIN EROSION CONTROL - S8 | Division 02 | SITE 8 | 11 | WEEK | 777.77 | 8555.47 |  |  |  |  | #REF! | [14 empty] | SOV
02-1500 | 02 | 1500 | SGN | REMOVE EROSION CONTROL - SGN | Division 02 | SURSFIDE GARDENS - NORTH | 1 | LOC | 9993.18 | 9993.18 |  |  |  |  | #REF! | [14 empty] | SOV
02-1500 | 02 | 1500 | SGS | REMOVE EROSION CONTROL - SGS | Division 02 | SURSFIDE GARDENS - SOUTH | 1 | LOC | 9993.18 | 9993.18 |  |  |  |  | #REF! | [14 empty] | SOV
02-1500 | 02 | 1500 | OGE | REMOVE EROSION CONTROL - OGE | Division 02 | O'DWYER GARDENS - EAST | 1 | LOC | 9993.18 | 9993.18 |  |  |  |  | #REF! | [14 empty] | SOV
02-1500 | 02 | 1500 | OGW | REMOVE EROSION CONTROL - OGW | Division 02 | O'DWYER GARDENS - WEST | 1 | LOC | 9993.18 | 9993.18 |  |  |  |  | #REF! | [14 empty] | SOV
02-1500 | 02 | 1500 | S8 | REMOVE EROSION CONTROL - S8 | Division 02 | SITE 8 | 1 | LOC | 9993.18 | 9993.18 |  |  |  |  | #REF! | [14 empty] | SOV
02-1700 | 02 | 1700 | SGN | REMOVE FENCE - SGN | Division 02 | SURSFIDE GARDENS - NORTH | 2350 | LF | 2.7241 | 6401.7116 |  |  |  |  | #REF! | [14 empty] | SOV
02-1700 | 02 | 1700 | SGS | REMOVE FENCE - SGS | Division 02 | SURSFIDE GARDENS - SOUTH | 2440 | LF | 2.7241 | 6646.8835 |  |  |  |  | #REF! | [14 empty] | SOV
02-1700 | 02 | 1700 | OGE | REMOVE FENCE - OGE | Division 02 | O'DWYER GARDENS - EAST | 2393 | LF | 2.7241 | 6518.8493 |  |  |  |  | #REF! | [14 empty] | SOV
02-1700 | 02 | 1700 | OGW | REMOVE FENCE - OGW | Division 02 | O'DWYER GARDENS - WEST | 680 | LF | 2.7241 | 1852.4102 |  |  |  |  | #REF! | [14 empty] | SOV
02-1700 | 02 | 1700 | S8 | REMOVE FENCE - S8 | Division 02 | SITE 8 | 1051 | LF | 2.7241 | 2863.0634 |  |  |  |  | #REF! | [14 empty] | SOV
02-1900 | 02 | 1900 | SGN | REMOVE FULL DEPTH ASPHALT PVMT - SGN | Division 02 | SURSFIDE GARDENS - NORTH | 3750 | SF | 1.3539 | 5076.9527 |  |  |  |  | #REF! | [14 empty] | SOV
02-1900 | 02 | 1900 | SGS | REMOVE FULL DEPTH ASPHALT PVMT - SGS | Division 02 | SURSFIDE GARDENS - SOUTH | 13765 | SF | 1.3539 | 18635.8009 |  |  |  |  | #REF! | [14 empty] | SOV
02-1900 | 02 | 1900 | OGE | REMOVE FULL DEPTH ASPHALT PVMT - OGE | Division 02 | O'DWYER GARDENS - EAST | 28350 | SF | 1.3539 | 38381.762 |  |  |  |  | #REF! | [14 empty] | SOV
02-1900 | 02 | 1900 | OGW | REMOVE FULL DEPTH ASPHALT PVMT - OGW | Division 02 | O'DWYER GARDENS - WEST | 31539 | SF | 1.3539 | 42699.2026 |  |  |  |  | #REF! | [14 empty] | SOV
02-1900 | 02 | 1900 | S8 | REMOVE FULL DEPTH ASPHALT PVMT - S8 | Division 02 | SITE 8 | 1750 | SF | 1.3539 | 2369.2446 |  |  |  |  | #REF! | [14 empty] | SOV
02-2000 | 02 | 2000 | SGN | REMOVE SITE FURNISHING - SGN | Division 02 | SURSFIDE GARDENS - NORTH | 36.4874 | LS | 116310.24 | 36272.2877 |  |  |  |  | #REF! | [14 empty] | SOV
02-2000 | 02 | 2000 | SGS | REMOVE SITE FURNISHING - SGS | Division 02 | SURSFIDE GARDENS - SOUTH | 13 | LS | 116310.24 | 12923.36 |  |  |  |  | #REF! | [14 empty] | SOV
02-2000 | 02 | 2000 | OGE | REMOVE SITE FURNISHING - OGE | Division 02 | O'DWYER GARDENS - EAST | 19.8824 | LS | 116310.24 | 19765.1388 |  |  |  |  | #REF! | [14 empty] | SOV
02-2000 | 02 | 2000 | OGW | REMOVE SITE FURNISHING - OGW | Division 02 | O'DWYER GARDENS - WEST | 23.3782 | LS | 116310.24 | 23240.3281 |  |  |  |  | #REF! | [14 empty] | SOV
02-2000 | 02 | 2000 | S8 | REMOVE SITE FURNISHING -S8 | Division 02 | SITE 8 | 24.2521 | LS | 116310.24 | 24109.1254 |  |  |  |  | #REF! | [14 empty] | SOV
02-2100 | 02 | 2100 | SGN | REMOVE CONCRETE CURB & STEPS - SGN | Division 02 | SURSFIDE GARDENS - NORTH | 164 | LF | 5.1721 | 848.2307 |  |  |  |  | #REF! | [14 empty] | SOV
02-2100 | 02 | 2100 | SGS | REMOVE CONCRETE CURB & STEPS - SGS | Division 02 | SURSFIDE GARDENS - SOUTH | 2410 | LF | 5.1721 | 12464.8537 |  |  |  |  | #REF! | [14 empty] | SOV
02-2100 | 02 | 2100 | OGE | REMOVE CONCRETE CURB & STEPS - OGE | Division 02 | O'DWYER GARDENS - EAST | 2791 | LF | 5.1721 | 14435.4384 |  |  |  |  | #REF! | [14 empty] | SOV
02-2100 | 02 | 2100 | OGW | REMOVE CONCRETE CURB & STEPS - OGW | Division 02 | O'DWYER GARDENS - WEST | 3941 | LF | 5.1721 | 20383.3977 |  |  |  |  | #REF! | [14 empty] | SOV
02-2100 | 02 | 2100 | S8 | REMOVE CONCRETE CURB & STEPS - S8 | Division 02 | SITE 8 | 624 | LF | 5.1721 | 3227.4144 |  |  |  |  | #REF! | [14 empty] | SOV
02-2200 | 02 | 2200 | SGN | REMOVE PVMTS - SGN | Division 02 | SURSFIDE GARDENS - NORTH | 30370 | SF | 1.4909 | 45278.4271 |  |  |  |  | #REF! | [14 empty] | SOV
02-2200 | 02 | 2200 | SGS | REMOVE PVMTS - SGS | Division 02 | SURSFIDE GARDENS - SOUTH | 20125 | SF | 1.4909 | 30004.2261 |  |  |  |  | #REF! | [14 empty] | SOV
02-2200 | 02 | 2200 | OGE | REMOVE PVMTS - OGE | Division 02 | O'DWYER GARDENS - EAST | 40520 | SF | 1.4909 | 60410.9933 |  |  |  |  | #REF! | [14 empty] | SOV
02-2200 | 02 | 2200 | OGW | REMOVE PVMTS - OGW | Division 02 | O'DWYER GARDENS - WEST | 41915 | SF | 1.4909 | 62490.7893 |  |  |  |  | #REF! | [14 empty] | SOV
02-2200 | 02 | 2200 | S8 | REMOVE PVMTS - S8 | Division 02 | SITE 8 | 23123 | SF | 1.4909 | 34473.9239 |  |  |  |  | #REF! | [14 empty] | SOV
02-6005 |  |  | OG1 |  |  |  | 2040 | SF |  | 22861.658
02-6005 |  |  | OG2 |  |  |  | 1210 | SF |  | 13560.101
02-6005 |  |  | OG3 |  |  |  | 1830 | SF |  | 20508.252
02-6005 |  |  | OG4 |  |  |  | 1750 | SF |  | 19611.7164
02-6005 |  |  | OG5 |  |  |  | 1630 | SF |  | 18266.913
02-6005 |  |  | OG6 |  |  |  | 3310 | SF |  | 37094.1607
02-6005 |  |  | SG1 |  |  |  | 2790 | SF |  | 31266.6793
02-6005 |  |  | SG2 |  |  |  | 2370 | SF |  | 26559.8673
02-6005 |  |  | SG3 |  |  |  | 3470 | SF |  | 38887.2319
02-6005 |  |  | SG4 |  |  |  | 3340 | SF |  | 37430.3616
02-6005 |  |  | SG5 |  |  |  | 3470 | SF |  | 38887.2319
02-6005 |  |  | S81 |  |  |  | 6110 | SF |  | 68472.9069
02-6010 |  |  | OG1 |  |  |  | 2 | EA |  | 2196.2489
02-6010 |  |  | OG2 |  |  |  | 3 | EA |  | 3294.3733
02-6010 |  |  | OG3 |  |  |  | 3 | EA |  | 3294.3733
02-6010 |  |  | OG4 |  |  |  | 2 | EA |  | 2196.2489
02-6010 |  |  | OG5 |  |  |  | 2 | EA |  | 2196.2489
02-6010 |  |  | OG6 |  |  |  | 2 | EA |  | 2196.2489
02-6010 |  |  | SG1 |  |  |  | 3 | EA |  | 3294.3733
02-6010 |  |  | SG2 |  |  |  | 2 | EA |  | 2196.2489
02-6010 |  |  | SG3 |  |  |  | 6 | EA |  | 6588.7467
02-6010 |  |  | SG4 |  |  |  | 4 | EA |  | 4392.4978
02-6010 |  |  | SG5 |  |  |  | 3 | EA |  | 3294.3733
02-6010 |  |  | S81 |  |  |  | 4 | EA |  | 4392.4978
02-6015 |  |  | OG1 |  |  |  | 13 | EA |  | 3846.4035
02-6015 |  |  | OG2 |  |  |  | 13 | EA |  | 3846.4035
02-6015 |  |  | OG3 |  |  |  | 14 | EA |  | 4142.2806
02-6015 |  |  | OG4 |  |  |  | 12 | EA |  | 3550.5263
02-6015 |  |  | OG5 |  |  |  | 12 | EA |  | 3550.5263
02-6015 |  |  | OG6 |  |  |  | 27 | EA |  | 7988.6841
02-6015 |  |  | SG1 |  |  |  | 13 | EA |  | 3846.4035
02-6015 |  |  | SG2 |  |  |  | 12 | EA |  | 3550.5263
02-6015 |  |  | SG3 |  |  |  | 16 | EA |  | 4734.035
02-6015 |  |  | SG4 |  |  |  | 10 | EA |  | 2958.7719
02-6015 |  |  | SG5 |  |  |  | 14 | EA |  | 4142.2806
02-6015 |  |  | S81 |  |  |  | 29 | EA |  | 8580.4385
02-6020 |  |  | OG1 |  |  |  | 1 | EA |  | 823.5933
02-6020 |  |  | OG2 |  |  |  | 3 | EA |  | 2470.78
02-6020 |  |  | OG3 |  |  |  | 1 | EA |  | 823.5933
02-6020 |  |  | OG4 |  |  |  | 1 | EA |  | 823.5933
02-6020 |  |  | OG5 |  |  |  | 1 | EA |  | 823.5933
02-6020 |  |  | OG6 |  |  |  | 5 | EA |  | 4117.9667
02-6020 |  |  | SG1 |  |  |  | 3 | EA |  | 2470.78
02-6020 |  |  | SG2 |  |  |  | 1 | EA |  | 823.5933
02-6020 |  |  | SG3 |  |  |  | 3 | EA |  | 2470.78
02-6020 |  |  | SG4 |  |  |  | 1 | EA |  | 823.5933
02-6020 |  |  | SG5 |  |  |  | 1 | EA |  | 823.5933
02-6020 |  |  | S81 |  |  |  | 3 | EA |  | 2470.78
02-6025 |  |  | OG1 |  |  |  | 4 | EA |  | 9831.6385
02-6025 |  |  | OG2 |  |  |  | 4 | EA |  | 9831.6385
02-6025 |  |  | OG3 |  |  |  | 4 | EA |  | 9831.6385
02-6025 |  |  | OG4 |  |  |  | 4 | EA |  | 9831.6385
02-6025 |  |  | OG5 |  |  |  | 4 | EA |  | 9831.6385
02-6025 |  |  | OG6 |  |  |  | 4 | EA |  | 9831.6385
02-6025 |  |  | SG1 |  |  |  | 5 | EA |  | 12289.5481
02-6025 |  |  | SG2 |  |  |  | 5 | EA |  | 12289.5481
02-6025 |  |  | SG3 |  |  |  | 5 | EA |  | 12289.5481
02-6025 |  |  | SG4 |  |  |  | 5 | EA |  | 12289.5481
02-6025 |  |  | SG5 |  |  |  | 5 | EA |  | 12289.5481
02-6025 |  |  | S81 |  |  |  | 5 | EA |  | 12289.5481
02-6030 |  |  | OG1 |  |  |  | 1520 | SF |  | 5374.72
02-6030 |  |  | OG2 |  |  |  | 1590 | SF |  | 5622.24
02-6030 |  |  | OG3 |  |  |  | 2280 | SF |  | 8062.08
02-6030 |  |  | OG4 |  |  |  | 1990 | SF |  | 7036.64
02-6030 |  |  | OG5 |  |  |  | 2080 | SF |  | 7354.88
02-6035 |  |  | S81 |  |  |  | 1 | EA |  | 1520.48
02-6040 |  |  | OG1 |  |  |  | 2 | EA |  | 1586.5878
02-6040 |  |  | OG2 |  |  |  | 2 | EA |  | 1586.5878
02-6040 |  |  | OG3 |  |  |  | 2 | EA |  | 1586.5878
02-6040 |  |  | OG4 |  |  |  | 2 | EA |  | 1586.5878
02-6040 |  |  | OG5 |  |  |  | 2 | EA |  | 1586.5878
02-6040 |  |  | OG6 |  |  |  | 1 | EA |  | 793.2939
02-6040 |  |  | SG1 |  |  |  | 2 | EA |  | 1586.5878
02-6040 |  |  | SG2 |  |  |  | 2 | EA |  | 1586.5878
02-6040 |  |  | SG3 |  |  |  | 2 | EA |  | 1586.5878
02-6040 |  |  | SG4 |  |  |  | 2 | EA |  | 1586.5878
02-6040 |  |  | SG5 |  |  |  | 2 | EA |  | 1586.5878
02-6040 |  |  | S81 |  |  |  | 2 | EA |  | 1586.5878
02-6045 |  |  | OG1 |  |  |  | 18 | EA |  | 4801.5158
02-6045 |  |  | OG2 |  |  |  | 17 | EA |  | 4534.7649
02-6045 |  |  | OG3 |  |  |  | 17 | EA |  | 4534.7649
02-6045 |  |  | OG4 |  |  |  | 17 | EA |  | 4534.7649
02-6045 |  |  | OG5 |  |  |  | 17 | EA |  | 4534.7649
02-6045 |  |  | OG6 |  |  |  | 23 | EA |  | 6135.2702
02-6045 |  |  | SG3 |  |  |  | 5 | EA |  | 1333.7544
02-6050 |  |  | SG1 |  |  |  | 3 | EA |  | 10058.32
02-6050 |  |  | SG2 |  |  |  | 1 | EA |  | 3352.7733
02-6050 |  |  | SG4 |  |  |  | 1 | EA |  | 3352.7733
02-6050 |  |  | SG5 |  |  |  | 1 | EA |  | 3352.7733
02-6055 |  |  | OG1 |  |  |  | 6 | EA |  | 6037.2
02-6055 |  |  | OG2 |  |  |  | 2 | EA |  | 2012.4
02-6055 |  |  | OG3 |  |  |  | 3 | EA |  | 3018.6
02-6055 |  |  | OG4 |  |  |  | 4 | EA |  | 4024.8
02-6055 |  |  | OG5 |  |  |  | 6 | EA |  | 6037.2
02-6055 |  |  | OG6 |  |  |  | 2 | EA |  | 2012.4
02-6055 |  |  | SG3 |  |  |  | 5 | EA |  | 5031
02-6055 |  |  | SG4 |  |  |  | 2 | EA |  | 2012.4
02-6055 |  |  | SG5 |  |  |  | 4 | EA |  | 4024.8
02-6060 |  |  | OG3 |  |  |  | 1 | EA |  | 18249.4267
02-6060 |  |  | OG4 |  |  |  | 1 | EA |  | 18249.4267
02-6060 |  |  | OG5 |  |  |  | 1 | EA |  | 18249.4267
02-6060 |  |  | OG6 |  |  |  | 1 | EA |  | 18249.4267
02-6060 |  |  | SG1 |  |  |  | 1 | EA |  | 18249.4267
02-6060 |  |  | SG2 |  |  |  | 1 | EA |  | 18249.4267
02-6060 |  |  | SG3 |  |  |  | 1 | EA |  | 18249.4267
02-6060 |  |  | SG4 |  |  |  | 1 | EA |  | 18249.4267
02-6060 |  |  | SG5 |  |  |  | 1 | EA |  | 18249.4267
03-1000 | 03 | 1000 | SG6 | FORMWORK NEW BUILDING - SG6 | Division 03 | SURFSIDE GARDENS - SG6 | 12658 | SF | 31.644 | 400549.6081 |  |  |  |  | #REF! | [14 empty] | SOV
03-1000 | 03 | 1000 | SG7 | FORMWORK NEW BUILDING - SG7 | Division 03 | SURFSIDE GARDENS - SG7 | 9518 | SF | 31.644 | 301187.4838 |  |  |  |  | #REF! | [14 empty] | SOV
03-1000 | 03 | 1000 | OG8 | FORMWORK NEW BUILDING - OG8 | Division 03 | O'DWYER GARDENS - OG8 | 20263 | SF | 31.644 | 641202.1416 |  |  |  |  | #REF! | [14 empty] | SOV
03-1000 | 03 | 1000 | OG9 | FORMWORK NEW BUILDING - OG9 | Division 03 | O'DWYER GARDENS - OG9 | 5800 | SF | 31.644 | 183535.1341 |  |  |  |  | #REF! | [14 empty] | SOV
03-1000 | 03 | 1000 | OG10 | FORMWORK NEW BUILDING - OG10 | Division 03 | O'DWYER GARDENS - OG10 | 5463 | SF | 31.644 | 172871.1099 |  |  |  |  | #REF! | [14 empty] | SOV
03-1000 | 03 | 1000 | S82 | FORMWORK NEW BUILDING - S8 | Division 03 | SITE 8 - S2 | 8549 | SF | 31.644 | 270524.4588 |  |  |  |  | #REF! | [14 empty] | SOV
03-1100 | 03 | 1100 | SG1 | FORM FLOOD BARRIER FOUNDATIONS - SG1 | Division 03 | SURFSIDE GARDENS - SG1 | 1674 | SF | 25.9685 | 43471.231 |  |  |  |  | #REF! | [14 empty] | SOV
03-1100 | 03 | 1100 | SG2 | FORM FLOOD BARRIER FOUNDATIONS - SG2 | Division 03 | SURFSIDE GARDENS - SG2 | 1109 | SF | 25.9685 | 28799.0413 |  |  |  |  | #REF! | [14 empty] | SOV
03-1100 | 03 | 1100 | SG3 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - SG3 | Division 03 | SURFSIDE GARDENS - SG3 | 1768 | SF | 25.9685 | 45912.2679 |  |  |  |  | #REF! | [14 empty] | SOV
03-1100 | 03 | 1100 | SG4 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - SG4 | Division 03 | SURFSIDE GARDENS - SG4 | 3543 | SF | 25.9685 | 92006.3151 |  |  |  |  | #REF! | [14 empty] | SOV
03-1100 | 03 | 1100 | SG5 | FORM FLOOD BARRIER FOUNDATIONS - SG5 | Division 03 | SURFSIDE GARDENS - SG5 | 2891 | SF | 25.9685 | 75074.8679 |  |  |  |  | #REF! | [14 empty] | SOV
03-1100 | 03 | 1100 | OG1 | FORM FLOOD BARRIER FOUNDATIONS - OG1 | Division 03 | O'DWYER GARDENS - OG1 | 1006 | SF | 25.9685 | 26124.2882 |  |  |  |  | #REF! | [14 empty] | SOV
03-1100 | 03 | 1100 | OG2 | FORM FLOOD BARRIER FOUNDATIONS - OG2 | Division 03 | O'DWYER GARDENS - OG2 | 1026 | SF | 25.9685 | 26643.6577 |  |  |  |  | #REF! | [14 empty] | SOV
03-1100 | 03 | 1100 | OG3 | FORM FLOOD BARRIER FOUNDATIONS - OG3 | Division 03 | O'DWYER GARDENS - OG3 | 1026 | SF | 25.9685 | 26643.6577 |  |  |  |  | #REF! | [14 empty] | SOV
03-1100 | 03 | 1100 | OG4 | FORM FLOOD BARRIER FOUNDATIONS - OG4 | Division 03 | O'DWYER GARDENS - OG4 | 1026 | SF | 25.9685 | 26643.6577 |  |  |  |  | #REF! | [14 empty] | SOV
03-1100 | 03 | 1100 | OG5 | FORM FLOOD BARRIER FOUNDATIONS - OG5 | Division 03 | O'DWYER GARDENS - OG5 | 1026 | SF | 25.9685 | 26643.6577 |  |  |  |  | #REF! | [14 empty] | SOV
03-1100 | 03 | 1100 | OG6 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - OG6 | Division 03 | O'DWYER GARDENS - OG6 | 6557 | SF | 25.9685 | 170275.3057 |  |  |  |  | #REF! | [14 empty] | SOV
03-1100 | 03 | 1100 | S81 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - S8 | Division 03 | SITE 8 - S81 | 5224 | SF | 25.9685 | 135659.3255 |  |  |  |  | #REF! | [14 empty] | SOV
03-1300 | 03 | 1300 | SG6 | SET ANCHOR BOLTS FOR STEEL COLUMNS - SG6 | Division 03 | SURFSIDE GARDENS - SG6 | 44 | EA | 113.5106 | 4540.4233 |  |  |  |  | #REF! | [14 empty] | SOV
03-1300 | 03 | 1300 | SG7 | SET ANCHOR BOLTS FOR STEEL COLUMNS - SG7 | Division 03 | SURFSIDE GARDENS - SG7 | 60 | EA | 113.5106 | 4540.4233 |  |  |  |  | #REF! | [14 empty] | SOV
03-1300 | 03 | 1300 | OG8 | SET ANCHOR BOLTS FOR STEEL COLUMNS - OG8 | Division 03 | O'DWYER GARDENS - OG8 | 64 | EA | 113.5106 | 4540.4233 |  |  |  |  | #REF! | [14 empty] | SOV
03-1300 | 03 | 1300 | OG9 | SET ANCHOR BOLTS FOR STEEL COLUMNS - OG9 | Division 03 | O'DWYER GARDENS - OG9 | 40 | EA | 113.5106 | 4540.4233 |  |  |  |  | #REF! | [14 empty] | SOV
03-1300 | 03 | 1300 | OG10 | SET ANCHOR BOLTS FOR STEEL COLUMNS - OG10 | Division 03 | O'DWYER GARDENS - OG10 | 48 | EA | 113.5106 | 4540.4233 |  |  |  |  | #REF! | [14 empty] | SOV
03-1300 | 03 | 1300 | S82 | SET ANCHOR BOLTS FOR STEEL COLUMNS - S8 | Division 03 | SITE 8 - S2 | 52 | EA | 113.5106 | 4540.4233 |  |  |  |  | #REF! | [14 empty] | SOV
03-1400 | 03 | 1400 | SG1 | DRILL & GROUT DOWELS - SG1 | Division 03 | SURFSIDE GARDENS - SG1 | 228 | EA | 23.9138 | 5452.3351 |  |  |  |  | #REF! | [14 empty] | SOV
03-1400 | 03 | 1400 | SG2 | DRILL & GROUT DOWELS - SG2 | Division 03 | SURFSIDE GARDENS - SG2 | 122 | EA | 23.9138 | 2917.4776 |  |  |  |  | #REF! | [14 empty] | SOV
03-1400 | 03 | 1400 | SG3 | DRILL & GROUT DOWELS - SG3 | Division 03 | SURFSIDE GARDENS - SG3 | 286 | EA | 23.9138 | 6839.3327 |  |  |  |  | #REF! | [14 empty] | SOV
03-1400 | 03 | 1400 | SG4 | DRILL & GROUT DOWELS - SG4 | Division 03 | SURFSIDE GARDENS - SG4 | 943 | EA | 23.9138 | 22550.6668 |  |  |  |  | #REF! | [14 empty] | SOV
03-1400 | 03 | 1400 | SG5 | DRILL & GROUT DOWELS - SG5 | Division 03 | SURFSIDE GARDENS - SG5 | 582 | EA | 23.9138 | 13917.8028 |  |  |  |  | #REF! | [14 empty] | SOV
03-1400 | 03 | 1400 | OG1 | DRILL & GROUT DOWELS - OG1 | Division 03 | O'DWYER GARDENS - OG1 | 136 | EA | 23.9138 | 3252.2701 |  |  |  |  | #REF! | [14 empty] | SOV
03-1400 | 03 | 1400 | OG2 | DRILL & GROUT DOWELS - OG2 | Division 03 | O'DWYER GARDENS - OG2 | 136 | EA | 23.9138 | 3252.2701 |  |  |  |  | #REF! | [14 empty] | SOV
03-1400 | 03 | 1400 | OG3 | DRILL & GROUT DOWELS - OG3 | Division 03 | O'DWYER GARDENS - OG3 | 136 | EA | 23.9138 | 3252.2701 |  |  |  |  | #REF! | [14 empty] | SOV
03-1400 | 03 | 1400 | OG4 | DRILL & GROUT DOWELS - OG4 | Division 03 | O'DWYER GARDENS - OG4 | 136 | EA | 23.9138 | 3252.2701 |  |  |  |  | #REF! | [14 empty] | SOV
03-1400 | 03 | 1400 | OG5 | DRILL & GROUT DOWELS - OG5 | Division 03 | O'DWYER GARDENS - OG5 | 136 | EA | 23.9138 | 3252.2701 |  |  |  |  | #REF! | [14 empty] | SOV
03-1400 | 03 | 1400 | OG6 | DRILL & GROUT DOWELS - OG6 | Division 03 | O'DWYER GARDENS - OG6 | 1549 | EA | 23.9138 | 37042.3996 |  |  |  |  | #REF! | [14 empty] | SOV
03-1400 | 03 | 1400 | S81 | DRILL & GROUT DOWELS - S8 | Division 03 | SITE 8 - S81 | 907 | EA | 23.9138 | 21689.7718 |  |  |  |  | #REF! | [14 empty] | SOV
03-1500 | 03 | 1500 | SG1 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG1 | Division 03 | SURFSIDE GARDENS - SG1 | 12 | LOC | 2099.146 | 25189.7524 |  |  |  |  | #REF! | [14 empty] | SOV
03-1500 | 03 | 1500 | SG2 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG2 | Division 03 | SURFSIDE GARDENS - SG2 | 10 | LOC | 2099.146 | 20991.4604 |  |  |  |  | #REF! | [14 empty] | SOV
03-1500 | 03 | 1500 | SG3 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG3 | Division 03 | SURFSIDE GARDENS - SG3 | 17 | LOC | 2099.146 | 35685.4826 |  |  |  |  | #REF! | [14 empty] | SOV
03-1500 | 03 | 1500 | SG4 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG4 | Division 03 | SURFSIDE GARDENS - SG4 | 10 | LOC | 2099.146 | 20991.4604 |  |  |  |  | #REF! | [14 empty] | SOV
03-1500 | 03 | 1500 | SG5 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG5 | Division 03 | SURFSIDE GARDENS - SG5 | 10 | LOC | 2099.146 | 20991.4604 |  |  |  |  | #REF! | [14 empty] | SOV
03-1500 | 03 | 1500 | OG1 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG1 | Division 03 | O'DWYER GARDENS - OG1 | 11 | LOC | 2099.146 | 23090.6064 |  |  |  |  | #REF! | [14 empty] | SOV
03-1500 | 03 | 1500 | OG2 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG2 | Division 03 | O'DWYER GARDENS - OG2 | 11 | LOC | 2099.146 | 23090.6064 |  |  |  |  | #REF! | [14 empty] | SOV
03-1500 | 03 | 1500 | OG3 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG3 | Division 03 | O'DWYER GARDENS - OG3 | 11 | LOC | 2099.146 | 23090.6064 |  |  |  |  | #REF! | [14 empty] | SOV
03-1500 | 03 | 1500 | OG4 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG4 | Division 03 | O'DWYER GARDENS - OG4 | 10 | LOC | 2099.146 | 20991.4604 |  |  |  |  | #REF! | [14 empty] | SOV
03-1500 | 03 | 1500 | OG5 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG5 | Division 03 | O'DWYER GARDENS - OG5 | 10 | LOC | 2099.146 | 20991.4604 |  |  |  |  | #REF! | [14 empty] | SOV
03-1500 | 03 | 1500 | OG6 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG6 | Division 03 | O'DWYER GARDENS - OG6 | 23 | LOC | 2099.146 | 48280.3588 |  |  |  |  | #REF! | [14 empty] | SOV
03-1500 | 03 | 1500 | S81 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - S8 | Division 03 | SITE 8 - S81 | 29 | LOC | 2099.146 | 60875.2351 |  |  |  |  | #REF! | [14 empty] | SOV
03-1600 | 03 | 1600 | SGN | FORMWORK SITE CONCRETE - SGN | Division 03 | SURSFIDE GARDENS - NORTH | 1500 | SF | 31.644 | 47465.9939 |  |  |  |  | #REF! | [14 empty] | SOV
03-1600 | 03 | 1600 | SGS | FORMWORK SITE CONCRETE - SGS | Division 03 | SURSFIDE GARDENS - SOUTH | 1500 | SF | 31.644 | 47465.9939 |  |  |  |  | #REF! | [14 empty] | SOV
03-1600 | 03 | 1600 | OGE | FORMWORK SITE CONCRETE - OGE | Division 03 | O'DWYER GARDENS - EAST | 1500 | SF | 31.644 | 47465.9939 |  |  |  |  | #REF! | [14 empty] | SOV
03-1600 | 03 | 1600 | OGW | FORMWORK SITE CONCRETE - OGW | Division 03 | O'DWYER GARDENS - WEST | 1500 | SF | 31.644 | 47465.9939 |  |  |  |  | #REF! | [14 empty] | SOV
03-1600 | 03 | 1600 | S8 | FORMWORK SITE CONCRETE - S8 | Division 03 | SITE 8 | 1500 | SF | 31.644 | 47465.9939 |  |  |  |  | #REF! | [14 empty] | SOV
03-1900 | 03 | 1900 | SG6 | POUR CONCRETE NEW BUILDINGS - SG6 | Division 03 | SURFSIDE GARDENS - SG6 | 469 | CY | 320.3773 | 150256.9355 |  |  |  |  | #REF! | [14 empty] | SOV
03-1900 | 03 | 1900 | SG7 | POUR CONCRETE NEW BUILDINGS - SG7 | Division 03 | SURFSIDE GARDENS - SG7 | 575 | CY | 320.3773 | 184216.9252 |  |  |  |  | #REF! | [14 empty] | SOV
03-1900 | 03 | 1900 | OG8 | POUR CONCRETE NEW BUILDINGS - OG8 | Division 03 | O'DWYER GARDENS - OG8 | 1050 | CY | 320.3773 | 336396.1244 |  |  |  |  | #REF! | [14 empty] | SOV
03-1900 | 03 | 1900 | OG9 | POUR CONCRETE NEW BUILDINGS - OG9 | Division 03 | O'DWYER GARDENS - OG9 | 267 | CY | 320.3773 | 85540.7288 |  |  |  |  | #REF! | [14 empty] | SOV
03-1900 | 03 | 1900 | OG10 | POUR CONCRETE NEW BUILDINGS - OG10 | Division 03 | O'DWYER GARDENS - OG10 | 322 | CY | 320.3773 | 103161.4781 |  |  |  |  | #REF! | [14 empty] | SOV
03-1900 | 03 | 1900 | S82 | POUR CONCRETE NEW BUILDINGS - S8 | Division 03 | SITE 8 - S2 | 384 | CY | 320.3773 | 123024.8683 |  |  |  |  | #REF! | [14 empty] | SOV
03-2000 | 03 | 2000 | SG6 | FINISH SLABS - SG6 | Division 03 | SURFSIDE GARDENS - SG6 | 5373 | SF | 2.4864 | 13359.1773 |  |  |  |  | #REF! | [14 empty] | SOV
03-2000 | 03 | 2000 | SG7 | FINISH SLABS - SG7 | Division 03 | SURFSIDE GARDENS - SG7 | 8948 | SF | 2.4864 | 22247.891 |  |  |  |  | #REF! | [14 empty] | SOV
03-2000 | 03 | 2000 | OG8 | FINISH SLABS - OG8 | Division 03 | O'DWYER GARDENS - OG8 | 17400 | SF | 2.4864 | 43262.5507 |  |  |  |  | #REF! | [14 empty] | SOV
03-2000 | 03 | 2000 | OG9 | FINISH SLABS - OG9 | Division 03 | O'DWYER GARDENS - OG9 | 4383 | SF | 2.4864 | 10897.6873 |  |  |  |  | #REF! | [14 empty] | SOV
03-2000 | 03 | 2000 | OG10 | FINISH SLABS - OG10 | Division 03 | O'DWYER GARDENS - OG10 | 6510 | SF | 2.4864 | 16186.1612 |  |  |  |  | #REF! | [14 empty] | SOV
03-2000 | 03 | 2000 | S82 | FINISH SLABS - S8 | Division 03 | SITE 8 - S2 | 6658 | SF | 2.4864 | 16554.1415 |  |  |  |  | #REF! | [14 empty] | SOV
03-2100 | 03 | 2100 | SG1 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG1 | Division 03 | SURFSIDE GARDENS - SG1 | 103 | CY | 275.2868 | 28354.5418 |  |  |  |  | #REF! | [14 empty] | SOV
03-2100 | 03 | 2100 | SG2 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG2 | Division 03 | SURFSIDE GARDENS - SG2 | 76 | CY | 275.2868 | 20921.7978 |  |  |  |  | #REF! | [14 empty] | SOV
03-2100 | 03 | 2100 | SG3 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG3 | Division 03 | SURFSIDE GARDENS - SG3 | 92 | CY | 275.2868 | 25326.3869 |  |  |  |  | #REF! | [14 empty] | SOV
03-2100 | 03 | 2100 | SG4 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG4 | Division 03 | SURFSIDE GARDENS - SG4 | 149 | CY | 275.2868 | 41017.7352 |  |  |  |  | #REF! | [14 empty] | SOV
03-2100 | 03 | 2100 | SG5 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG5 | Division 03 | SURFSIDE GARDENS - SG5 | 139 | CY | 275.2868 | 38264.8671 |  |  |  |  | #REF! | [14 empty] | SOV
03-2100 | 03 | 2100 | OG1 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG1 | Division 03 | O'DWYER GARDENS - OG1 | 56 | CY | 275.2868 | 15416.0616 |  |  |  |  | #REF! | [14 empty] | SOV
03-2100 | 03 | 2100 | OG2 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG2 | Division 03 | O'DWYER GARDENS - OG2 | 57 | CY | 275.2868 | 15691.3484 |  |  |  |  | #REF! | [14 empty] | SOV
03-2100 | 03 | 2100 | OG3 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG3 | Division 03 | O'DWYER GARDENS - OG3 | 57 | CY | 275.2868 | 15691.3484 |  |  |  |  | #REF! | [14 empty] | SOV
03-2100 | 03 | 2100 | OG4 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG4 | Division 03 | O'DWYER GARDENS - OG4 | 57 | CY | 275.2868 | 15691.3484 |  |  |  |  | #REF! | [14 empty] | SOV
03-2100 | 03 | 2100 | OG5 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG5 | Division 03 | O'DWYER GARDENS - OG5 | 57 | CY | 275.2868 | 15691.3484 |  |  |  |  | #REF! | [14 empty] | SOV
03-2100 | 03 | 2100 | OG6 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG6 | Division 03 | O'DWYER GARDENS - OG6 | 173 | CY | 275.2868 | 47624.6188 |  |  |  |  | #REF! | [14 empty] | SOV
03-2100 | 03 | 2100 | S81 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - S8 | Division 03 | SITE 8 - S81 | 389 | CY | 275.2868 | 107086.5705 |  |  |  |  | #REF! | [14 empty] | SOV
03-2200 | 03 | 2200 | SGN | CONCRETE FOOTING FOR SITE FURNISHING - SGN | Division 03 | SURSFIDE GARDENS - NORTH | 18 | CY | 276.2034 | 4971.6612 |  |  |  |  | #REF! | [14 empty] | SOV
03-2200 | 03 | 2200 | SGS | CONCRETE FOOTING FOR SITE FURNISHING - SGS | Division 03 | SURSFIDE GARDENS - SOUTH | 18 | CY | 276.2034 | 4971.6612 |  |  |  |  | #REF! | [14 empty] | SOV
03-2200 | 03 | 2200 | OGE | CONCRETE FOOTING FOR SITE FURNISHING - OGE | Division 03 | O'DWYER GARDENS - EAST | 10 | CY | 276.2034 | 2762.034 |  |  |  |  | #REF! | [14 empty] | SOV
03-2200 | 03 | 2200 | OGW | CONCRETE FOOTING FOR SITE FURNISHING - OGW | Division 03 | O'DWYER GARDENS - WEST | 16 | CY | 276.2034 | 4419.2544 |  |  |  |  | #REF! | [14 empty] | SOV
03-2200 | 03 | 2200 | S81 | CONCRETE FOOTING FOR SITE FURNISHING - S8 | Division 03 | SITE 8 | 18 | CY | 276.2034 | 4971.6612 |  |  |  |  | #REF! | [14 empty] | SOV
03-2300 | 03 | 2300 | SGN | CONCRETE DUCTBANKS - SGN | Division 03 | SURSFIDE GARDENS - NORTH | 158 | CY | 213.5686 | 33743.8388 |  |  |  |  | #REF! | [14 empty] | SOV
03-2300 | 03 | 2300 | SGS | CONCRETE DUCTBANKS - SGS | Division 03 | SURSFIDE GARDENS - SOUTH | 235 | CY | 213.5686 | 50188.621 |  |  |  |  | #REF! | [14 empty] | SOV
03-2300 | 03 | 2300 | OGE | CONCRETE DUCTBANKS - OGE | Division 03 | O'DWYER GARDENS - EAST | 221 | CY | 213.5686 | 47198.6606 |  |  |  |  | #REF! | [14 empty] | SOV
03-2300 | 03 | 2300 | OGW | CONCRETE DUCTBANKS - OGW | Division 03 | O'DWYER GARDENS - WEST | 243 | CY | 213.5686 | 51897.1698 |  |  |  |  | #REF! | [14 empty] | SOV
03-2300 | 03 | 2300 | S8 | CONCRETE DUCTBANKS - S8 | Division 03 | SITE 8 | 150 | CY | 213.5686 | 32035.29 |  |  |  |  | #REF! | [14 empty] | SOV
03-2400 | 03 | 2400 | SGN | CONCRETE SITE RETAINING WALL AND FOOTINGS - SGN | Division 03 | SURSFIDE GARDENS - NORTH | 48 | CY | 439.2592 | 21084.4407 |  |  |  |  | #REF! | [14 empty] | SOV
03-2400 | 03 | 2400 | OGE | CONCRETE SITE RETAINING WALL AND FOOTINGS - OGE | Division 03 | O'DWYER GARDENS - EAST | 63 | CY | 439.2592 | 27673.3284 |  |  |  |  | #REF! | [14 empty] | SOV
03-2400 | 03 | 2400 | OGW | CONCRETE SITE RETAINING WALL AND FOOTINGS OGW | Division 03 | O'DWYER GARDENS - WEST | 60 | CY | 439.2592 | 26355.5509 |  |  |  |  | #REF! | [14 empty] | SOV
03-2500 | 03 | 2500 | SG1 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG1 | Division 03 | SURFSIDE GARDENS - SG1 | 22 | CY | 716.1371 | 15755.0156 |  |  |  |  | #REF! | [14 empty] | SOV
03-2500 | 03 | 2500 | SG2 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG2 | Division 03 | SURFSIDE GARDENS - SG2 | 29 | CY | 716.1371 | 20767.9751 |  |  |  |  | #REF! | [14 empty] | SOV
03-2500 | 03 | 2500 | SG3 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG3 | Division 03 | SURFSIDE GARDENS - SG3 | 36 | CY | 716.1371 | 25780.9347 |  |  |  |  | #REF! | [14 empty] | SOV
03-2500 | 03 | 2500 | SG4 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG4 | Division 03 | SURFSIDE GARDENS - SG4 | 28 | CY | 716.1371 | 20051.8381 |  |  |  |  | #REF! | [14 empty] | SOV
03-2500 | 03 | 2500 | SG5 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG5 | Division 03 | SURFSIDE GARDENS - SG5 | 28 | CY | 716.1371 | 20051.8381 |  |  |  |  | #REF! | [14 empty] | SOV
03-2500 | 03 | 2500 | OG1 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG1 | Division 03 | O'DWYER GARDENS - OG1 | 18 | CY | 716.1371 | 12890.4673 |  |  |  |  | #REF! | [14 empty] | SOV
03-2500 | 03 | 2500 | OG2 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG2 | Division 03 | O'DWYER GARDENS - OG2 | 18 | CY | 716.1371 | 12890.4673 |  |  |  |  | #REF! | [14 empty] | SOV
03-2500 | 03 | 2500 | OG3 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG3 | Division 03 | O'DWYER GARDENS - OG3 | 18 | CY | 716.1371 | 12890.4673 |  |  |  |  | #REF! | [14 empty] | SOV
03-2500 | 03 | 2500 | OG4 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG4 | Division 03 | O'DWYER GARDENS - OG4 | 18 | CY | 716.1371 | 12890.4673 |  |  |  |  | #REF! | [14 empty] | SOV
03-2500 | 03 | 2500 | OG5 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG5 | Division 03 | O'DWYER GARDENS - OG5 | 18 | CY | 716.1371 | 12890.4673 |  |  |  |  | #REF! | [14 empty] | SOV
03-2500 | 03 | 2500 | OG6 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG6 | Division 03 | O'DWYER GARDENS - OG6 | 13 | CY | 716.1371 | 9309.782 |  |  |  |  | #REF! | [14 empty] | SOV
03-2500 | 03 | 2500 | S81 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - S8 | Division 03 | SITE 8 - S81 | 13 | CY | 716.1371 | 9309.782 |  |  |  |  | #REF! | [14 empty] | SOV
03-2600 | 03 | 2600 | SG3 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG3 | Division 03 | SURFSIDE GARDENS - SG3 | 904 | SF | 4.0803 | 3688.6354 |  |  |  |  | #REF! | [14 empty] | SOV
03-2600 | 03 | 2600 | SG4 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG4 | Division 03 | SURFSIDE GARDENS - SG4 | 864 | SF | 4.0803 | 3525.4214 |  |  |  |  | #REF! | [14 empty] | SOV
03-2600 | 03 | 2600 | SG5 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG5 | Division 03 | SURFSIDE GARDENS - SG5 | 750 | SF | 4.0803 | 3060.2617 |  |  |  |  | #REF! | [14 empty] | SOV
03-2600 | 03 | 2600 | OG1 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG1 | Division 03 | O'DWYER GARDENS - OG1 | 650 | SF | 4.0803 | 2652.2268 |  |  |  |  | #REF! | [14 empty] | SOV
03-2600 | 03 | 2600 | OG2 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG2 | Division 03 | O'DWYER GARDENS - OG2 | 650 | SF | 4.0803 | 2652.2268 |  |  |  |  | #REF! | [14 empty] | SOV
03-2600 | 03 | 2600 | OG3 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG3 | Division 03 | O'DWYER GARDENS - OG3 | 650 | SF | 4.0803 | 2652.2268 |  |  |  |  | #REF! | [14 empty] | SOV
03-2600 | 03 | 2600 | OG4 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG4 | Division 03 | O'DWYER GARDENS - OG4 | 675 | SF | 4.0803 | 2754.2355 |  |  |  |  | #REF! | [14 empty] | SOV
03-2600 | 03 | 2600 | OG5 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG5 | Division 03 | O'DWYER GARDENS - OG5 | 650 | SF | 4.0803 | 2652.2268 |  |  |  |  | #REF! | [14 empty] | SOV
03-2600 | 03 | 2600 | OG6 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG6 | Division 03 | O'DWYER GARDENS - OG6 | 820 | SF | 4.0803 | 3345.8861 |  |  |  |  | #REF! | [14 empty] | SOV
03-6000 |  |  | SG3 |  |  |  | 684 | SF |  | 42788.3311 | 181 | SF
03-6000 |  |  | SG4 |  |  |  | 1264.4 | SF |  | 42788.3311 | 181 | SF
03-6000 |  |  | SG5 |  |  |  | 1027.67 | SF |  | 42788.3311 | 181 | SF
03-6000 |  |  | OG1 |  |  |  | 1021.33 | SF |  | 42788.3311 | 181 | SF
03-6000 |  |  | OG2 |  |  |  | 1105.33 | SF |  | 42788.3311 | 181 | SF
03-6000 |  |  | OG3 |  |  |  | 902.67 | SF |  | 42788.3311 | 181 | SF
03-6000 |  |  | OG4 |  |  |  | 1133.73 | SF |  | 42788.3311 | 181 | SF
03-6000 |  |  | OG5 |  |  |  | 782.67 | SF |  | 42788.3311 | 181 | SF
03-6000 |  |  | OG6 |  |  |  | 1050.67 | SF |  | 42788.3311 | 181 | SF
04-1000 | 04 | 1000 | SG1 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG1 | Division 04 | SURFSIDE GARDENS - SG1 | 100 | SF | 3.541 | 354.1 |  |  |  |  | #REF! | [14 empty] | SOV
04-1000 | 04 | 1000 | SG2 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG2 | Division 04 | SURFSIDE GARDENS - SG2 | 90 | SF | 3.541 | 318.69 |  |  |  |  | #REF! | [14 empty] | SOV
04-1000 | 04 | 1000 | SG3 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG3 | Division 04 | SURFSIDE GARDENS - SG3 | 105 | SF | 3.541 | 371.805 |  |  |  |  | #REF! | [14 empty] | SOV
04-1000 | 04 | 1000 | SG4 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG4 | Division 04 | SURFSIDE GARDENS - SG4 | 75 | SF | 3.541 | 265.575 |  |  |  |  | #REF! | [14 empty] | SOV
04-1000 | 04 | 1000 | SG5 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG5 | Division 04 | SURFSIDE GARDENS - SG5 | 75 | SF | 3.541 | 265.575 |  |  |  |  | #REF! | [14 empty] | SOV
04-1000 | 04 | 1000 | OG1 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG1 | Division 04 | O'DWYER GARDENS - OG1 | 110 | SF | 3.541 | 389.51 |  |  |  |  | #REF! | [14 empty] | SOV
04-1000 | 04 | 1000 | OG2 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG2 | Division 04 | O'DWYER GARDENS - OG2 | 110 | SF | 3.541 | 389.51 |  |  |  |  | #REF! | [14 empty] | SOV
04-1000 | 04 | 1000 | OG3 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG3 | Division 04 | O'DWYER GARDENS - OG3 | 110 | SF | 3.541 | 389.51 |  |  |  |  | #REF! | [14 empty] | SOV
04-1000 | 04 | 1000 | OG4 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG4 | Division 04 | O'DWYER GARDENS - OG4 | 110 | SF | 3.541 | 389.51 |  |  |  |  | #REF! | [14 empty] | SOV
04-1000 | 04 | 1000 | OG5 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG5 | Division 04 | O'DWYER GARDENS - OG5 | 110 | SF | 3.541 | 389.51 |  |  |  |  | #REF! | [14 empty] | SOV
07-1000 | 07 | 1000 | SG6 | HIGH DENSITY STYROFOAM INFILL NEW BLDGS - SG6 | Division 07 | SURFSIDE GARDENS - SG6 | 5 | CF | 56.9717 | 0 | [19 empty] | SUBCONTRACTOR SCOPE
07-1000 | 07 | 1000 | SG7 | HIGH DENSITY STYROFOAM INFILL NEW BLDGS - SG7 | Division 07 | SURFSIDE GARDENS - SG7 | 5 | CF | 56.9717 | 0 | [19 empty] | SUBCONTRACTOR SCOPE
07-1000 | 07 | 1000 | OG8 | HIGH DENSITY STYROFOAM INFILL NEW BLDGS - OG8 | Division 07 | O'DWYER GARDENS - OG8 | 5 | CF | 56.9717 | 0 | [19 empty] | SUBCONTRACTOR SCOPE
07-1000 | 07 | 1000 | OG9 | HIGH DENSITY STYROFOAM INFILL NEW BLDGS - OG9 | Division 07 | O'DWYER GARDENS - OG9 | 5 | CF | 56.9717 | 0 | [19 empty] | SUBCONTRACTOR SCOPE
07-1000 | 07 | 1000 | OG10 | HIGH DENSITY STYROFOAM INFILL NEW BLDGS - OG10 | Division 07 | O'DWYER GARDENS - OG10 | 5 | CF | 56.9717 | 0 | [19 empty] | SUBCONTRACTOR SCOPE
07-1000 | 07 | 1000 | S82 | HIGH DENSITY STYROFOAM INFILL NEW BLDGS - S8 | Division 07 | SITE 8 - S2 | 5 | CF | 56.9717 | 0 | [19 empty] | SUBCONTRACTOR SCOPE
07-1100 | 07 | 1100 | SG6 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - SG6 | Division 07 | SURFSIDE GARDENS - SG6 | 402 | SF | 3.9864 | 1602.5454 |  |  |  |  | #REF! | [14 empty] | SOV
07-1100 | 07 | 1100 | SG7 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - SG7 | Division 07 | SURFSIDE GARDENS - SG7 | 2015 | SF | 3.9864 | 8032.659 |  |  |  |  | #REF! | [14 empty] | SOV
07-1100 | 07 | 1100 | OG8 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG8 | Division 07 | O'DWYER GARDENS - OG8 | 6850 | SF | 3.9864 | 27307.0541 |  |  |  |  | #REF! | [14 empty] | SOV
07-1100 | 07 | 1100 | OG9 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG9 | Division 07 | O'DWYER GARDENS - OG9 | 2800 | SF | 3.9864 | 11162.0075 |  |  |  |  | #REF! | [14 empty] | SOV
07-1100 | 07 | 1100 | OG10 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG10 | Division 07 | O'DWYER GARDENS - OG10 | 3550 | SF | 3.9864 | 14151.8309 |  |  |  |  | #REF! | [14 empty] | SOV
07-1100 | 07 | 1100 | S82 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - S8 | Division 07 | SITE 8 - S2 | 3500 | SF | 3.9864 | 13952.5094 |  |  |  |  | #REF! | [14 empty] | SOV
07-1200 | 07 | 1200 | SG1 | PENETRATION FIRESTOPPING EXTG BLDG - SG1 | Division 07 | SURFSIDE GARDENS - SG1 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1200 | 07 | 1200 | SG2 | PENETRATION FIRESTOPPING EXTG BLDG - SG2 | Division 07 | SURFSIDE GARDENS - SG2 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1200 | 07 | 1200 | SG3 | PENETRATION FIRESTOPPING EXTG BLDG - SG3 | Division 07 | SURFSIDE GARDENS - SG3 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1200 | 07 | 1200 | SG4 | PENETRATION FIRESTOPPING EXTG BLDG - SG4 | Division 07 | SURFSIDE GARDENS - SG4 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1200 | 07 | 1200 | SG5 | PENETRATION FIRESTOPPING EXTG BLDG - SG5 | Division 07 | SURFSIDE GARDENS - SG5 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1200 | 07 | 1200 | OG1 | PENETRATION FIRESTOPPING EXTG BLDG - OG1 | Division 07 | O'DWYER GARDENS - OG1 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1200 | 07 | 1200 | OG2 | PENETRATION FIRESTOPPING EXTG BLDG - OG2 | Division 07 | O'DWYER GARDENS - OG2 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1200 | 07 | 1200 | OG3 | PENETRATION FIRESTOPPING EXTG BLDG - OG3 | Division 07 | O'DWYER GARDENS - OG3 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1200 | 07 | 1200 | OG4 | PENETRATION FIRESTOPPING EXTG BLDG - OG 4 | Division 07 | O'DWYER GARDENS - OG4 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1200 | 07 | 1200 | OG5 | PENETRATION FIRESTOPPING EXTG BLDG - OG 5 | Division 07 | O'DWYER GARDENS - OG5 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1200 | 07 | 1200 | OG6 | PENETRATION FIRESTOPPING EXTG BLDG - OG6 | Division 07 | O'DWYER GARDENS - OG6 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1200 | 07 | 1200 | S81 | PENETRATION FIRESTOPPING EXTG BLDG - S8 | Division 07 | SITE 8 - S81 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1300 | 07 | 1300 | SG6 | PENETRATION FIRESTOPPING NEW BLDG - SG6 | Division 07 | SURFSIDE GARDENS - SG6 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1300 | 07 | 1300 | SG7 | PENETRATION FIRESTOPPING NEW BLDG - SG7 | Division 07 | SURFSIDE GARDENS - SG7 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1300 | 07 | 1300 | OG8 | PENETRATION FIRESTOPPING NEW BLDG - OG8 | Division 07 | O'DWYER GARDENS - OG8 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1300 | 07 | 1300 | OG9 | PENETRATION FIRESTOPPING NEW BLDG - OG9 | Division 07 | O'DWYER GARDENS - OG9 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1300 | 07 | 1300 | OG10 | PENETRATION FIRESTOPPING NEW BLDG - OG10 | Division 07 | O'DWYER GARDENS - OG10 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1300 | 07 | 1300 | S82 | PENETRATION FIRESTOPPING NEW BLDG - S8 | Division 07 | SITE 8 - S2 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1400 | 07 | 1400 | SG1 | JOINT SEALANTS EXTG BLDGS - SG1 | Division 07 | SURFSIDE GARDENS - SG1 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1400 | 07 | 1400 | SG2 | JOINT SEALANTS EXTG BLDGS - SG2 | Division 07 | SURFSIDE GARDENS - SG2 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1400 | 07 | 1400 | SG3 | JOINT SEALANTS EXTG BLDGS - SG3 | Division 07 | SURFSIDE GARDENS - SG3 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1400 | 07 | 1400 | SG4 | JOINT SEALANTS EXTG BLDGS - SG4 | Division 07 | SURFSIDE GARDENS - SG4 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1400 | 07 | 1400 | SG5 | JOINT SEALANTS EXTG BLDGS - SG5 | Division 07 | SURFSIDE GARDENS - SG5 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1400 | 07 | 1400 | OG1 | JOINT SEALANTS EXTG BLDGS - OG1 | Division 07 | O'DWYER GARDENS - OG1 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1400 | 07 | 1400 | OG2 | JOINT SEALANTS EXTG BLDGS - OG2 | Division 07 | O'DWYER GARDENS - OG2 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1400 | 07 | 1400 | OG3 | JOINT SEALANTS EXTG BLDGS - OG3 | Division 07 | O'DWYER GARDENS - OG3 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1400 | 07 | 1400 | OG4 | JOINT SEALANTS EXTG BLDGS - OG4 | Division 07 | O'DWYER GARDENS - OG4 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1400 | 07 | 1400 | OG5 | JOINT SEALANTS EXTG BLDGS - OG5 | Division 07 | O'DWYER GARDENS - OG5 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1400 | 07 | 1400 | OG6 | JOINT SEALANTS EXTG BLDGS - OG 6 | Division 07 | O'DWYER GARDENS - OG6 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1400 | 07 | 1400 | S81 | JOINT SEALANTS EXTG BLDGS - S8 | Division 07 | SITE 8 - S81 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1500 | 07 | 1500 | SG6 | JOINT SEALANTS NEW BLDGS - S6 | Division 07 | SURFSIDE GARDENS - SG6 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1500 | 07 | 1500 | SG7 | JOINT SEALANTS NEW BLDGS - S7 | Division 07 | SURFSIDE GARDENS - SG7 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1500 | 07 | 1500 | OG8 | JOINT SEALANTS NEW BLDGS - OG8 | Division 07 | O'DWYER GARDENS - OG8 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1500 | 07 | 1500 | OG9 | JOINT SEALANTS NEW BLDGS - OG9 | Division 07 | O'DWYER GARDENS - OG9 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1500 | 07 | 1500 | OG10 | JOINT SEALANTS NEW BLDGS - OG10 | Division 07 | O'DWYER GARDENS - OG10 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
07-1500 | 07 | 1500 | S82 | JOINT SEALANTS NEW BLDGS - S8 | Division 07 | SITE 8 - S2 | 1 | BLDG | 9611.44 | 9611.44 |  |  |  |  | #REF! | [14 empty] | SOV
08-1700 | 08 | 1700 | SG6 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S6 | Division 08 | SURFSIDE GARDENS - SG6 | 6 | EA | 1027.8709 | 6167.2255 |  |  |  |  | #REF! | [14 empty] | SOV
08-1700 | 08 | 1700 | SG7 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S7 | Division 08 | SURFSIDE GARDENS - SG7 | 5 | EA | 1027.8709 | 5139.3545 |  |  |  |  | #REF! | [14 empty] | SOV
08-1700 | 08 | 1700 | OG8 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG8 | Division 08 | O'DWYER GARDENS - OG8 | 7 | EA | 1027.8709 | 7195.0964 |  |  |  |  | #REF! | [14 empty] | SOV
08-1700 | 08 | 1700 | OG9 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG9 | Division 08 | O'DWYER GARDENS - OG9 | 6 | EA | 1027.8709 | 6167.2255 |  |  |  |  | #REF! | [14 empty] | SOV
08-1700 | 08 | 1700 | OG10 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG10 | Division 08 | O'DWYER GARDENS - OG10 | 4 | EA | 1027.8709 | 4111.4836 |  |  |  |  | #REF! | [14 empty] | SOV
08-1700 | 08 | 1700 | S82 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S8 | Division 08 | SITE 8 - S2 | 7 | EA | 1027.8709 | 7195.0964 |  |  |  |  | #REF! | [14 empty] | SOV
08-1800 | 08 | 1800 | SG1 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG1 | Division 08 | SURFSIDE GARDENS - SG1 | 4 | SF | 150.67 | 602.68 |  |  |  |  | #REF! | [14 empty] | SOV
08-1800 | 08 | 1800 | SG2 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG2 | Division 08 | SURFSIDE GARDENS - SG2 | 4 | SF | 150.67 | 602.68 |  |  |  |  | #REF! | [14 empty] | SOV
08-1800 | 08 | 1800 | SG4 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG4 | Division 08 | SURFSIDE GARDENS - SG4 | 4 | SF | 150.67 | 602.68 |  |  |  |  | #REF! | [14 empty] | SOV
08-1800 | 08 | 1800 | SG5 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG5 | Division 08 | SURFSIDE GARDENS - SG5 | 4 | SF | 150.67 | 602.68 |  |  |  |  | #REF! | [14 empty] | SOV
10-1000 | 10 | 1000 | SG6 | FIRE EXTINGUISHERS NEW BLDGS - SG6 | Division 10 | SURFSIDE GARDENS - SG6 | 4 | EA | 612.4214 | 2449.6857 |  |  |  |  | #REF! | [14 empty] | SOV
10-1000 | 10 | 1000 | SG7 | FIRE EXTINGUISHERS NEW BLDGS - SG7 | Division 10 | SURFSIDE GARDENS - SG7 | 1 | EA | 612.4214 | 612.4214 |  |  |  |  | #REF! | [14 empty] | SOV
10-1000 | 10 | 1000 | S82 | FIRE EXTINGUISHERS NEW BLDGS - S8 | Division 10 | O'DWYER GARDENS - OG8 | 2 | EA | 612.4214 | 1224.8429 |  |  |  |  | #REF! | [14 empty] | SOV
10-1100 | 10 | 1100 | SG6 | TOILET ACCESSORIES NEW BLDGS - SG6 | Division 10 | SURFSIDE GARDENS - SG6 | 3 | EA | 788.85 | 2366.55 |  |  |  |  | #REF! | [14 empty] | SOV
10-1100 | 10 | 1100 | SG7 | TOILET ACCESSORIES NEW BLDGS - SG7 | Division 10 | SURFSIDE GARDENS - SG7 | 3 | EA | 788.85 | 2366.55 |  |  |  |  | #REF! | [14 empty] | SOV
10-1100 | 10 | 1100 | OG8 | TOILET ACCESSORIES NEW BLDGS - OG8 | Division 10 | O'DWYER GARDENS - OG8 | 3 | EA | 788.85 | 2366.55 |  |  |  |  | #REF! | [14 empty] | SOV
10-1100 | 10 | 1100 | OG9 | TOILET ACCESSORIES NEW BLDGS - OG9 | Division 10 | O'DWYER GARDENS - OG9 | 3 | EA | 788.85 | 2366.55 |  |  |  |  | #REF! | [14 empty] | SOV
10-1100 | 10 | 1100 | OG10 | TOILET ACCESSORIES NEW BLDGS - OG10 | Division 10 | O'DWYER GARDENS - OG10 | 3 | EA | 788.85 | 2366.55 |  |  |  |  | #REF! | [14 empty] | SOV
10-1200 | 10 | 1200 | SG1 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG1 | Division 10 | SURFSIDE GARDENS - SG1 | 68 | LF | 860.325 | 58502.1007 |  |  |  |  | #REF! | [14 empty] | SOV
10-1200 | 10 | 1200 | SG2 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG2 | Division 10 | SURFSIDE GARDENS - SG2 | 42 | LF | 860.325 | 36133.6505 |  |  |  |  | #REF! | [14 empty] | SOV
10-1200 | 10 | 1200 | SG3 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG3 | Division 10 | SURFSIDE GARDENS - SG3 | 44 | LF | 860.325 | 37854.3005 |  |  |  |  | #REF! | [14 empty] | SOV
10-1200 | 10 | 1200 | SG4 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG4 | Division 10 | SURFSIDE GARDENS - SG4 | 50 | LF | 860.325 | 43016.2505 |  |  |  |  | #REF! | [14 empty] | SOV
10-1200 | 10 | 1200 | SG5 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG5 | Division 10 | SURFSIDE GARDENS - SG5 | 48 | LF | 860.325 | 41295.6005 |  |  |  |  | #REF! | [14 empty] | SOV
10-1200 | 10 | 1200 | OG1 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG1 | Division 10 | O'DWYER GARDENS - OG1 | 56 | LF | 860.325 | 48178.2006 |  |  |  |  | #REF! | [14 empty] | SOV
10-1200 | 10 | 1200 | OG2 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG2 | Division 10 | O'DWYER GARDENS - OG2 | 56 | LF | 860.325 | 48178.2006 |  |  |  |  | #REF! | [14 empty] | SOV
10-1200 | 10 | 1200 | OG3 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG3 | Division 10 | O'DWYER GARDENS - OG3 | 56 | LF | 860.325 | 48178.2006 |  |  |  |  | #REF! | [14 empty] | SOV
10-1200 | 10 | 1200 | OG4 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG4 | Division 10 | O'DWYER GARDENS - OG4 | 56 | LF | 860.325 | 48178.2006 |  |  |  |  | #REF! | [14 empty] | SOV
10-1200 | 10 | 1200 | OG5 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG5 | Division 10 | O'DWYER GARDENS - OG5 | 56 | LF | 860.325 | 48178.2006 |  |  |  |  | #REF! | [14 empty] | SOV
10-1200 | 10 | 1200 | OG6 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG6 | Division 10 | O'DWYER GARDENS - OG6 | 108 | LF | 860.325 | 92915.1012 |  |  |  |  | #REF! | [14 empty] | SOV
10-1200 | 10 | 1200 | S81 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - S8 | Division 10 | SITE 8 - S81 | 298 | LF | 860.325 | 256376.8532 |  |  |  |  | #REF! | [14 empty] | SOV
10-1300 | 10 | 1300 | SG1 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - SG1 | Division 10 | SURFSIDE GARDENS - SG1 | 1 | EA | 26494.145 | 26494.145 |  |  |  |  | #REF! | [14 empty] | SOV
10-1300 | 10 | 1300 | SG2 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - SG2 | Division 10 | SURFSIDE GARDENS - SG2 | 1 | EA | 26494.145 | 26494.145 |  |  |  |  | #REF! | [14 empty] | SOV
10-1300 | 10 | 1300 | OG1 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG1 | Division 10 | O'DWYER GARDENS - OG1 | 2 | EA | 26494.145 | 52988.29 |  |  |  |  | #REF! | [14 empty] | SOV
10-1300 | 10 | 1300 | OG2 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG2 | Division 10 | O'DWYER GARDENS - OG2 | 2 | EA | 26494.145 | 52988.29 |  |  |  |  | #REF! | [14 empty] | SOV
10-1300 | 10 | 1300 | OG3 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG3 | Division 10 | O'DWYER GARDENS - OG3 | 2 | EA | 26494.145 | 52988.29 |  |  |  |  | #REF! | [14 empty] | SOV
10-1300 | 10 | 1300 | OG4 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG4 | Division 10 | O'DWYER GARDENS - OG4 | 2 | EA | 26494.145 | 52988.29 |  |  |  |  | #REF! | [14 empty] | SOV
10-1300 | 10 | 1300 | OG5 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG5 | Division 10 | O'DWYER GARDENS - OG5 | 2 | EA | 26494.145 | 52988.29 |  |  |  |  | #REF! | [14 empty] | SOV
10-1300 | 10 | 1300 | OG6 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG6 | Division 10 | O'DWYER GARDENS - OG6 | 2 | EA | 26494.145 | 52988.29 |  |  |  |  | #REF! | [14 empty] | SOV
10-1400 | 10 | 1400 | SG1 | WINDOW FLOODGATES (8.06 AND 8.14) - SG1 | Division 10 | SURFSIDE GARDENS - SG1 | 112 | LF | 514.8897 | 57667.6482 |  |  |  |  | #REF! | [14 empty] | SOV
10-1400 | 10 | 1400 | SG2 | WINDOW FLOODGATES (8.06 AND 8.14) - SG2 | Division 10 | SURFSIDE GARDENS - SG2 | 131 | LF | 514.8897 | 67450.5528 |  |  |  |  | #REF! | [14 empty] | SOV
10-1400 | 10 | 1400 | SG4 | WINDOW FLOODGATES (8.06 AND 8.14) - SG4 | Division 10 | SURFSIDE GARDENS - SG4 | 19 | LF | 514.8897 | 9782.9046 |  |  |  |  | #REF! | [14 empty] | SOV
10-1400 | 10 | 1400 | SG5 | WINDOW FLOODGATES (8.06 AND 8.14) - SG5 | Division 10 | SURFSIDE GARDENS - SG5 | 44 | LF | 514.8897 | 22655.1475 |  |  |  |  | #REF! | [14 empty] | SOV
10-1400 | 10 | 1400 | S81 | WINDOW FLOODGATES (8.06 AND 8.14) - S8 | Division 10 | SITE 8 - S81 | 81 | LF | 514.8897 | 41706.067 |  |  |  |  | #REF! | [14 empty] | SOV
10-1500 | 10 | 1500 | SG4 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE (8.15) - SG4 | Division 10 | SURFSIDE GARDENS - SG4 | 40 | LF | 2942.1166 | 117684.6629 |  |  |  |  | #REF! | [14 empty] | SOV
10-1500 | 10 | 1500 | SG5 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE (8.15) - SG5 | Division 10 | SURFSIDE GARDENS - SG5 | 40 | LF | 2942.1166 | 117684.6629 |  |  |  |  | #REF! | [14 empty] | SOV
11-1000 | 11 | 1000 | SGN | EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - SGN | Division 11 | SURSFIDE GARDENS - NORTH | 2 | EA | 10295.0171 | 20590.0343 |  |  |  |  | #REF! | [14 empty] | SOV
11-1000 | 11 | 1000 | OGW | EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - OGW | Division 11 | O'DWYER GARDENS - WEST | 2 | EA | 10295.0171 | 20590.0343 |  |  |  |  | #REF! | [14 empty] | SOV
11-1000 | 11 | 1000 | S8 | EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - S8 | Division 11 | SITE 8 | 3 | 0 | 10295.0171 | 30885.0514 |  |  |  |  | #REF! | [14 empty] | SOV
31-1000 | 31 | 1000 | SG1 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG1 | Division 31 | SURFSIDE GARDENS - SG1 | 295 | CY | 59.0681 | 17425.0795 |  |  |  |  | #REF! | [14 empty] | SOV
31-1000 | 31 | 1000 | SG2 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG2 | Division 31 | SURFSIDE GARDENS - SG2 | 180 | CY | 59.0681 | 10632.2519 |  |  |  |  | #REF! | [14 empty] | SOV
31-1000 | 31 | 1000 | SG3 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG3 | Division 31 | SURFSIDE GARDENS - SG3 | 220 | CY | 59.0681 | 12994.9745 |  |  |  |  | #REF! | [14 empty] | SOV
31-1000 | 31 | 1000 | SG4 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG4 | Division 31 | SURFSIDE GARDENS - SG4 | 250 | CY | 59.0681 | 14767.0165 |  |  |  |  | #REF! | [14 empty] | SOV
31-1000 | 31 | 1000 | SG5 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG5 | Division 31 | SURFSIDE GARDENS - SG5 | 250 | CY | 59.0681 | 14767.0165 |  |  |  |  | #REF! | [14 empty] | SOV
31-1000 | 31 | 1000 | OG1 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG1 | Division 31 | O'DWYER GARDENS - OG1 | 160 | CY | 59.0681 | 9450.8906 |  |  |  |  | #REF! | [14 empty] | SOV
31-1000 | 31 | 1000 | OG2 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG2 | Division 31 | O'DWYER GARDENS - OG2 | 160 | CY | 59.0681 | 9450.8906 |  |  |  |  | #REF! | [14 empty] | SOV
31-1000 | 31 | 1000 | OG3 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG3 | Division 31 | O'DWYER GARDENS - OG3 | 160 | CY | 59.0681 | 9450.8906 |  |  |  |  | #REF! | [14 empty] | SOV
31-1000 | 31 | 1000 | OG4 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG4 | Division 31 | O'DWYER GARDENS - OG4 | 160 | CY | 59.0681 | 9450.8906 |  |  |  |  | #REF! | [14 empty] | SOV
31-1000 | 31 | 1000 | OG5 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG5 | Division 31 | O'DWYER GARDENS - OG5 | 160 | CY | 59.0681 | 9450.8906 |  |  |  |  | #REF! | [14 empty] | SOV
31-1000 | 31 | 1000 | OG6 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG6 | Division 31 | O'DWYER GARDENS - OG6 | 280 | CY | 59.0681 | 16539.0585 |  |  |  |  | #REF! | [14 empty] | SOV
31-1000 | 31 | 1000 | S81 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - S8 | Division 31 | SITE 8 - S81 | 1060 | CY | 59.0681 | 62612.1499 |  |  |  |  | #REF! | [14 empty] | SOV
31-1100 | 31 | 1100 | SG1 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG1 | Division 31 | SURFSIDE GARDENS - SG1 | 180 | CY | 35.1076 | 6319.3688 |  |  |  |  | #REF! | [14 empty] | SOV
31-1100 | 31 | 1100 | SG2 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG2 | Division 31 | SURFSIDE GARDENS - SG2 | 120 | CY | 35.1076 | 4212.9126 |  |  |  |  | #REF! | [14 empty] | SOV
31-1100 | 31 | 1100 | SG3 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG3 | Division 31 | SURFSIDE GARDENS - SG3 | 150 | CY | 35.1076 | 5266.1407 |  |  |  |  | #REF! | [14 empty] | SOV
31-1100 | 31 | 1100 | SG4 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG4 | Division 31 | SURFSIDE GARDENS - SG4 | 180 | CY | 35.1076 | 6319.3688 |  |  |  |  | #REF! | [14 empty] | SOV
31-1100 | 31 | 1100 | SG5 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG5 | Division 31 | SURFSIDE GARDENS - SG5 | 180 | CY | 35.1076 | 6319.3688 |  |  |  |  | #REF! | [14 empty] | SOV
31-1100 | 31 | 1100 | OG1 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG1 | Division 31 | O'DWYER GARDENS - OG1 | 95 | CY | 35.1076 | 3335.2224 |  |  |  |  | #REF! | [14 empty] | SOV
31-1100 | 31 | 1100 | OG2 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG2 | Division 31 | O'DWYER GARDENS - OG2 | 95 | CY | 35.1076 | 3335.2224 |  |  |  |  | #REF! | [14 empty] | SOV
31-1100 | 31 | 1100 | OG3 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG3 | Division 31 | O'DWYER GARDENS - OG3 | 95 | CY | 35.1076 | 3335.2224 |  |  |  |  | #REF! | [14 empty] | SOV
31-1100 | 31 | 1100 | OG4 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG4 | Division 31 | O'DWYER GARDENS - OG4 | 95 | CY | 35.1076 | 3335.2224 |  |  |  |  | #REF! | [14 empty] | SOV
31-1100 | 31 | 1100 | OG5 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG5 | Division 31 | O'DWYER GARDENS - OG5 | 95 | CY | 35.1076 | 3335.2224 |  |  |  |  | #REF! | [14 empty] | SOV
31-1100 | 31 | 1100 | OG6 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG6 | Division 31 | O'DWYER GARDENS - OG6 | 150 | CY | 35.1076 | 5266.1407 |  |  |  |  | #REF! | [14 empty] | SOV
31-1100 | 31 | 1100 | S81 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - S8 | Division 31 | SITE 8 - S81 | 690 | CY | 35.1076 | 24224.2472 |  |  |  |  | #REF! | [14 empty] | SOV
31-1200 | 31 | 1200 | SG1 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG1 | Division 31 | SURFSIDE GARDENS - SG1 | 19 | CY | 58.1133 | 1104.1525 |  |  |  |  | #REF! | [14 empty] | SOV
31-1200 | 31 | 1200 | SG2 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG2 | Division 31 | SURFSIDE GARDENS - SG2 | 7 | CY | 58.1133 | 406.793 |  |  |  |  | #REF! | [14 empty] | SOV
31-1200 | 31 | 1200 | SG3 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG3 | Division 31 | SURFSIDE GARDENS - SG3 | 9 | CY | 58.1133 | 523.0196 |  |  |  |  | #REF! | [14 empty] | SOV
31-1200 | 31 | 1200 | SG4 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG4 | Division 31 | SURFSIDE GARDENS - SG4 | 9 | CY | 58.1133 | 523.0196 |  |  |  |  | #REF! | [14 empty] | SOV
31-1200 | 31 | 1200 | SG5 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG5 | Division 31 | SURFSIDE GARDENS - SG5 | 9 | CY | 58.1133 | 523.0196 |  |  |  |  | #REF! | [14 empty] | SOV
31-1200 | 31 | 1200 | OG1 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG1 | Division 31 | O'DWYER GARDENS - OG1 | 17 | CY | 58.1133 | 987.926 |  |  |  |  | #REF! | [14 empty] | SOV
31-1200 | 31 | 1200 | OG2 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG2 | Division 31 | O'DWYER GARDENS - OG2 | 17 | CY | 58.1133 | 987.926 |  |  |  |  | #REF! | [14 empty] | SOV
31-1200 | 31 | 1200 | OG3 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG3 | Division 31 | O'DWYER GARDENS - OG3 | 17 | CY | 58.1133 | 987.926 |  |  |  |  | #REF! | [14 empty] | SOV
31-1200 | 31 | 1200 | OG4 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG4 | Division 31 | O'DWYER GARDENS - OG4 | 17 | CY | 58.1133 | 987.926 |  |  |  |  | #REF! | [14 empty] | SOV
31-1200 | 31 | 1200 | OG5 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG5 | Division 31 | O'DWYER GARDENS - OG5 | 17 | CY | 58.1133 | 987.926 |  |  |  |  | #REF! | [14 empty] | SOV
31-1200 | 31 | 1200 | OG6 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG6 | Division 31 | O'DWYER GARDENS - OG6 | 17 | CY | 58.1133 | 987.926 |  |  |  |  | #REF! | [14 empty] | SOV
31-1200 | 31 | 1200 | S81 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - S8 | Division 31 | SITE 8 - S81 | 6 | CY | 58.1133 | 348.6798 |  |  |  |  | #REF! | [14 empty] | SOV
31-1300 | 31 | 1300 | SG6 | EXCAVATION NEW BLDGS - SG6 | Division 31 | SURFSIDE GARDENS - SG6 | 624 | CY | 44.1655 | 27559.3021 |  |  |  |  | #REF! | [14 empty] | SOV
31-1300 | 31 | 1300 | SG7 | EXCAVATION NEW BLDGS - SG7 | Division 31 | SURFSIDE GARDENS - SG7 | 695 | CY | 44.1655 | 30695.056 |  |  |  |  | #REF! | [14 empty] | SOV
31-1300 | 31 | 1300 | OG8 | EXCAVATION NEW BLDGS - OG8 | Division 31 | O'DWYER GARDENS - OG8 | 1400 | CY | 44.1655 | 61831.7675 |  |  |  |  | #REF! | [14 empty] | SOV
31-1300 | 31 | 1300 | OG9 | EXCAVATION NEW BLDGS - OG9 | Division 31 | O'DWYER GARDENS - OG9 | 1150 | CY | 44.1655 | 50790.3804 |  |  |  |  | #REF! | [14 empty] | SOV
31-1300 | 31 | 1300 | OG10 | EXCAVATION NEW BLDGS - OG10 | Division 31 | O'DWYER GARDENS - OG10 | 1310 | CY | 44.1655 | 57856.8681 |  |  |  |  | #REF! | [14 empty] | SOV
31-1300 | 31 | 1300 | S82 | EXCAVATION NEW BLDGS - S8 | Division 31 | SITE 8 - S2 | 1150 | CY | 44.1655 | 50790.3804 |  |  |  |  | #REF! | [14 empty] | SOV
31-1400 | 31 | 1400 | SG6 | BACKFILL NEW BLDGS - SG6 | Division 31 | SURFSIDE GARDENS - SG6 | 432 | CY | 35.1686 | 15192.8563 |  |  |  |  | #REF! | [14 empty] | SOV
31-1400 | 31 | 1400 | SG7 | BACKFILL NEW BLDGS - SG7 | Division 31 | SURFSIDE GARDENS - SG7 | 431 | CY | 35.1686 | 15157.6876 |  |  |  |  | #REF! | [14 empty] | SOV
31-1400 | 31 | 1400 | OG8 | BACKFILL NEW BLDGS - OG8 | Division 31 | O'DWYER GARDENS - OG8 | 880 | CY | 35.1686 | 30948.4109 |  |  |  |  | #REF! | [14 empty] | SOV
31-1400 | 31 | 1400 | OG9 | BACKFILL NEW BLDGS - OG9 | Division 31 | O'DWYER GARDENS - OG9 | 900 | CY | 35.1686 | 31651.7839 |  |  |  |  | #REF! | [14 empty] | SOV
31-1400 | 31 | 1400 | OG10 | BACKFILL NEW BLDGS - OG10 | Division 31 | O'DWYER GARDENS - OG10 | 950 | CY | 35.1686 | 33410.2163 |  |  |  |  | #REF! | [14 empty] | SOV
31-1400 | 31 | 1400 | S82 | BACKFILL NEW BLDGS - S8 | Division 31 | SITE 8 - S2 | 840 | CY | 35.1686 | 29541.665 |  |  |  |  | #REF! | [14 empty] | SOV
31-1500 | 31 | 1500 | OG8 | STONE FOR FOUNDATION - OG8 |  | O'DWYER GARDENS - OG8 | 104 | CY | 58.1107 | 6043.5169 |  |  |  |  | #REF! | [14 empty] | SOV
31-1500 | 31 | 1500 | OG9 | STONE FOR FOUNDATION - OG9 |  | O'DWYER GARDENS - OG9 | 104 | CY | 58.1107 | 6043.5169 |  |  |  |  | #REF! | [14 empty] | SOV
31-1500 | 31 | 1500 | OG10 | STONE FOR FOUNDATION - OG10 |  | O'DWYER GARDENS - OG10 | 104 | CY | 58.1107 | 6043.5169 |  |  |  |  | #REF! | [14 empty] | SOV
31-1700 | 31 | 1700 | SG6 | DEWATERING FOR NEW BUILDINGS - SG6 | Division 31 | SURFSIDE GARDENS - SG6 | 1.2 | MO | 29301.25 | 35161.5 |  |  |  |  | #REF! | [14 empty] | SOV
31-1700 | 31 | 1700 | SG7 | DEWATERING FOR NEW BUILDINGS - SG7 | Division 31 | SURFSIDE GARDENS - SG7 | 1.2 | MO | 29301.25 | 35161.5 |  |  |  |  | #REF! | [14 empty] | SOV
31-1700 | 31 | 1700 | OG8 | DEWATERING FOR NEW BUILDINGS - OG8 | Division 31 | O'DWYER GARDENS - OG8 | 1.2 | MO | 29301.25 | 35161.5 |  |  |  |  | #REF! | [14 empty] | SOV
31-1700 | 31 | 1700 | OG9 | DEWATERING FOR NEW BUILDINGS - OG9 | Division 31 | O'DWYER GARDENS - OG9 | 1.2 | MO | 29301.25 | 35161.5 |  |  |  |  | #REF! | [14 empty] | SOV
31-1700 | 31 | 1700 | OG10 | DEWATERING FOR NEW BUILDINGS - OG10 | Division 31 | O'DWYER GARDENS - OG10 | 1.2 | MO | 29301.25 | 35161.5 |  |  |  |  | #REF! | [14 empty] | SOV
31-1700 | 31 | 1700 | S82 | DEWATERING FOR NEW BUILDINGS - S8 | Division 31 | SITE 8 - S2 | 1.2 | MO | 29301.25 | 35161.5 |  |  |  |  | #REF! | [14 empty] | SOV
31-1800 | 31 | 1800B | SG6 | DRIVE PILES AND INSTALL LAGGING FOR SOE - SG6 | Division 31 | SURFSIDE GARDENS - SG6 | 549 | SF | 52.5504 | 28850.1916 |  |  |  |  | #REF! | [14 empty] | SOV
31-1800 | 31 | 1800B | SG7 | DRIVE PILES AND INSTALL LAGGING FOR SOE - SG7 | Division 31 | SURFSIDE GARDENS - SG7 | 549 | SF | 52.5504 | 28850.1916 |  |  |  |  | #REF! | [14 empty] | SOV
31-1800 | 31 | 1800B | OG8 | DRIVE PILES AND INSTALL LAGGING FOR SOE - OG8 | Division 31 | O'DWYER GARDENS - OG8 | 1097 | SF | 52.5504 | 57647.8328 |  |  |  |  | #REF! | [14 empty] | SOV
31-1800 | 31 | 1800B | OG10 | DRIVE PILES AND INSTALL LAGGING FOR SOE - OG10 | Division 31 | O'DWYER GARDENS - OG10 | 549 | SF | 52.5504 | 28850.1916 |  |  |  |  | #REF! | [14 empty] | SOV
31-1800 | 31 | 1800B | S82 | DRIVE PILES AND INSTALL LAGGING FOR SOE - S8 | Division 31 | SITE 8 - S2 | 1097 | SF | 52.5504 | 57647.8328 |  |  |  |  | #REF! | [14 empty] | SOV
31-1900 | 31 | 1900 | SGN | TREE PROTECTION - SGN | Division 31 | SURSFIDE GARDENS - NORTH | 28 | EA | 173.9719 | 4871.2119 |  |  |  |  | #REF! | [14 empty] | SOV
31-1900 | 31 | 1900 | SGS | TREE PROTECTION - SGS | Division 31 | SURSFIDE GARDENS - SOUTH | 17 | EA | 173.9719 | 2957.5215 |  |  |  |  | #REF! | [14 empty] | SOV
31-1900 | 31 | 1900 | OGE | TREE PROTECTION - OGE | Division 31 | O'DWYER GARDENS - EAST | 28 | EA | 173.9719 | 4871.2119 |  |  |  |  | #REF! | [14 empty] | SOV
31-1900 | 31 | 1900 | OGW | TREE PROTECTION - OGW | Division 31 | O'DWYER GARDENS - WEST | 48 | EA | 173.9719 | 8350.6489 |  |  |  |  | #REF! | [14 empty] | SOV
31-1900 | 31 | 1900 | S8 | TREE PROTECTION - S8 | Division 31 | SITE 8 | 14 | EA | 173.9719 | 2435.6059 |  |  |  |  | #REF! | [14 empty] | SOV
31-2000 | 31 | 2000 | SGN | HAND EXCAVATION AS NEEDED - SGN | Division 31 | SURSFIDE GARDENS - NORTH | 150 | CY | 110.1522 | 16522.824 |  |  |  |  | #REF! | [14 empty] | SOV
31-2000 | 31 | 2000 | SGS | HAND EXCAVATION AS NEEDED - SGS | Division 31 | SURSFIDE GARDENS - SOUTH | 160 | CY | 110.1522 | 17624.3456 |  |  |  |  | #REF! | [14 empty] | SOV
31-2000 | 31 | 2000 | OGE | HAND EXCAVATION AS NEEDED - OGE | Division 31 | O'DWYER GARDENS - EAST | 280 | CY | 110.1522 | 30842.6048 |  |  |  |  | #REF! | [14 empty] | SOV
31-2000 | 31 | 2000 | OGW | HAND EXCAVATION AS NEEDED - OGW | Division 31 | O'DWYER GARDENS - WEST | 660 | CY | 110.1522 | 72700.4256 |  |  |  |  | #REF! | [14 empty] | SOV
31-2000 | 31 | 2000 | S8 | HAND EXCAVATION AS NEEDED - S8 | Division 31 | SITE 8 | 400 | CY | 110.1522 | 44060.864 |  |  |  |  | #REF! | [14 empty] | SOV
31-2100 | 31 | 2100 | SGN | EXCAVATION FOR SITE FURNISHING FOOTINGS - SGN | Division 31 | SURSFIDE GARDENS - NORTH | 82 | CY | 41.8113 | 3428.524 |  |  |  |  | #REF! | [14 empty] | SOV
31-2100 | 31 | 2100 | SGS | EXCAVATION FOR SITE FURNISHING FOOTINGS - SGS | Division 31 | SURSFIDE GARDENS - SOUTH | 82 | CY | 41.8113 | 3428.524 |  |  |  |  | #REF! | [14 empty] | SOV
31-2100 | 31 | 2100 | OGE | EXCAVATION FOR SITE FURNISHING FOOTINGS - OGE | Division 31 | O'DWYER GARDENS - EAST | 82 | CY | 41.8113 | 3428.524 |  |  |  |  | #REF! | [14 empty] | SOV
31-2100 | 31 | 2100 | OGW | EXCAVATION FOR SITE FURNISHING FOOTINGS - OGW | Division 31 | O'DWYER GARDENS - WEST | 82 | CY | 41.8113 | 3428.524 |  |  |  |  | #REF! | [14 empty] | SOV
31-2100 | 31 | 2100 | S8 | EXCAVATION FOR SITE FURNISHING FOOTINGS - S8 | Division 31 | SITE 8 | 82 | CY | 41.8113 | 3428.524 |  |  |  |  | #REF! | [14 empty] | SOV
31-2200 | 31 | 2200 | SGN | BACKFILL - SGN | Division 31 | SURSFIDE GARDENS - NORTH | 2735 | CY | 47.0976 | 128811.9526 |  |  |  |  | #REF! | [14 empty] | SOV
31-2200 | 31 | 2200 | SGS | BACKFILL - SGS | Division 31 | SURSFIDE GARDENS - SOUTH | 3475 | CY | 47.0976 | 163664.1811 |  |  |  |  | #REF! | [14 empty] | SOV
31-2200 | 31 | 2200 | OGE | BACKFILL - OGE | Division 31 | O'DWYER GARDENS - EAST | 3955 | CY | 47.0976 | 186271.032 |  |  |  |  | #REF! | [14 empty] | SOV
31-2200 | 31 | 2200 | OGW | BACKFILL - OGW | Division 31 | O'DWYER GARDENS - WEST | 3487 | CY | 47.0976 | 164229.3523 |  |  |  |  | #REF! | [14 empty] | SOV
31-2200 | 31 | 2200 | S8 | BACKFILL - S8 | Division 31 | SITE 8 | 2522 | CY | 47.0976 | 118780.1625 |  |  |  |  | #REF! | [14 empty] | SOV
31-2300 | 31 | 2300 | OGE | EXCAVATE FOR ASPHALT PAVEMENTS - OGE | Division 31 | O'DWYER GARDENS - EAST | 300 | CY | 59.069 | 17720.7051 |  |  |  |  | #REF! | [14 empty] | SOV
31-2300 | 31 | 2300 | OGW | EXCAVATE FOR ASPHALT PAVEMENTS - OGW | Division 31 | O'DWYER GARDENS - WEST | 300 | CY | 59.069 | 17720.7051 |  |  |  |  | #REF! | [14 empty] | SOV
31-2300 | 31 | 2300 | S8 | EXCAVATE FOR ASPHALT PAVEMENTS - S8 | Division 31 | SITE 8 | 100 | CY | 59.069 | 5906.9017 |  |  |  |  | #REF! | [14 empty] | SOV
31-2400 | 31 | 2400 | OGE | BACKFILL FOR ASPHALT PAVEMENTS - OGE | Division 31 | O'DWYER GARDENS - EAST | 235 | CY | 35.105 | 8249.6834 |  |  |  |  | #REF! | [14 empty] | SOV
31-2400 | 31 | 2400 | OGW | BACKFILL FOR ASPHALT PAVEMENTS - OGW | Division 31 | O'DWYER GARDENS - WEST | 100 | CY | 35.105 | 3510.5036 |  |  |  |  | #REF! | [14 empty] | SOV
31-2400 | 31 | 2400 | S8 | BACKFILL FOR ASPHALT PAVEMENTS - S8 | Division 31 | SITE 8 | 100 | CY | 35.105 | 3510.5036 |  |  |  |  | #REF! | [14 empty] | SOV
31-2500 | 31 | 2500 | SG6 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - SG6 | Division 31 | SURFSIDE GARDENS - SG6 | 280 | CY | 81.7993 | 22903.8133 |  |  |  |  | #REF! | [14 empty] | SOV
31-2500 | 31 | 2500 | SG7 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - SG7 | Division 31 | SURFSIDE GARDENS - SG7 | 280 | CY | 81.7993 | 22903.8133 |  |  |  |  | #REF! | [14 empty] | SOV
31-2500 | 31 | 2500 | OG8 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG8 | Division 31 | O'DWYER GARDENS - OG8 | 280 | CY | 81.7993 | 22903.8133 |  |  |  |  | #REF! | [14 empty] | SOV
31-2500 | 31 | 2500 | OG9 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG9 | Division 31 | O'DWYER GARDENS - OG9 | 280 | CY | 81.7993 | 22903.8133 |  |  |  |  | #REF! | [14 empty] | SOV
31-2500 | 31 | 2500 | OG10 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG10 | Division 31 | O'DWYER GARDENS - OG10 | 280 | CY | 81.7993 | 22903.8133 |  |  |  |  | #REF! | [14 empty] | SOV
31-2500 | 31 | 2500 | S82 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - S8 | Division 31 | SITE 8 - S2 | 280 | CY | 81.7993 | 22903.8133 |  |  |  |  | #REF! | [14 empty] | SOV
31-2600 | 31 | 2600 | SGN | SITE FURNISHINGS - SGN | Division 31 | SURSFIDE GARDENS - NORTH | 20 | EA | 1557.559 | 31151.1795 |  |  |  |  | #REF! | [14 empty] | SOV
31-2600 | 31 | 2600 | SGS | SITE FURNISHINGS - SGS | Division 31 | SURSFIDE GARDENS - SOUTH | 40 | EA | 1557.559 | 62302.359 |  |  |  |  | #REF! | [14 empty] | SOV
31-2600 | 31 | 2600 | OGE | SITE FURNISHINGS - OGE | Division 31 | O'DWYER GARDENS - EAST | 25 | EA | 1557.559 | 38938.9744 |  |  |  |  | #REF! | [14 empty] | SOV
31-2600 | 31 | 2600 | OGW | SITE FURNISHINGS - OGW | Division 31 | O'DWYER GARDENS - WEST | 17 | EA | 1557.559 | 26478.5026 |  |  |  |  | #REF! | [14 empty] | SOV
31-2600 | 31 | 2600 | S8 | SITE FURNISHINGS - S8 | Division 31 | SITE 8 | 15 | EA | 1557.559 | 23363.3846 |  |  |  |  | #REF! | [14 empty] | SOV
31-2700 | 31 | 2700 | SGS | BOLLARDS - SGS | Division 31 | SURSFIDE GARDENS - SOUTH | 8 | EA | 1627.1 | 13016.8 |  |  |  |  | #REF! | [14 empty] | SOV
31-2800 | 31 | 2800 | SGN | DRINKING FOUNTAIN - SGN | Division 31 | SURSFIDE GARDENS - NORTH | 2 | EA | 6708.4 | 13416.8 |  |  |  |  | #REF! | [14 empty] | SOV
31-2800 | 31 | 2800 | SGS | DRINKING FOUNTAIN - SGS | Division 31 | SURSFIDE GARDENS - SOUTH | 1 | EA | 6708.4 | 6708.4 |  |  |  |  | #REF! | [14 empty] | SOV
31-2800 | 31 | 2800 | OGE | DRINKING FOUNTAIN - OGE | Division 31 | O'DWYER GARDENS - EAST | 1 | EA | 6708.4 | 6708.4 |  |  |  |  | #REF! | [14 empty] | SOV
31-2800 | 31 | 2800 | OGW | DRINKING FOUNTAIN - OGW | Division 31 | O'DWYER GARDENS - WEST | 1 | EA | 6708.4 | 6708.4 |  |  |  |  | #REF! | [14 empty] | SOV
31-2800 | 31 | 2800 | S8 | DRINKING FOUNTAIN - S8 | Division 31 | SITE 8 | 1 | EA | 6708.4 | 6708.4 |  |  |  |  | #REF! | [14 empty] | SOV
31-2900 | 31 | 2900 | SGN | LANDSCAPE BOULDERS - SGN | Division 31 | SURSFIDE GARDENS - NORTH | 11 | EA | 1695.9795 | 18655.7741 |  |  |  |  | #REF! | [14 empty] | SOV
31-2900 | 31 | 2900 | OGW | LANDSCAPE BOULDERS - OGW | Division 31 | O'DWYER GARDENS - WEST | 137 | EA | 1695.9795 | 232349.1859 |  |  |  |  | #REF! | [14 empty] | SOV
31-3000 | 31 | 3000 | OGE | BASKETBALL BACKSTOP - OGE | Division 31 |  | 2 | EA | 4618.16 | 9236.32 | 2 | EA | 2401EC | 32 | 3296.32 | 1648.16 | 5340 | 2670 | 0 | 0 | 600 | 300 | 0 | 0 |  | 0 | 0 | 4618.16 | 9236.32 | SOV |  | 0
33-1000 | 33 | 1000 | SGN | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 1 | LOC | 13605.32 | 13605.32 |  |  |  |  | #REF! | [14 empty] | SOV
33-1000 | 33 | 1000 | SGS | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 1 | LOC | 13605.32 | 13605.32 |  |  |  |  | #REF! | [14 empty] | SOV
33-1000 | 33 | 1000 | OGE | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - OGE | Division 33 | O'DWYER GARDENS - EAST | 1 | LOC | 13605.32 | 13605.32 |  |  |  |  | #REF! | [14 empty] | SOV
33-1000 | 33 | 1000 | OGW | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - OGW | Division 33 | O'DWYER GARDENS - WEST | 1 | LOC | 13605.32 | 13605.32 |  |  |  |  | #REF! | [14 empty] | SOV
33-1000 | 33 | 1000 | S8 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - S8 | Division 33 | SITE 8 | 1 | LOC | 13605.32 | 13605.32 |  |  |  |  | #REF! | [14 empty] | SOV
33-1100 | 33 | 1100 | SGN | TERMINATE AND DEMOLISH EXISTING UTILITIES - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 950 | LF | 22.6755 | 21541.7567 |  |  |  |  | #REF! | [14 empty] | SOV
33-1100 | 33 | 1100 | SGS | TERMINATE AND DEMOLISH EXISTING UTILITIES - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 982 | LF | 22.6755 | 22267.3737 |  |  |  |  | #REF! | [14 empty] | SOV
33-1100 | 33 | 1100 | OGE | TERMINATE AND DEMOLISH EXISTING UTILITIES - OGE | Division 33 | O'DWYER GARDENS - EAST | 334 | LF | 22.6755 | 7573.6281 |  |  |  |  | #REF! | [14 empty] | SOV
33-1100 | 33 | 1100 | OGW | TERMINATE AND DEMOLISH EXISTING UTILITIES - OGW | Division 33 | O'DWYER GARDENS - WEST | 770 | LF | 22.6755 | 17460.1607 |  |  |  |  | #REF! | [14 empty] | SOV
33-1100 | 33 | 1100 | S8 | TERMINATE AND DEMOLISH EXISTING UTILITIES - S8 | Division 33 | SITE 8 | 263 | LF | 22.6755 | 5963.6653 |  |  |  |  | #REF! | [14 empty] | SOV
33-1400 | 33 | 1400 | SGN | INSTALL HW, CW PIPE - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 988 | EA | 341.7915 | 337690.0238 |  |  |  |  | #REF! | [14 empty] | SOV
33-1400 | 33 | 1400 | SGS | INSTALL HW, CW PIPE - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 1237 | EA | 341.7915 | 422796.1127 |  |  |  |  | #REF! | [14 empty] | SOV
33-1400 | 33 | 1400 | OGE | INSTALL HW, CW PIPE - OGE | Division 33 | O'DWYER GARDENS - EAST | 568 | EA | 341.7915 | 194137.5845 |  |  |  |  | #REF! | [14 empty] | SOV
33-1400 | 33 | 1400 | OGW | INSTALL HW, CW PIPE - OGW | Division 33 | O'DWYER GARDENS - WEST | 1109 | EA | 341.7915 | 379046.7979 |  |  |  |  | #REF! | [14 empty] | SOV
33-1700 | 33 | 1700 | SGN | TEST HW, CW - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 4 | EA | 3673.0463 | 14692.185 |  |  |  |  | #REF! | [14 empty] | SOV
33-1700 | 33 | 1700 | SGS | TEST HW, CW - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 5 | EA | 3673.0463 | 18365.2313 |  |  |  |  | #REF! | [14 empty] | SOV
33-1700 | 33 | 1700 | OGE | TEST HW, CW - OGE | Division 33 | O'DWYER GARDENS - EAST | 2 | EA | 3673.0463 | 7346.0925 |  |  |  |  | #REF! | [14 empty] | SOV
33-1700 | 33 | 1700 | OGW | TEST HW, CW - OGW | Division 33 | O'DWYER GARDENS - WEST | 5 | EA | 3673.0463 | 18365.2313 |  |  |  |  | #REF! | [14 empty] | SOV
33-2000 | 33 | 2000 | SGN | INSTALL CONDENSATE AND STEAM PIPE - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 622 | EA | 414.3621 | 257733.2298 |  |  |  |  | #REF! | [14 empty] | SOV
33-2000 | 33 | 2000 | SGS | INSTALL CONDENSATE AND STEAM PIPE - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 1042 | EA | 414.3621 | 431765.3142 |  |  |  |  | #REF! | [14 empty] | SOV
33-2000 | 33 | 2000 | OGE | INSTALL CONDENSATE AND STEAM PIPE - OGE | Division 33 | O'DWYER GARDENS - EAST | 862 | EA | 414.3621 | 357180.1352 |  |  |  |  | #REF! | [14 empty] | SOV
33-2000 | 33 | 2000 | OGW | INSTALL CONDENSATE AND STEAM PIPE - OGW | Division 33 | O'DWYER GARDENS - WEST | 1256 | EA | 414.3621 | 520438.8049 |  |  |  |  | #REF! | [14 empty] | SOV
33-2000 | 33 | 2000 | S8 | INSTALL CONDENSATE AND STEAM PIPE - S8 | Division 33 | SITE 8 | 113 | EA | 414.3621 | 46822.918 |  |  |  |  | #REF! | [14 empty] | SOV
33-2300 | 33 | 2300 | SGN | TEST CONDENSATE, STEAM - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 2 | EA | 5408.1414 | 10816.2829 |  |  |  |  | #REF! | [14 empty] | SOV
33-2300 | 33 | 2300 | SGS | TEST CONDENSATE, STEAM - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 3 | EA | 5408.1414 | 16224.4243 |  |  |  |  | #REF! | [14 empty] | SOV
33-2300 | 33 | 2300 | OGE | TEST CONDENSATE, STEAM - OGE | Division 33 | O'DWYER GARDENS - EAST | 3 | EA | 5408.1414 | 16224.4243 |  |  |  |  | #REF! | [14 empty] | SOV
33-2300 | 33 | 2300 | OGW | TEST CONDENSATE, STEAM - OGW | Division 33 | O'DWYER GARDENS - WEST | 5 | EA | 5408.1414 | 27040.7071 |  |  |  |  | #REF! | [14 empty] | SOV
33-2300 | 33 | 2300 | S8 | TEST CONDENSATE, STEAM - S8 | Division 33 | SITE 8 | 1 | EA | 5408.1414 | 5408.1414 |  |  |  |  | #REF! | [14 empty] | SOV
33-2400 | 33 | 2400 | SGN | DEWATERING FOR UTILITY WORK - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 1.6 | MO | 29301.25 | 46882 |  |  |  |  | #REF! | [14 empty] | SOV
33-2400 | 33 | 2400 | SGS | DEWATERING FOR UTILITY WORK - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 1.6 | MO | 29301.25 | 46882 |  |  |  |  | #REF! | [14 empty] | SOV
33-2400 | 33 | 2400 | OGE | DEWATERING FOR UTILITY WORK - OGE | Division 33 | O'DWYER GARDENS - EAST | 1.6 | MO | 29301.25 | 46882 |  |  |  |  | #REF! | [14 empty] | SOV
33-2400 | 33 | 2400 | OGW | DEWATERING FOR UTILITY WORK - OGW | Division 33 | O'DWYER GARDENS - WEST | 1.6 | MO | 29301.25 | 46882 |  |  |  |  | #REF! | [14 empty] | SOV
33-2400 | 33 | 2400 | S8 | DEWATERING FOR UTILITY WORK - S8 | Division 33 | SITE 8 | 1.6 | MO | 29301.25 | 46882 |  |  |  |  | #REF! | [14 empty] | SOV
33-2500 | 33 | 2500 | SGN | SEWER / DRAINAGE PIPE - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 699 | LF | 180.9042 | 126452.0495 |  |  |  |  | #REF! | [14 empty] | SOV
33-2500 | 33 | 2500 | SGS | SEWER / DRAINAGE PIPE - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 615 | LF | 180.9042 | 111256.095 |  |  |  |  | #REF! | [14 empty] | SOV
33-2500 | 33 | 2500 | OGE | SEWER / DRAINAGE PIPE - OGE | Division 33 | O'DWYER GARDENS - EAST | 1028 | LF | 180.9042 | 185969.5377 |  |  |  |  | #REF! | [14 empty] | SOV
33-2500 | 33 | 2500 | OGW | SEWER / DRAINAGE PIPE - OGW | Division 33 | O'DWYER GARDENS - WEST | 869 | LF | 180.9042 | 157205.7668 |  |  |  |  | #REF! | [14 empty] | SOV
33-2500 | 33 | 2500 | S8 | SEWER / DRAINAGE PIPE - S8 | Division 33 | SITE 8 | 588 | LF | 180.9042 | 106371.6811 |  |  |  |  | #REF! | [14 empty] | SOV
33-2600 | 33 | 2600 | SGN | CATCH BASIN DRAINS AND CONNECTIONS - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 19 | EA | 7298.74 | 138676.06 |  |  |  |  | #REF! | [14 empty] | SOV
33-2600 | 33 | 2600 | SGS | CATCH BASIN DRAINS AND CONNECTIONS - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 9 | EA | 7298.74 | 65688.66 |  |  |  |  | #REF! | [14 empty] | SOV
33-2600 | 33 | 2600 | OGE | CATCH BASIN DRAINS AND CONNECTIONS - OGE | Division 33 | O'DWYER GARDENS - EAST | 18 | EA | 7298.74 | 131377.32 |  |  |  |  | #REF! | [14 empty] | SOV
33-2600 | 33 | 2600 | OGW | CATCH BASIN DRAINS AND CONNECTIONS - OGW | Division 33 | O'DWYER GARDENS - WEST | 15 | EA | 7298.74 | 109481.1 |  |  |  |  | #REF! | [14 empty] | SOV
33-2600 | 33 | 2600 | S8 | CATCH BASIN DRAINS AND CONNECTIONS - S8 | Division 33 | SITE 8 | 8 | EA | 7298.74 | 58389.92 |  |  |  |  | #REF! | [14 empty] | SOV
33-2800 | 33 | 2800 | OGE | DRAINAGE MANHOLES - OGE | Division 33 | O'DWYER GARDENS - EAST | 2 | EA | 14197.48 | 28394.96 |  |  |  |  | #REF! | [14 empty] | SOV
33-2900 | 33 | 2900 | SGN | REMOVE AREA DRAINS - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 2 | EA | 2332.77 | 4665.54 |  |  |  |  | #REF! | [14 empty] | SOV
33-2900 | 33 | 2900 | SGS | REMOVE AREA DRAINS - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 2 | EA | 2332.77 | 4665.54 |  |  |  |  | #REF! | [14 empty] | SOV
33-2900 | 33 | 2900 | OGE | REMOVE AREA DRAINS - OGE | Division 33 | O'DWYER GARDENS - EAST | 5 | EA | 2332.77 | 11663.85 |  |  |  |  | #REF! | [14 empty] | SOV
33-2900 | 33 | 2900 | OGW | REMOVE AREA DRAINS - OGW | Division 33 | O'DWYER GARDENS - WEST | 4 | EA | 2332.77 | 9331.08 |  |  |  |  | #REF! | [14 empty] | SOV
33-2900 | 33 | 2900 | S8 | REMOVE AREA DRAINS - S8 | Division 33 | SITE 8 | 5 | EA | 2332.77 | 11663.85 |  |  |  |  | #REF! | [14 empty] | SOV
33-3000 | 33 | 3000 | SGN | ELECTRICAL MANHOLES - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 1 | EA | 5315.54 | 5315.54 |  |  |  |  | #REF! | [14 empty] | SOV
33-3000 | 33 | 3000 | SGS | ELECTRICAL MANHOLES - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 5 | EA | 5315.54 | 26577.7 |  |  |  |  | #REF! | [14 empty] | SOV
33-3000 | 33 | 3000 | OGE | ELECTRICAL MANHOLES - OGE | Division 33 | O'DWYER GARDENS - EAST | 2 | EA | 5315.54 | 10631.08 |  |  |  |  | #REF! | [14 empty] | SOV
33-3000 | 33 | 3000 | S8 | ELECTRICAL MANHOLES - S8 | Division 33 | SITE 8 | 1 | EA | 5315.54 | 5315.54 |  |  |  |  | #REF! | [14 empty] | SOV
33-3100 | 33 | 3100 | SGN | ELECTRICAL CONDUIT TRENCHES - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 6432 | LF | 107.1749 | 37939.9107 |  |  |  |  | #REF! | [14 empty] | SOV
33-3100 | 33 | 3100 | SGS | ELECTRICAL CONDUIT TRENCHES - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 3174 | LF | 107.1749 | 51443.9467 |  |  |  |  | #REF! | [14 empty] | SOV
33-3100 | 33 | 3100 | OGE | ELECTRICAL CONDUIT TRENCHES - OGE | Division 33 | O'DWYER GARDENS - EAST | 6289 | LF | 107.1749 | 76201.3461 |  |  |  |  | #REF! | [14 empty] | SOV
33-3100 | 33 | 3100 | OGW | ELECTRICAL CONDUIT TRENCHES - OGW | Division 33 | O'DWYER GARDENS - WEST | 7663 | LF | 107.1749 | 64626.4581 |  |  |  |  | #REF! | [14 empty] | SOV
33-3100 | 33 | 3100 | S8 | ELECTRICAL CONDUIT TRENCHES - S8 | Division 33 | SITE 8 | 1000 | LF | 107.1749 | 32795.5161 |  |  |  |  | #REF! | [14 empty] | SOV
33-3300 | 33 | 3300 | SGN | CRANE SUPPORT FOR SITE - SGN | Division 33 | SURSFIDE GARDENS - NORTH | 2.5 | MO | 56058.7333 | 140146.8333 |  |  |  |  | #REF! | [14 empty] | SOV
33-3300 | 33 | 3300 | SGS | CRANE SUPPORT FOR SITE - SGS | Division 33 | SURSFIDE GARDENS - SOUTH | 2.5 | MO | 56058.7333 | 140146.8333 |  |  |  |  | #REF! | [14 empty] | SOV
33-3300 | 33 | 3300 | OGE | CRANE SUPPORT FOR SITE - OGE | Division 33 | O'DWYER GARDENS - EAST | 2.5 | MO | 56058.7333 | 140146.8333 |  |  |  |  | #REF! | [14 empty] | SOV
33-3300 | 33 | 3300 | OGW | CRANE SUPPORT FOR SITE - OGW | Division 33 | O'DWYER GARDENS - WEST | 2.5 | MO | 56058.7333 | 140146.8333 |  |  |  |  | #REF! | [14 empty] | SOV
33-3300 | 33 | 3300 | S8 | CRANE SUPPORT FOR SITE - S8 | Division 33 | SITE 8 | 2.5 | MO | 56058.7333 | 140146.8333 |  |  |  |  | #REF! | [14 empty] | SOV